## BOQ
RUNNING BILL NO 1
TR Air-conditioning Retrofitting Works
Deustche Bank
at Dolmen Sky Towers, Karachi.
[5 empty] | MATERIAL |  | LABOUR |  | TOTAL | Billed Qty | Billed Amount
Sr. No. |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT | RATE | AMOUNT | AMOUNT
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Cutting, dismantling of existing water cooled package unit including pipes, valves, accessories, duct, allied works etc, complete in all respect including cleaning the site and shifting the dismantled parts / material to suitable place given by client complete in all respects ready to operate as per instruction of client & consultant. (Note; contractor should check / verify dismantling works as per site requirement). | Job. | 1 | 0 | 0 | 30000 | 30000 | 30000 | 1 | 30000
2 |  | Supply & installation of water cooled package unit with lindaptor type supports, including hanger steel base, vibration isolators, including interconnecting power & control wiring connections with inlet & outlet cooling water connections (including pipe), drain connection (including pipe), flexible rubber duct connection / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant. | Job. | 1 | 650000 | 650000 | 30000 | 30000 | 680000 | 1 | 680000
3 |  | Supply & installation of valves & accessories of water cooled package units, complete in all respects as per specifications, drawings and as per instructions of consultant.
| 3.1 | Ball Valve
| i. | 38mm dia | Nos. | 4 | 17500 | 70000 | 2000 | 8000 | 78000 | 4 | 78000
| 3.2 | Strainer
| i. | 38mm dia | No. | 1 | 11500 | 11500 | 2000 | 2000 | 13500 | 1 | 13500
| 3.3 | Balancing Valve (with self sealing measuring nipples)
| i. | 38mm dia | No. | 1 | 22000 | 22000 | 2000 | 2000 | 24000 | 1 | 24000
| 3.4 | Flexible pipe connectors
| i. | 38mm dia | Nos. | 2 | 12000 | 24000 | 2000 | 4000 | 28000 | 2 | 28000
| 3.5 | Digital Flow Meter-Ultrasonic Type with display and ports for connections. | Nos. | 1 | 365000 | 365000 | 5000 | 5000 | 370000 | 0 | 0
| 3.6 | Pressure Switch | No. | 1 | 25000 | 25000 | 5000 | 5000 | 30000 | 1 | 30000
4 |  | Supply, fabrication and installation of machine made G.I sheet metal duct including plenums, splitter dampers, guide vanes, flexible duct connector / connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction of Consultant. (6 ~ 7 Sqm Approx.) | Job. | 1 | 95000 | 95000 | 25000 | 25000 | 120000 | 1 | 120000
5 |  | Supply & installation of 20mm thick adhesive rubber foam (XLPE) insulation with aluminum foil over fresh air duct only, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. (6 ~ 7 Sqm Approx.) | Job. | 1 | 95000 | 95000 | 25000 | 25000 | 120000 | 1 | 120000
6 |  | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant.
| 6.1 | Grills
| i. | 450mm x 250mm | Nos. | 2 | 12000 | 24000 | 2000 | 4000 | 28000 | 2 | 28000
7 |  | Supply and installation of Fire Damper with linkage & fuse complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant.
| 7.1 | 450mm x 250mm | No. | 1 | 11500 | 11500 | 2000 | 2000 | 13500 | 1 | 13500
8 |  | Testing, balancing and commissioning of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 10000 | 10000 | 30000 | 30000 | 40000 | 1 | 40000
9 |  | Making of Shop drawings on Auto CAD (latest version) with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 10000 | 10000 | 15000 | 15000 | 25000 | 1 | 25000
10 |  | Removing and reinstallation of existing 2x2 ceiling | Job. | 1 | N/A | N/A |  | 0 | 0
|  | Total Cost of Works Rs. |  |  |  | 1413000 |  | 187000 | 1600000 |  | 1230000
Note:
1) | Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
2) | Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).