## Summary
Bill of Quantities
SR. # |  |  | Amount
1- | HVAC Work | Rs. | 2409640
2- | Fire Fighting Work | Rs. | 2715106.52
Grand Total Rs. |  |  | 5124746.52
409979.7216
4714766.7984

## HVAC-BOQ
Bill of Quantities
Heating Ventilation & Air Conditioning Services
Generation Store | [9 empty] | Rev.00
Dolmen Mall Lahore | [9 empty] | Date: 19-02-2024
S # | Description | Bill of Quantities |  |  |  | Running Bill No 1
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labour Rate | Bill Qty | Amount | Bill Qty | Amount
1 | All Heating, Ventilation & Air Conditioning Services shall be completed, tested and commissioned as per drawings, specifications and as per Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Sqm | 135 | 6000 | 1000 | 173.8 | 1042800 | 173.8 | 173800 | 1216600
2 | Supply and Installation of aluminum foil facing fiber glass (24 kg/m3 density) insulation 1" thick for G.I. sheet metal ducts of different sections with Aluminum tape protected with 8oz canvas cloth than painted anti fungus paint compete in all respect as per specifications, drawings and as per instructions of Consultant. | Sqm | 130 | 2200 | 600 | 173.8 | 382360 | 173.8 | 104280 | 486640
3 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. Supply & Return Air Diffuser | Sqm | 1 | 55000 | 5000 | 1 | 55000 | 1 | 5000 | 60000
3.1 | Supply & Return Air Diffuser | Sqm | 1 | 55000 | 5000 | 1 | 55000 | 1 | 5000 | 60000
3.2 i. | Fresh & Ehaust Air Grill 250x250 mm | No. | 3 | 4800 | 1000 | 3 | 14400 | 3 | 3000 | 17400
ii. | 900x200 mm | No. | 1 | 8000 | 1000 | 1 | 8000 | 1 | 1000 | 9000
3.3 i. | Round Diffusers 14" Dia | Nos. | 20 | 11000 | 100 | 20 | 220000 | 20 | 2000 | 222000
4 | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqm | 1 | 55000 | 5000 | 1.5 | 82500 | 1.5 | 7500 | 90000
5 | Supply and Installation of Acoustical duct sound liner in supply air duct complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqm | 15 | 5000 | 1000 | 12.5 | 62500 | 12.5 | 12500 | 75000
6 | Supply, installation of Fire Damper with gas kits, nut bolts complete in all respects ready to operate as per specification, drawings and as per instructions of Consultant. | Sqm | 1 | 48000 | 5000 | 1 | 48000 | 1 | 5000 | 53000
7 | Painting & Identification work on supports, hangers, base of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Job. | 1 | 20000 | 20000 | 1 | 20000 | 1 | 20000 | 40000
8 | Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 10000 | 30000 | 1 | 10000 | 1 | 30000 | 40000
9 | Making of Shop drawings & As.built drawings on Auto CAD 2016 with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 20000 | 20000 | 1 | 20000 | 1 | 20000 | 40000
| Total Cost of HVAC Works Rs. | [5 empty] | 2020560 |  | 389080 | 2409640
Note: 1) Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work. 2) Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).

## FF-BOQ
Bill of Quantities
Fire Suppression Services
Generation Store | [9 empty] | Rev.01
Dolmen Mall, Lahore | [9 empty] | Date: 05-03-2024
S # | Description | Bill of Quantities |  |  |  | Running Bill No 1
[6 empty] | Material |  | Labour |  | Total Amount
|  | Unit | Qty | Material Rate | Labour Rate | Bill Qty | Amount | Bill Qty | Amount
FIRE FIGHTING SERVICES Supply, installation, testing & commissioning of fire suppression system including all equipment, pipe works and accessories ready to operate as per specifications, drawings and instructions of Consultants.
1 | MS Sch-40 seamless pipes including all specials M.I & D.I threaded & machenical joint threaded & grooved fittings UL listed FM approved, flexible pipe, flanges, coupling, masking plates, bends, tees, clamps, supports and hangers, sleeves, masking plates chiseling, cutting holes, making good where required, painting and protection treatment etc. Complete in all respects.
i | Dia 25mm | Meter | 125 | 2850 | 1000 | 166.5 | 474525 | 166.5 | 166500 | 641025
ii | Dia 32mm | Meter | 95 | 3560 | 1200 | 36.449 | 129758.44 | 36.449 | 43738.8 | 173497.24
iii | Dia 40mm | Meter | 15 | 4250 | 1300 | 3.67 | 15597.5 | 3.67 | 4771 | 20368.5
iv | Dia 50mm | Meter | 20 | 5560 | 1400 | 9.13 | 50762.8 | 9.13 | 12782 | 63544.8
v | Dia 65mm | Meter | 20 | 9450 | 1500 | 5.85 | 55282.5 | 5.85 | 8775 | 64057.5
vi | Dia 75mm | Meter | 90 | 11200 | 1700 | 15.68 | 175616 | 15.68 | 26656 | 202272
vii | Dia 100mm | Meter | 20 | 16222 | 2000 | 18.34 | 297511.48 | 18.34 | 36680 | 334191.48
2 i. | Sprinkler Heads Sprinkler Upright type K = 5.6 (Opening Temperature 68ºC) | Nos. | 56 | 4500 | 750 | 51 | 229500 | 51 | 38250 | 267750
ii | Sprinkler Pendent type (concealed with face / Cover plate) K = 5.6 (Opening Temperature 68ºC) | Nos. | 51 | 8900 | 800 | 47 | 418300 | 47 | 37600 | 455900
3 i | Check valve with matching flanges. Dia. 4" | Nos. | 2 | 127000 | 5000 | 2 | 254000 | 2 | 10000 | 264000
4 i | Fire extinguishers with fixing accessories. Type Class B&C FX-3 (6 Kg. CO2 Carbon Dioxide Gas) | No. | 1 | 29000 | 1000 | 1 | 29000 | 1 | 1000 | 30000
ii | Type Class A,B&C FX-4 (6 Kg. Dry Chemical Powder) | No. | 1 | 17500 | 1000 | 1 | 17500 | 1 | 1000 | 18500
5 | Submittals, samples, shop drawings, inspections, As- built drawings, operation and maintenance manuals and the like as required by specifications. | Job. | 1 | 10000 | 15000 | 1 | 10000 | 1 | 15000 | 25000
6 | Painting, identification and tagging to the installations and equipments. | Job. | 1 | 40000 | 40000 | 1 | 40000 | 1 | 40000 | 80000
7 | Flushing of entire fire pipe work according to (NFPA- 13). | Job. | 1 | 15000 | 30000 | 1 | 15000 | 1 | 30000 | 45000
8 | Testing, and commissioning of entire fire fighting installation as per Consultant's approval. | Job. | 1 |  | 30000 | 1 | 0 | 1 | 30000 | 30000
| Total Cost of Fire Suppression Services Rs. | [5 empty] | 2212353.72 |  | 502752.8 | 2715106.52
Note:
1) Contractor is instructed to visit the site, understand the nature of work & then fill the rates accordingly and submit the quotation. No argument and discussion will be entertained after awarding of work.
2) Miscellaneous work which was not included in BOQ but necessary to complete the project in all respects and ready to operate as per instructions of Consultant. (Bidder should mentioned the type of works).