## HVAC
[6 empty] | Date | 08 Aug 2024
[6 empty] | Quote # | 002
Attn: Mr. Taha Ghaznavi
Quotation for Extra work to be carried out for VRF Outdoor units - Gul Ahmed 7th Floor Tijarah Center Karachi
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Labour Amount
1 | Making existing as built drawings of VRF system. | Job | 1 | 0 | 15000 | 0 | 15000
2 | Removal of installed indoor units wall mounted / cassette type | Nos | 20 | 0 | 7000 | 0 | 140000
a) Dismantle of evaporator coil from indoor unit.
b) Wash with Karchar pump
c) Pressurized with nitrogen and test leak.
d) Satisfaction of leak test reassembled evaporator coil.
e) Clean all body and related parts.
f) Reassemble with evaporator coil and assembled whole unit.
g) Reassemble with evaporator coil and assembled whole unit.
3 | Reinstallation of wall mounted / cassette units at their new desired location. | Nos | 32 | 0 | 5000 | 0 | 160000
4 | Supply and installation of isolation valve for indoor units (Gas + Liquid) |  |  |  |  | 0 | 0
| a) 1/4" Dia | Nos | 18 | 10000 | 2000 | 180000 | 36000
| b) 3/8" Dia | Nos | 7 | 11280 | 2000 | 78960 | 14000
| c) 1/2" Dia | Nos | 19 | 11875 | 2000 | 225625 | 38000
| d) 5/8" Dia | Nos | 7 | 13125 | 2000 | 91875 | 14000
| e) 3/4" Dia | No | 1 | 25625 | 2000 | 25625 | 2000
5 | After installation of copper piping, flushing with nitrogen and freon. | Cir | 2 | 50000 | 20000 | 100000 | 40000
6 | Dismantle of copper pipes, power / controls cable from VRF condensing units. | Unit | 5 |  | 8000 | 0 | 40000
7 | Regging, liftings and shifting of VRF condensing unit at new location. | Nos | 4 | 0 | 5000 | 0 | 20000
8 | Providing and installation of motorized damper for fresh air units. 24 x 10 | No | 1 | 80000 | 5000 | 80000 | 5000
Sub Total Amount Rs | [5 empty] | 782085 | 524000
Total Amount Rs | [6 empty] | 1306085
Total Amount Rs
Note: Room or space required for keeping removed units with Lock and key.
For PIONEER ENGINEERING SERVICES

## eee
|  |  |  | Date | 29 June 2024
|  |  |  | Quotation # | 001
Attn: Mr. Taha Ghaznavi
Quotation
Extra work to be carried out for VRF Outdoor units - Gul Ahmed 7th Floor Tijarah Center Karachi
S. # | Description | Unit | Qty | Rate | Amount
1 | Removal of installaed indoor units service/ pressure tesr of evaporator coil re assebled and reintall adter wood work | Nos | 32 | 10000 | 320000
| Supply and installation of isolation valve for indoor units (Gas + Liquid) |  |  |  | 0
| Making existing as built drawings of VRF system. | Job | 1 | 25000 | 25000
| Makind new piping layout tree for Gree (copper sizing) of system | Job | 1 | 25000 | 25000
5 | Removal Reinstallation of GI sheet metal ducts with new fittings hanger & supports. |  |  |  | 0
6 | Providing and fixing of flexible duct connector for condenser discharge. | Rft | 800 | 6000 | 4800000
1 | Dismantle of copper refrigerent pipes electric power cable control wiring from condensing units. | Job | 1 | 1001 | 1001
2 | Remove all of existing exhaust air ducts |  |  | 1002 | 0
3 | Regging lifting and shifitng of VRF condensing units at new location. |  |  | 1003 | 0
4 | Providing and installation of Newpron pads for condensing units. |  |  | 1004 | 0
9 | Providing an installation of fresh air fans 8000 CFM for condensing units. |  |  | 1009 | 0
9 | Removal of refixing of cable tray. |  |  | 1010 | 0
Total Amount Rs |  |  |  |  | 1001
Note: Copper pipe and new GI Ducts rates already in BOQ, charged accordingly.
Terms & Conditions: 1) Above prices are exclusive of SST 2) Scaffolding included for installation of Platform.
For PIONEER ENGINEERING SERVICES