## SUMMARY
GRAND SUMMARY
ENGRO 7TH FLOOR)
S.NO | DESCRIPTION | SUPPLY AMOUNT | INSTALLATION AMOUNT | TOTAL AMOUNT
| HVAC | 9456570.9 | 1840771.8 | 11297342.7
| Fire fighting | 5598489.6 | 668295 | 6266784.6
| Plumbing | 524277 | 341986.25 | 866263.25
| BMS | 2471300 | 320500 | 2791800
| GRAND TOTAL AMOUNT | 18050637.5 | 3171553.05 | 21222190.55
|  | Variations |  | 1430752.6
|  | Total |  | 22652943.15
|  | Add 4.5% |  | 1019382.4418
|  | Grand Total |  | 23672325.5918
|  | Received |  | 8508670
|  | Receivalbe Amount |  | 15163655.5918

## HVAC 7F
SECTION III/A: BILL OF QUANTITIES FOR HVAC WORKS (LEVEL-07)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 6 | 7
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost | Rate | Amount
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7 | 6 | 6 x 4
AIR CONDITIONING AND VENTILATION SYSTEM
| 23 82 19 | Supply, installation, Testing & Commissioning of Ceiling Suspended WCP Units complete with hanger Supports, Vibration Isolator as per drawing and specification.
A |  | WCP-7F-01 | 1 | No. | 0 | 0 | 45000 | 45000 | 45000
B |  | Automatic Air Vent | 1 | No. | 8100 | 8100 | 1800 | 1800 | 9900
C |  | Temperature Sensor | 2 | Nos. | 19800 | 39600 | 1800 | 3600 | 43200
|  | Flexible Connectors |  |  | 0 |  | 0 | 0
D |  | 1-1/4 inch | 2 | Nos. | 9450 | 18900 | 1800 | 3600 | 22500
E |  | Pressure guages | 2 | Nos. | 9900 | 19800 | 900 | 1800 | 21600
|  | Strainer |  |  | 0 |  | 0 | 0
F |  | 1-1/4 inch | 2 | Nos. | 12600 | 25200 | 900 | 1800 | 27000
|  | Double Regulating Valve |  |  | 0 |  | 0 | 0
G |  | 1-1/4 inch | 1 | No. | 19800 | 19800 | 900 | 900 | 20700
|  | Gate Valve |  |  | 0 |  | 0 | 0 | 0
H |  | 1-1/4 inch | 2 | Nos. | 12150 | 24300 | 900 | 1800 | 26100
I |  | 3/4 inch | 1 | No. | 7650 | 7650 | 900 | 900 | 8550
|  | Sub Total (Page 1) |  |  |  | 163350 |  | 61200 | 224550
Supply, Installation & Commissioning of Exhaust Fans with wire mesh as per drawings, schedule & specifications.
A |  | EF-7F-01 | 1 | No. | 765000 | 765000 | 2700 | 2700 | 767700
|  | Installation and Comissioning of Fresh Air Handling Units, complete in all respects with necessary fittings and as per schedule, drawings and specifications. |  |  | 0 |  | 0 | 0 | 0
B |  | FAHU-7F-01 | 1 | No. | 0 | 0 | 13500 | 13500 | 13500
| 23 31 00 | Supply, Installation and Commissioning of G.I Sheet metal air ducts as per ASHRAE Standards plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings as per drawings and specification. |  |  | 0 |  | 0 | 0 | 0
|  | Ducting |  |  | 0 |  | 0 | 0 | 0
C |  | 24 Gauge | 4855 | Sq.ft | 405 | 1966275 | 76.5 | 371407.5 | 2337682.5
D |  | 22 Gauge | 1495 | Sq.ft | 423 | 632385 | 76.5 | 114367.5 | 746752.5
E |  | 18 Gauge | 134 | Sq.ft | 612 | 82008 | 76.5 | 10251 | 92259
F | 23 07 00 | Supply, Installation & Commissioning of Closed cell elastromeric Insulation of thickness for G.I Ducts required as per drawings and specifications. | 6610 | Sq.ft | 549 | 3628890 | 63 | 416430 | 4045320
G |  | Colored Wrapping for ducts | 6610 | Sq.ft | 76.5 | 505665 | 22.5 | 148725 | 654390
| 23 33 46 | Supply, installation and Commissioning of flexible ducts complete in all respects as per schedule, drawings and specifications. |  |  | 0 |  | 0 | 0 | 0
H |  | 8" Diameter | 14.3 | Rft. | 675 | 9652.5 | 72 | 1029.6 | 10682.1
I |  | 6" Diameter | 2.2 | Rft. | 630 | 1386 | 72 | 158.4 | 1544.4
|  | Sub Total (Page 2) |  |  |  | 7591261.5 |  | 1078569 | 8669830.5
| 23 37 13 | Supply, Installation and Commissioning of Air Devices as per drawings, schedules and specifications.
Supply Air Grille
A |  | 24"x16" | 2 | Nos. | 8640 | 17280 | 900 | 1800 | 19080
|  | Return Air Grille |  |  | 0 | 0 | 0 | 0 | 0
B |  | 24"x16" | 2 | Nos. | 8640 | 17280 | 900 | 1800 | 19080
|  | Supply Air Diffuser |  |  | 0 | 0 | 0 | 0 | 0
C |  | 15"x15" | 6 | Nos. | 7200 | 43200 | 900 | 5400 | 48600
D |  | 12"x12" | 6 | Nos. | 5400 | 32400 | 900 | 5400 | 37800
E |  | 18"x18" | 4 | Nos. | 9000 | 36000 | 900 | 3600 | 39600
F |  | 21"x21" | 4 | Nos. | 12150 | 48600 | 900 | 3600 | 52200
|  | Return Air Diffuser |  |  | 0 | 0 | 0 | 0 | 0
G |  | 12"12" | 4 | Nos. | 5400 | 21600 | 900 | 3600 | 25200
|  | Supply Air Register |  |  | 0 | 0 | 0 | 0 | 0
H |  | 12"x12" | 12 | Nos. | 3780 | 45360 | 900 | 10800 | 56160
I |  | 36"x16" | 2 | Nos. | 16650 | 33300 | 900 | 1800 | 35100
|  | Sub Total (Page 3) |  |  |  | 295020 |  | 37800 | 332820
Return Air Register
A |  | 12"x12" | 6 | Nos. | 3780 | 22680 | 900 | 5400 | 28080
B |  | 18"x12" | 6 | Nos. | 6210 | 37260 | 900 | 5400 | 42660
|  | Air Transfer Grill |  |  | 0 | 0 | 0 | 0 | 0
C |  | 12"x12" | 8 | Nos. | 5850 | 46800 | 900 | 7200 | 54000
|  | Exhaust Air Diffuser |  |  | 0 | 0 | 0 | 0 | 0
D |  | 12"x12" | 3 | Nos. | 4320 | 12960 | 900 | 2700 | 15660
|  | Supply Air Linear Slot Diffuser S.A.L.S.D |  |  | 0 | 0 | 0 | 0 | 0
E |  | 2/1"/108" | 1 | No. | 13500 | 13500 | 900 | 900 | 14400
F |  | 2/1"/132" | 2 | Nos. | 14400 | 28800 | 900 | 1800 | 30600
G |  | 3/1"/96" | 2 | Nos. | 12150 | 24300 | 900 | 1800 | 26100
H |  | 3/1"/132" | 1 | No. | 16830 | 16830 | 900 | 900 | 17730
|  | Return Air Linear Slot Diffuser R.A.L.S.D |  |  | 0 | 0 | 0 | 0 | 0
I |  | 1/1"/84" | 2 | Nos. | 7740 | 15480 | 900 | 1800 | 17280
J |  | 2/1"/132" | 3 | Nos. | 14400 | 43200 | 900 | 2700 | 45900
K |  | 3/1"/96" | 2 | Nos. | 13140 | 26280 | 900 | 1800 | 28080
|  | Sub Total (Page 4) |  |  |  | 288090 |  | 32400 | 320490
| 23 33 05 | Supply, installation, Testing & Commissioning of VAVs complete in all respect as per drawing and specification and schedule.
VAVs
A |  | VAV-7F-01 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
B |  | VAV-7F-02 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
C |  | VAV-7F-03 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
D |  | VAV-7F-04 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
E |  | VAV-7F-05 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
F |  | VAV-7F-06 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
G |  | VAV-7F-07 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
H |  | VAV-7F-08 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
I |  | VAV-7F-09 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
J |  | VAV-7F-10 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
K |  | VAV-7F-11 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
L |  | VAV-7F-12 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
M |  | VAV-7F-13 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
N |  | VAV-7F-14 | 1 | No. | 0 | 0 | 6750 | 6750 | 6750
|  | Sub Total (Page 5) |  |  |  | 0 |  | 94500 | 94500
| 23 33 05 | Supply, Installation and Commissioning of Motorised Fire and Smoke Damper for ducts as per SMACNA standards as mentioned in the specifications and drawings.
A |  | 20"x10" | 2 | Nos. | 103500 | 207000 | 9000 | 18000 | 225000
B |  | 24"x8" | 2 | Nos. | 112500 | 225000 | 9000 | 18000 | 243000
|  | Supply, Installation and Commissioning of Volume Damper for ducts as per SMACNA standards as mentioned in the specifications and drawings. |  |  | 0 | 0 | 0 | 0 | 0
C |  | 20"x6" | 1 | No. | 3600 | 3600 | 900 | 900 | 4500
D |  | 10"x6" | 1 | No. | 3150 | 3150 | 900 | 900 | 4050
E |  | 14"x6" | 1 | No. | 2520 | 2520 | 900 | 900 | 3420
F |  | 22"x8" | 3 | Nos. | 3780 | 11340 | 900 | 2700 | 14040
G |  | 14"x8" | 3 | Nos. | 3600 | 10800 | 900 | 2700 | 13500
H |  | 10"x10" | 4 | Nos. | 4050 | 16200 | 900 | 3600 | 19800
I |  | 40"x18" | 1 | No. | 15300 | 15300 | 900 | 900 | 16200
J |  | 20"x14" | 1 | No. | 8100 | 8100 | 900 | 900 | 9000
K |  | 24"x8" | 1 | No. | 5850 | 5850 | 900 | 900 | 6750
L |  | 24"x12" | 1 | No. | 7830 | 7830 | 900 | 900 | 8730
|  | Sub Total (Page 6) |  |  |  | 516690 |  | 51300 | 567990
Supply, Installation and Commissioning of Volume Damper for ducts as per SMACNA standards as mentioned in the specifications and drawings. (Contd.)
A |  | 14"x12" | 1 | No. | 5400 | 5400 | 900 | 900 | 6300
B |  | 20"x8" | 1 | No. | 4950 | 4950 | 900 | 900 | 5850
C |  | 26"x14" | 1 | No. | 8820 | 8820 | 900 | 900 | 9720
D |  | 24"x14" | 1 | No. | 8100 | 8100 | 900 | 900 | 9000
E |  | 16"x12" | 3 | No. | 5400 | 16200 | 900 | 2700 | 18900
F |  | 22"x16" | 1 | No. | 8370 | 8370 | 900 | 900 | 9270
G |  | 22"x14" | 1 | No. | 8820 | 8820 | 900 | 900 | 9720
H |  | 12"x10" | 1 | No. | 3420 | 3420 | 900 | 900 | 4320
|  | Supply, Installation and Commissioning of U-PVC piping with insulation for condensate drain piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications. |  |  | 0 | 0 | 0 | 0 | 0
I |  | 3/4" Diameter | 9.9 | Rft. | 306 | 3029.4 | 72 | 712.8 | 3742.2
|  | Supply, Installation and Commissioning of MS Schedule 40 piping with insulation for Condensate Water piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications. |  |  | 0 | 0 | 0 | 0 | 0
J |  | 1-1/4" Diameter | 55 | Rft. | 900 | 49500 | 198 | 10890 | 60390
K |  | Sound Trap with duct Z-piece and sound lining for return lot air intake. | 17 | Nos. | 7650 | 130050 | 2700 | 45900 | 175950
L |  | Engineering & Programming commissioning testing all above VAVs including Controller and thermostat. | 1 | Lot | 0 | 0 | 180000 | 180000 | 180000
|  | Sub Total (Page 7) |  |  |  | 246659.4 |  | 246502.8 | 493162.2
MISCELLANEOUS
A | 01 46 00 | Supply, Installation & Commissioning of brass tags for Equipment and system including all accessories complete in all respect. | 1 | Job | 22500 | 22500 | 9000 | 9000 | 31500
B | 23 05 48 | Supply, Installation & Commissioning of hangers and supports for pipes and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 247500 | 247500 | 45000 | 45000 | 292500
C | 09 90 00 | Painting on equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 22500 | 22500 | 9000 | 9000 | 31500
D | 23 05 93 23 08 00 | Testing, adjusting, Balancing & Commissioning of HVAC system omplete in all respect. | 1 | Job | 0 | 0 | 135000 | 135000 | 135000
E | 07 84 00 | Supply, Installation and commision of fire stopping materials as per specifications and drawings complete in all respect. | 1 | Job | 45000 | 45000 | 22500 | 22500 | 67500
|  | Drawings |  |  | 0 | 0 | 0 | 0 | 0
F | 01 00 00 23 05 01 | Shop Drawings and As Built Drawings as per specifications. | 1 | Job | 18000 | 18000 | 18000 | 18000 | 36000
|  | Sundries |  |  | 0 | 0 | 0 | 0 | 0
G | 01 00 00 23 05 01 | Supply, installing and Commissioning of items not listed in BOQ but required. | 1 | Job | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0
|  | Sub Total (Page 8) |  |  |  | 355500 |  | 238500 | 594000
|  | GRAND TOTAL FOR HVAC WORKS (LEVEL-07) |  |  |  | 9456570.9 |  | 1840771.8 | 11297342.7
9941661.576

## FF 7F
SECTION III/C: BILL OF QUANTITIES FOR FIRE FIGHTING WORKS (LEVEL-07)
1 | 2 | 3 | 4 |  |  |  | 5 | 6 | 7 | 6 | 7 | 8 | 9 | 10
BOQ No. | Specification Reference | Description | Qty |  |  |  | Unit | Rate | Amount | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 |  |  |  | 5 | 6 | 6 x 4 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7
|  | Fire Fighting |  |  |  | OLD
| 21 11 00 | Supply, install and commission of Mild Steel Schedule 40 pipe including all special fittings and Hangers including the cost of breaking through wall and roof complete in all respects shown on drawings & specifications.
A |  | 4" Diameter | 42.55 | 10 | 5% | 11 | Rft. |  |  | 3672 | 156243.6 | 540 | 22977 | 179220.6
B |  | 3" Diameter | 156.4 | 177 | 5% | 186 | Rft. |  |  | 2583 | 403981.2 | 495 | 77418 | 481399.2
C |  | 2.5" Diameter | 72.45 | 136 | 5% | 143 | Rft. |  |  | 1980 | 143451 | 405 | 29342.25 | 172793.25
D |  | 2" Diameter | 97.75 | 103.6955 | 5% | 109 | Rft. |  |  | 1332 | 130203 | 369 | 36069.75 | 166272.75
E |  | 1.5" Diameter | 41.4 | 78.0965 | 5% | 82 | Rft. |  |  | 990 | 40986 | 270 | 11178 | 52164
F |  | 1.25" Diameter | 82.8 | 38 | 5% | 40 | Rft. |  |  | 891 | 73774.8 | 225 | 18630 | 92404.8
G |  | 1" Diameter | 920 | 633.1785 | 5% | 665 | Rft. |  |  | 711 | 654120 | 189 | 173880 | 828000
| 21 11 00 | Supply, install and commissioning of Sprinklers including all accessories complete in all respects as per drawings & specifications. |  |  |  |  | 6: 0; 8: 0
H |  | Concealed Pendent Sprinkler with Paint Finish (Quick Response) | 39 |  |  | 71 | Nos. |  |  | 7920 | 308880 | 675 | 26325 | 335205
I |  | Upright Sprinkler Head Quick Response | 73 |  |  |  | Nos. |  |  | 5850 | 427050 | 675 | 49275 | 476325
J |  | Corrugated Stainless Steel Flexible Connector 1inch x 3ft (ULFM) | 39 | Nos. |  | Nos. | Nos. |  |  | 11700 | 456300 | 900 | 35100 | 491400
|  | Sub Total (Page 1) |  |  |  |  | 7: 2794989.6; 9: 480195; 10: 3275184.6
| 21 20 00 | Supply, install and commission Fire Extinguisher as per drawing & specification.
A |  | Class-K Type Fire Extinguisher Capacity 6 Litres | 1 |  |  | 1 | No. |  |  | 14850 | 14850 | 900 | 900 | 15750
B |  | Fire Blanket | 2 |  |  | 1 | Nos. |  |  | 7650 | 15300 | 900 | 1800 | 17100
C |  | CO2 Extinguisher Capacity | 1 |  |  | 1 | No. |  |  | 24300 | 24300 | 900 | 900 | 25200
D |  | Dry Powder Extinguisher Capacity | 1 |  |  | 1 | No. |  |  | 14400 | 14400 | 900 | 900 | 15300
| 21 20 00 | Supply, installation, testing & commissioning of FM200 fire supression system with all valves and accessories,control panels,control switches etc:- complete as per drawings & specifications. |  |  |  |  | 6: 0; 8: 0
E |  | I.T Rooms ( Volume=720 ft3) | 1 |  |  | 1 | No. |  |  | 2475000 | 2475000 | 90000 | 90000 | 2565000
|  | Miscellaneous |  |  |  |  | 6: 0; 8: 0
F | 01 46 00 | Supply, Installation & Commissioning of brass tags of 2" dia tags for valves and fixed with chains complete as per drawings & specifications. | 1 |  |  | 1 | Job |  |  | 22500 | 22500 | 4500 | 4500 | 27000
G | 21 11 00 | Supply, Installation & Commissioning of hangers and supports for pipes and Equipments including roller type (if required) as per drawings & specifications. | 1 |  |  | 1 | Job |  |  | 189000 | 189000 | 27000 | 27000 | 216000
H | 07 84 00 | Supply, installation and commision fire stopping aid as per specifications and drawings complete in all respect. | 1 |  |  | 1 | Job |  |  | 31500 | 31500 | 9000 | 9000 | 40500
I | 22 11 00 | Painting of equipment / Hangers, Supports, Pipe etc as per specifications. | 1 |  |  | 1 | Job |  |  | 22500 | 22500 | 9000 | 9000 | 31500
J | 21 05 05 | Testing, adjusting, Balancing & commissioning of Fire Fighting System. | 1 |  |  | 1 | Job |  |  | 0 | 0 | 36000 | 36000 | 36000
|  | Sub Total (Page 2) |  |  |  |  | 7: 2794500; 9: 179100; 10: 2973600
Drawings
A | 21 05 01 | Shop drawings and As Built Drawings as per specifications. | 1 |  |  | 1 | Job |  |  | 9000 | 9000 | 9000 | 9000 | 18000
Sundries
B |  | Supply, installing and commissioning of items not listed in BOQ but required.(Contractors to provide list) | 1 |  |  | 1 | 5: Job
|  | Sub Total (Page 3) |  |  |  |  | 7: 9000; 9: 9000; 10: 18000
|  | GRAND TOTAL FOR FIRE FIGHTING WORKS (LEVEL-07) |  |  |  |  | 7: 5598489.6; 9: 668295; 10: 6266784.6

## Plum 7th
SECTION III/B: BILL OF QUANTITIES FOR PLUMBING WORKS (LEVEL-07)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7
PPR Pipe
| 22 10 00 | Supply, install, testing and commission of PP-R type 3 (fittings PN 20) piping for Cold Water Supply system complete in all respects with all fittings & accessories as per drawings and specifications.
A |  | Ø1-1/4" | 8.05 | Rft. | 990 | 7969.5 | 175 | 1408.75 | 9378.25
B |  | Ø1" | 27.6 | Rft. | 550 | 15180 | 150 | 4140 | 19320
C |  | Ø3/4" | 34.5 | Rft. | 480 | 16560 | 125 | 4312.5 | 20872.5
D |  | Ø1/2" | 33.35 | Rft. | 350 | 11672.5 | 100 | 3335 | 15007.5
Grand-Total for PPR Pipe | [5 empty] | 51382 |  | 13196.25 | 64578.25
UPVC Pipe
| 22 10 00 | Supply, install and commission uPVC to BSEN – 1329 and BS5255 - 1989 piping including all special accessories and fittings complete in all respects as per drawings & specifications for Soil and Waste Water systems (Push Fit Joint).
A |  | Ø2" | 26.45 | Rft. | 600 | 15870 | 200 | 5290 | 21160
B |  | Ø3" | 57.5 | Rft. | 950 | 54625 | 200 | 11500 | 66125
Grand-Total for UPVC Pipe | [5 empty] | 70495 |  | 16790 | 87285
Floor Drains
| 22 05 23 | Supply, install and commission uPVC type Drains complete in all respects as per drawings & specifications.
A |  | Floor Drains | 6 | Nos. | 8900 | 53400 | 1000 | 6000 | 59400
B |  | Floor Clean Out | 5 | Nos. | 7000 | 35000 | 1000 | 5000 | 40000
| 23 33 05 | Installation of plumbing fixtures and fittings complete in all respects as shown on drawings & specifications.
7TH FLOOR
Executive Toilets
C |  | Installation of Wall Hung Water Closet (Black) with "P" or "S" trap, seat and cover best approved quality including imported flush Tank C.P. stop cock, C.P., Muslim Shower (Black), Fixing bolt (SS), Angle Valve (SS) & Bottle trap (Black) with all accessories & fittings, complete all connection and relative material making requisite hole in walls, floors and plinth for pipe connections and making good with approved materials complete in all respects in as shown on drawings & specifications. | 2 | Nos. |  | 0 | 8000 | 16000 | 16000
D |  | Installation of full size Wall Mounted Wash Basin(Black) including imported one hole C.P. faucet, mixer (black) with electronic sensor, angle vavle, C.P. stop cocks for hot and cold water, C.P. bottle trap, C.P. strainer C.P. copper pipe connections, C.P. brass waste chain plug complete with concealed safety brackets, waste water jointing assembly, making requisite number of holes in walls, floor and plinth for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. | 2 | Nos. |  | 0 | 8000 | 16000 | 16000
E |  | Installation of Wall Mounted Soap Dispensers for Vanity as per drawings & specifications. | 2 | Nos. |  | 0 | 800 | 1600 | 1600
F |  | Installation of Hand Dryers(Black) with sensor as per drawings & specifications. | 2 | Nos. |  | 0 | 500 | 1000 | 1000
G |  | Installation of Tissue Paper Dispenser,Toilet Paper Holder as per drawings & specifications. | 2 | Nos. |  | 0 | 500 | 1000 | 1000
H |  | Installation of Towel Ring (Black) as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
I |  | Installation of Robe Hook as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
J |  | Installation of Wastebins as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
|  | Sub Total for Floor Drains |  |  |  | 88400 |  | 50800 | 139200
A |  | Installation of Concealed Flush Plate (Black) with accessories as per drawings & specifications. | 2 | Nos. |  | 0 | 3000 | 6000 | 6000
B |  | Installation of Shower Set, including imported best quality C.P. shower head with shower mixer, C.P. waste plug chain complete with all connections and relative materials making requisite number of holes in walls, plinth and floor for pipe making good with approved materials complete in all respect as per drawings & specifications. | 1 | No. |  | 0 | 5000 | 5000 | 5000
|  | Staff Toilets |  |  |  | 0 |  | 0 | 0
C |  | Installation of Wall Hung Water Closet (white) with "P" or "S" trap, seat and cover best approved quality including imported flush Tank C.P. stop cock, C.P., Muslim Shower (SS), Fixing bolt (SS), Angle Valve (SS) & Bottle trap (SS) with all accessories & fittings, complete all connection and relative material making requisite hole in walls, floors and plinth for pipe connections and making good with approved materials complete in all respects in as shown on drawings & specifications. | 1 | No. |  | 0 | 7500 | 7500 | 7500
D |  | Installation of Asian type Water Closet (White) with "P" or "S" trap, seat and cover best approved quality including imported flush Tank C.P. stop cock, C.P., Muslim shower with all accessories & fittings, complete all connection and relative material making requisite hole in walls, floors and plinth for pipe connections and making good with approved materials complete in all respects in as shown on drawings & specifications. | 1 | No. |  | 0 | 7500 | 7500 | 7500
E |  | Supply, testing and commissioning of urinal (White) with Flush Valve, trap best approved quality with all accessories and fittings complete in all respects as per specifications / drawings. | 1 | No. | 125000 | 125000 | 15000 | 15000 | 140000
F |  | Installation of full size Wall Mounted Wash Basin(White)) including imported one hole C.P. faucet, High neck basin mixer (SS) with electronic sensor, angle vavle, C.P. stop cocks for hot and cold water, C.P. bottle trap, C.P. strainer C.P. copper pipe connections, C.P. brass waste chain plug complete with concealed safety brackets, waste water jointing assembly, making requisite number of holes in walls, floor and plinth for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. | 3 | Nos. |  | 0 | 7500 | 22500 | 22500
|  | Sub Total for Floor Drains |  |  |  | 125000 |  | 63500 | 188500
A |  | Installation of full size Janitor Sink including imported one hole C.P. faucet, High neck basin mixer (SS) with electronic sensor, angle vavle, C.P. stop cocks for hot and cold water, C.P. bottle trap, C.P. strainer C.P. copper pipe connections, C.P. brass waste chain plug complete with concealed safety brackets, waste water jointing assembly, making requisite number of holes in walls, floor and plinth for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. | 1 | No. |  | 0 | 7500 | 7500 | 7500
B |  | Installation of Wall Mounted Soap Dispensers for Vanity as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
C |  | Installation of Hose bibs for Ablution Faucet (SS) with sensor integrated in the spout and all accessories as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
D |  | Installation of Hand Dryers(Black) with sensor as per drawings & specifications. | 1 | No. |  | 0 | 700 | 700 | 700
E |  | Installation of Tissue Paper Dispenser,Toilet Paper Holder (SS) as per drawings & specifications. | 3 | Nos. |  | 0 | 700 | 2100 | 2100
F |  | Installation of Towel Ring (Black) as per drawings & specifications. | 1 | No. |  | 0 | 700 | 700 | 700
G |  | Installation of of Robe Hook(SS) as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
H |  | Installation of Wastebins as per drawings & specifications. | 1 | No. |  | 0 | 700 | 700 | 700
I |  | Installation of Concealed Flush Plate (SS) with accessories as per drawings & specifications. | 3 | Nos. |  | 0 | 7500 | 22500 | 22500
J |  | Installation of Handle Rail (SS) with accessories as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
|  | Pantry | [5 empty] | 0 | 0
K |  | Installation of Kitchen Sinks (SS) with angle valves (SS), sink mixer (SS) and all accessories and valves as per drawings & specifications. | 2 | Nos. |  | 0 | 6000 | 12000 | 12000
|  | Sub Total for Floor Drains |  |  |  | 0 |  | 51800 | 51800
Gym
A |  | Installation of Shower Set, including imported best quality C.P. shower head with shower mixer, C.P. waste plug chain complete with all connections and relative materials making requisite number of holes in walls, plinth and floor for pipe making good with approved materials complete in all respect as per drawings & specifications. | 2 | Nos. |  | 0 | 7500 | 15000 | 15000
B |  | Installation of full size Wall Mounted Wash Basin(White)) including imported one hole C.P. faucet, High neck basin mixer (SS) with electronic sensor, angle vavle, C.P. stop cocks for hot and cold water, C.P. bottle trap, C.P. strainer C.P. copper pipe connections, C.P. brass waste chain plug complete with concealed safety brackets, waste water jointing assembly, making requisite number of holes in walls, floor and plinth for pipe connections and making good with approved material complete in all respects as shown on drawings & specifications. | 2 | Nos. |  | 0 | 7500 | 15000 | 15000
C |  | Installation of Wall Mounted Soap Dispensers for Vanity as per drawings & specifications. | 1 | No. |  | 0 | 700 | 700 | 700
D |  | Installation of Hand Dryers(Black) with sensor as per drawings & specifications. | 1 | No. |  | 0 | 700 | 700 | 700
E |  | Installation of Towel Ring (Black) as per drawings & specifications. | 3 | Nos. |  | 0 | 700 | 2100 | 2100
F |  | Installation of Robe Hook(SS) as per drawings & specifications. | 2 | Nos. |  | 0 | 700 | 1400 | 1400
| 22 05 23 | Supply, Installation, Testing and commissioning of Valves with accessories as per drawings & specifications. |  |  |  | 0 |  | 0 | 0
G |  | HOSE BIB (DIA 3/4") | 2 | Nos. | 5500 | 11000 | 1000 | 2000 | 13000
H |  | BALL VALVE (DIA 3/4") | 4 | Nos. | 7000 | 28000 | 1000 | 4000 | 32000
|  | Sub Total for Floor Drains |  |  |  | 39000 |  | 40900 | 79900
Grand Total for Floor Drains
Miscellaneous
A | 22 05 29 | Supply, Installation & commissioning of hangers and supports for pipes and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 50000 | 50000 | 25000 | 25000 | 75000 | 75000 | 95000
B | 07 84 00 | Supply, Installation and commision fire stopping aid as per specifications and drawings complete in all respect. | 1 | Job | 75000 | 75000 | 20000 | 20000 | 95000
| 01 00 00 | Drawings |  |  |  | 0 |  | 0 | 0 | 0 | 5000
C |  | Shop Drawings as per specifications | 1 | Job | 15000 | 15000 | 5000 | 5000 | 20000 | 20000 | 25000
D |  | As Built Drawings as per specifications | 1 | Job | 10000 | 10000 | 5000 | 5000 | 15000
| 01 00 00 | Testing & Commissioning |  |  |  | 0 |  | 0 | 0 | 0 | 50000
E |  | Water Supply System | 1 | Job |  | 0 | 50000 | 50000 | 50000 | 20000 | 80000
|  | Grand Total for Miscellaneous |  |  |  | 150000 |  | 105000 | 255000
|  | GRAND TOTAL FOR PLUMBING WORKS (LEVEL-07) |  |  |  | 524277 |  | 341986.25 | 866263.25

## BMS 7F
SECTION III/D: BILL OF QUANTITIES FOR BMS WORKS (LEVEL-07)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7
HVAC
Water Cooled Package Units
A |  | Supply, Installation and Commissioning of complete control sets for Water Cooled Packaged Units as per specifications and drawings complete in all respects. | 1 | No.
B |  | Digital display thermostat(BACnet compliant). | 1 | Job | 237500 | 237500 | 13750 | 13750 | 251250
C |  | Duct Type Temperature Sensor. | 1 | No. | 80500 | 80500 | 7750 | 7750 | 88250
D |  | Control valve actuator (Floating type) | 1 | No. |  | 0 |  | 0 | 0
E |  | Flow switch | 2 | Nos. | 86500 | 173000 | 6750 | 13500 | 186500
Motorized Fire Smoke Damper
Supply, Installation and Commissioning of complete control sets for MFSD complete in all respects as per drawings and specifications.
F |  | 24" x 8" | 2 | Nos. | 130000 | 260000 | 15000 | 30000 | 290000
G |  | 20" x 10" | 2 | Nos. | 130000 | 260000 | 15000 | 30000 | 290000
Air Handling units
Supply, Installation and Commissioning of complete control sets for Air Handling Units including all sensors, actuators etc as per specifications and drawings complete in all respects.
H |  | VAVs | 1 | Job |  | 0 |  | 0 | 0
I |  | Thermostats (Temp, CO2 & Occ. sensors) | 1 | Job | 350000 | 350000 | 75000 | 75000 | 425000
J |  | Controller | 1 | Job | 200000 | 200000 | 25000 | 25000 | 225000
K |  | Occupancy Sensor | 1 | Job |  | 0 |  | 0 | 0
L |  | Water Meter | 1 | No. | 0 | 0 | 8000 | 8000 | 8000
|  | Sub Total for HVAC (Page 1) |  |  |  | 1561000 |  | 203000 | 1764000
Exhaust Fan
A |  | DDC Controller (BACnet Compliant) Freely Programmable | 1 | No. | 165000 | 165000 | 10000 | 10000 | 175000
B |  | Exhaust Fan On/Off command. | 1 | No. | 9500 | 9500 | 3000 | 3000 | 12500
C |  | Exhaust Fan On/Off Status. | 1 | No. | 10800 | 10800 | 4500 | 4500 | 15300
|  | Sub Total for HVAC (Page 2) |  |  |  | 185300 |  | 17500 | 202800
Grand Total for HVAC (Page 1 to 2)
Fire Protection
A |  | Supply installation and commissioning of controls set for Zone control valve and flow switch | 2 | Nos. |  | 0 |  | 0 | 0
B |  | DDC Controller (BACnet Compliant) Freely Programmable | 1 | No. |  | 0 |  | 0 | 0
|  | Grand Total for Fire Protection | [6 empty] | 0
Building Management System
A | 25 00 00 | Building management shall include the server with all its required peripherals, BMS software and license for third party integration. | 1 | Job | 575000 | 575000 | 50000 | 50000 | 625000
|  | Grand Total for Building Management System |  |  |  | 575000 |  | 50000 | 625000
Testing & Commissioning
A |  | It shall cover the commisiong and testing of all the systems | 1 | Job | 150000 | 150000 | 50000 | 50000 | 200000
|  | Grand Total for Testing & Commissioning |  |  |  | 150000 |  | 50000 | 200000
GUI Development
A |  | It shall include all the software and hardware points to be mapped on GUI | 1 | Job |  | 0 |  | 0 | 0
|  | Grand Total for GUI Development | [6 empty] | 0
Miscelleneous
A |  | Any item left for the smooth, fully operational IBMS system shall be provided in this scope with details. | 1 | Job |  | 0 |  | 0 | 0
|  | Grand Total for Miscelleneous | [6 empty] | 0
|  | GRAND TOTAL FOR BMS WORKS (LEVEL-07) |  |  |  | 2471300 |  | 320500 | 2791800