## HVAC
[6 empty] | Date |  | 2025-05-26
M/S Patients’ Aid Foundation
Attn: Mr. Zameer Sahab
Bill for OT Area 6th Floor Surgical Complex - JPMC KARACHI
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Labour Amount | Total Amount
Machine Made G.I Sheet metal Duct
1 | Supply, Installation, testing & Commissioning of Machine made G.I. sheet metal ducts with related mateiral such as nut bolts gasket etc for supply and return air. | Sqft | 1738.2332 | 488.75 | 86.25 | 849561.4738 | 149922.613 | 999484.0868
XLPE insulation
2 | Supply and installation of 20mm thick self adhesive XLPE insulation with Aluminum Faced with related material. | Sqft | 1738.2332 | 485 | 57.5 | 843043.0993 | 99948.4087 | 942991.508
Air devices
3 | Supply and installation of volume control damper
i | 36" x 08" | Nos |  | 11500 | 1150 | 0 | 0 | 0
ii | 24" x 14" | Nos |  | 13512.5 | 1150 | 0 | 0 | 0
iii | 18" x 08" | Nos |  | 6325 | 1150 | 0 | 0 | 0
iv | 30" x 16" | Nos |  | 19320 | 1150 | 0 | 0 | 0
v | 20" x 16" | Nos |  | 13225 | 1150 | 0 | 0 | 0
vi | 16" x 08" | Nos |  | 5152 | 1150 | 0 | 0 | 0
7 | Supply and installation of Fire Damper |  |  | 0 | 0 | 0 | 0 | 0
i | 38 x 16 | Nos | 7 | 0 | 0 | 0 | 0 | 0
ii | 32 x 14 | Nos | 4 | 0 | 0 | 0 | 0 | 0
8 | Supply and installation of access door for fire / split damper. Size 18 x 18 | Nos | 11 | 0 | 0 | 0 | 0 | 0
4 | Installation of owner supplied VAV boxes with hangers & supports for supply & return air. | Nos | 12 | 0 | 5750 | 0 | 69000 | 69000
5 | Supply and Installation of flexbile duct connector for luminar connections | Rft |  | 1092.5 | 172.5 | 0 | 0 | 0
| M.S SCH-40 Pipe and related material |  |  | 0 | 0
10 | Providing and installation of temporary scaffolding for installation of chilled water riser (after completion of work removal of folding) | Job | 1 | 0 | 0 | 0 | 0 | 0
11 | Installation of M.S Sch-40 Seamless chilled water pipe with comsumable material such as cutting discs, grinding disc, electrodes etc |  |  | 0 | 0
i | 6" dia | Rft | 350 | 0 | 0 | 0 | 0 | 0
ii | 4" dia | Rft | 130 | 0 | 0 | 0 | 0 | 0
iii | 3" dia | Rft | 350 | 0 | 0 | 0 | 0 | 0
iv | 2-1/2" dia | Rft | 650 | 0 | 0 | 0 | 0 | 0
v | 2" dia | Rft | 400 | 0 | 0 | 0 | 0 | 0
vi | 1-1/2" dia | Rft | 200 | 0 | 0 | 0 | 0 | 0
vii | 1-1/4" dia | Rft | 320 | 0 | 0 | 0 | 0 | 0
viii | 1" dia | Rft | 180 | 0 | 0 | 0 | 0 | 0
ix | 3/4" dia | Rft | 200 | 0 | 0 | 0 | 0 | 0
12 | Providing and making of chilled water connection from main plant room for supply and return. | Job | 1 | 0 | 0 | 0 | 0 | 0
13 | Supply and installation of related fittings for M.S SCH-40 Pipe fittings such as tee, elbow, reduser, gasket, nut washer etc. | Job | 1 | 0 | 0 | 0 | 0 | 0
| Premolded PU Insulation |  |  | 0 | 0
14 | Supply and Intallation of premolded PU insulation over chilled water piping with 26 SWG G.I sheet metal cladding, kraft paper, canvas cloth etc complete in all respect. |  |  | 0 | 0
| Thickness 2" |  |  | 0 | 0
i | 6" dia | Rft | 350 | 0 | 0 | 0 | 0 | 0
ii | 4" dia | Rft | 130 | 0 | 0 | 0 | 0 | 0
iii | 3" dia | Rft | 350 | 0 | 0 | 0 | 0 | 0
iv | 2-1/2" dia | Rft | 650 | 0 | 0 | 0 | 0 | 0
v | 2" dia | Rft | 400 | 0 | 0 | 0 | 0 | 0
| Thickness 1-1/2" |  |  | 0 | 0
i | 1-1/2" dia | Rft | 200 | 0 | 0 | 0 | 0 | 0
ii | 1-1/4" dia | Rft | 320 | 0 | 0 | 0 | 0 | 0
iii | 1" dia | Rft | 180 | 0 | 0 | 0 | 0 | 0
iv | 3/4" dia | Rft | 200 | 0 | 0 | 0 | 0 | 0
15 | Supply and installation of condensate drain with insulation. |  |  | 0 | 0
i | 2" dia | Rft | 240 | 0 | 0 | 0 | 0 | 0
ii | 1-1/2" dia | Rft | 220 | 0 | 0 | 0 | 0 | 0
iii | 1" dia | Rft | 360 | 0 | 0 | 0 | 0 | 0
6 | Supply and installation of Hanger & supports for supply & return air Ducts. | Job |  | 172500 | 57500 | 0 | 0 | 0
7 | Testing & Commissioning of HVAC system | Job |  | 0 | 28750 | 0 | 0 | 0
8 | Providing and making of shop drawings and as built drawings. | Job |  | 11500 | 34500 | 0 | 0 | 0
Total Amount Rs | [7 empty] | 2011475.5948
Total Amount Rs | [7 empty] | 2011475.5948
Note: Bill will be claimed on actual measurements
For PIONEER ENGINEERING SERVICES
[5 empty] | Pre Quote |  |  | 6376150
[5 empty] | 15% TC Margin |  |  | 956422.5
[5 empty] | Revised Quote |  |  | 7332572.5
PIONEER SERVICES

## Sheet1
Project | Amount Due | Amount Claimed | Payment
JPMC OT Area 6th Floor | 2011475.5948 | 2011475.5948 | Running Bill
PHSYCHTRY DEPT | 1395426.45 | 697713.225 | Retention amount
FOOD COURT | 1043612 | 521806 | Retention amount
Total Amount Rs |  | 3230994.8198