## Summary
SMOKE EXTRACT FANS |  | 2025-05-26
NASTP SILICON-II KARACHI
FINAL BILL
S.No | Description | Total Amount
1 | SMOKE EXTRACT FANS INTEGRATED WITH FIRE ALARM SYSTEM AND ALLIED WORKS (S-2) | 5672100
2 | SMOKE EXTRACT FANS INTEGRATED WITH FIRE ALARM SYSTEM AND ALLIED WORKS (S-3) | 5607760
3 | SMOKE EXTRACT FANS INTEGRATED WITH FIRE ALARM SYSTEM AND ALLIED WORKS (S-4) | 6711730
| Total Amount | 17991590
PIONEER SERVICES

## Smoke Extraction (S-2)
NASTP SILICON-II KARACHI
SMOKE EXTRACT FANS INTEGRATED WITH FIRE ALARM SYSTEM AND ALLIED WORKS (S-2)
13-11-2024
S.No | Description | Brands | Unit | Qty. | Total Cost Rs.
[5 empty] | Unit Rate | Amount
1 | Supply, installation, testing & commissioning of VFD Operated Fire Rated Smoke Extract Fans ducted in-line as specified, scheduled & specification complete with un-loading, lifting and fixing at locations as shown on the drawings complete in all respect. Compliance to specification required. (Close to Fan, a lockable isolator switch need to be installed, near to each Fan). The fan should comply NFPA standard requirement for smoke extract fan alongwith signal wire for smoke extract fan is in fire alarm contractor scope of work. | AMCA Certified Fire Rated Fans with 2 hours Fire rating
Ground Floor:
1.1 | GF S-2 (4000 CFM) @ 1'' ESP | BVN TURKEY or UAE | Nos. | 1 | 850000 | 850000
First Floor:
1.2 | FF S-2 (4000 CFM) @ 1'' ESP | BVN TURKEY or UAE | Nos. | 1 | 850000 | 850000
2 | Duct Work & Accessories:
Supply, Installation, Testing & Commissioning of G.I. Sheet Metal Low Pressure ducting ( Machine Made ) as per SMACNA & ASHRAE Standards for air ducting, plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings with galvanized hanger supports as per specification and drawings.
2.1 | G.I Duct - 20 Gauge | ISL Pakistan | Sq. ft | 35 | 460 | 16100
2.2 | G.I Duct - 22 Gauge | ISL Pakistan | Sq. ft | 5000 | 495 | 2475000
3 | Duct Insulation:
3.1 | Supply and installation of 1 Inch thick Glass Wool Insulation of density 16 kg/m3 with Aluminum Foil for Internal G.I. sheet metal ducts of different sections for supply and return air duct with Alumninum tape and protected with 8 oz Canvas Cloth wrapping than painted anti fungus paint complete in all respect as per schedule, specifications and drawings. | Afico Saudia Arabia | Sq. ft | 4850 | 200 | 970000
4 | Air Devices
4.1 | Supply, installation, testing & commissioning of Aluminum air devices Ionized with adjustable damper as specified, scheduled & specification and as shown in drawings should be included, complete in all respect, for installation refer to schedule & specification. (Color selection as per Architect).compliance to specification required. | EAP Pakistan
Exshaust Air Diffuser:
4.1 | Ground Floor:
a | GF E.A.D S-2 (15" x 15") | EAP Pakistan | Nos. | 16 | 6500 | 104000
4.2 | First Floor
a | GF E.A.D S-2 (15" x 15") | EAP Pakistan | Nos. | 8 | 6500 | 52000
5 | Exshaust Air Louver 60''X40'' |  | Nos. | 2 | 55000 | 110000
6 | Supply & Installation of MS C - Channal Bracket For Smoke Extract Fans Complete in all respect. |  | Nos. | 2 | 35000 | 70000
Miscellaneous Items:
7 | Cost testing, Starting up, Comissioning & Air Balancing, adjusting and handling over of the Complete System |  | Job | 1 | 50000 | 50000
8 | Equipment foundation and equipment shifting charges from Ground floor to foundation pads as per specification and drawings. |  | Job | 1 | 30000 | 30000
9 | Supply and Installation of Hangers and Supports System as per Drawings and Specification. |  | Job | 1 | 75000 | 75000
10 | Shop drawings (On minimum Scale 1/8"=1'-0") |  | Sets | 1 | 10000 | 10000
11 | As-installed drawings with Soft Copy as Auto Cad 2021 (03 Sets). (On minimum Scale 1/8"=1'-0") |  | Sets | 1 | 10000 | 10000
| Total Amount (Rs.) |  |  |  |  | 5672100
Validity:
i | Validity of our above offer is 20 days.
Payment Terms:
i | 50% advance with Purchase Order
ii | 30% on material delivery at site
iii | 20% on completion of the work.
Warranty:
i | 06 months from the date of commissioning of the System for all items
Special Note:
i | Prices are based on 1 USD = 280 Pkr as per current rate if exceed more then 2% then variation should be bear by client.
ii | Due to current forex rate fluctuations, deal will be lock in US dollars ($) and the time payment against order advance or running bill will be considered that day forex rate.
iii | If Payment not received till our delivery date than storage charges wil be on client @100 USD/day.
iv | Above mentioned prices are exclusive of all taxes.

## Smoke Extraction (S-3)
NASTP SILICON-II KARACHI
SMOKE EXTRACT FANS INTEGRATED WITH FIRE ALARM SYSTEM AND ALLIED WORKS (S-3)
13-11-2024
S.No | Description | Brands | Unit | Qty. | Total Cost Rs.
[5 empty] | Unit Rate | Amount
1 | Supply, installation, testing & commissioning of VFD Operated Fire Rated Smoke Extract Fans ducted in-line as specified, scheduled & specification complete with un-loading, lifting and fixing at locations as shown on the drawings complete in all respect. Compliance to specification required. (Close to Fan, a lockable isolator switch need to be installed, near to each Fan). The fan should comply NFPA standard requirement for smoke extract fan alongwith signal wire for smoke extract fan is in fire alarm contractor scope of work. | AMCA Certified Fire Rated Fans with 2 hours Fire rating
Ground Floor:
1.1 | GF S-3 (4000 CFM) @ 1'' ESP | BVN TURKEY or UAE | Nos. | 1 | 850000 | 850000
First Floor:
1.2 | FF S-3 (4000 CFM) @ 1'' ESP | BVN TURKEY or UAE | Nos. | 1 | 850000 | 850000
2 | Duct Work & Accessories:
Supply, Installation, Testing & Commissioning of G.I. Sheet Metal Low Pressure ducting ( Machine Made ) as per SMACNA & ASHRAE Standards for air ducting, plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings with galvanized hanger supports as per specification and drawings.
2.1 | G.I Duct - 20 Gauge | ISL Pakistan | Sq. ft | 31 | 460 | 14260
2.2 | G.I Duct - 22 Gauge | ISL Pakistan | Sq. ft | 4900 | 495 | 2425500
3 | Duct Insulation:
3.1 | Supply and installation of 1 Inch thick Glass Wool Insulation of density 16 kg/m3 with Aluminum Foil for Internal G.I. sheet metal ducts of different sections for supply and return air duct with Alumninum tape and protected with 8 oz Canvas Cloth wrapping than painted anti fungus paint complete in all respect as per schedule, specifications and drawings. | Afico Saudia Arabia | Sq. ft | 4850 | 200 | 970000
4 | Air Devices
4.1 | Supply, installation, testing & commissioning of Aluminum air devices Ionized with adjustable damper as specified, scheduled & specification and as shown in drawings should be included, complete in all respect, for installation refer to schedule & specification. (Color selection as per Architect).compliance to specification required. | EAP Pakistan
Exshaust Air Diffuser:
4.1 | Ground Floor:
a | GF E.A.D S-3 (15" x 15") | EAP Pakistan | Nos. | 11 | 6500 | 71500
4.2 | First Floor
b | GF E.A.D S-3 (15" x 15") | EAP Pakistan | Nos. | 11 | 6500 | 71500
5 | Exshaust Air Louver 60''X40'' |  | Nos. | 2 | 55000 | 110000
6 | Supply & Installation of MS C - Channal Bracket For Smoke Extract Fans Complete in all respect. |  | Nos. | 2 | 35000 | 70000
Miscellaneous Items:
7 | Cost testing, Starting up, Comissioning & Air Balancing, adjusting and handling over of the Complete System |  | Job | 1 | 50000 | 50000
8 | Equipment foundation and equipment shifting charges from Ground floor to foundation pads as per specification and drawings. |  | Job | 1 | 30000 | 30000
9 | Supply and Installation of Hangers and Supports System as per Drawings and Specification. |  | Job | 1 | 75000 | 75000
10 | Shop drawings (On minimum Scale 1/8"=1'-0") |  | Sets | 1 | 10000 | 10000
11 | As-installed drawings with Soft Copy as Auto Cad 2021 (03 Sets). (On minimum Scale 1/8"=1'-0") |  | Sets | 1 | 10000 | 10000
| Total Amount (Rs.) |  |  |  |  | 5607760
Validity:
i | Validity of our above offer is 20 days.
Payment Terms:
i | 50% advance with Purchase Order
ii | 30% on material delivery at site
iii | 20% on completion of the work.
Warranty:
i | 06 months from the date of commissioning of the System for all items
Special Note:
i | Prices are based on 1 USD = 280 Pkr as per current rate if exceed more then 2% then variation should be bear by client.
ii | Due to current forex rate fluctuations, deal will be lock in US dollars ($) and the time payment against order advance or running bill will be considered that day forex rate.
iii | If Payment not received till our delivery date than storage charges wil be on client @100 USD/day.
iv | Above mentioned prices are exclusive of all taxes.

## Smoke Extraction (S-4)
NASTP SILICON-II KARACHI
SMOKE EXTRACT FANS INTEGRATED WITH FIRE ALARM SYSTEM AND ALLIED WORKS (S-4)
13-11-2024
S.No | Description | Brands | Unit | Qty. | Total Cost Rs.
[5 empty] | Unit Rate | Amount
1 | Supply, installation, testing & commissioning of VFD Operated Fire Rated Smoke Extract Fans ducted in-line as specified, scheduled & specification complete with un-loading, lifting and fixing at locations as shown on the drawings complete in all respect. Compliance to specification required. (Close to Fan, a lockable isolator switch need to be installed, near to each Fan). The fan should comply NFPA standard requirement for smoke extract fan alongwith signal wire for smoke extract fan is in fire alarm contractor scope of work. | AMCA Certified Fire Rated Fans with 2 hours Fire rating
Ground Floor:
1.1 | GF S-4 (4000 CFM) @ 1'' ESP | BVN TURKEY or UAE | Nos. | 1 | 850000 | 850000
First Floor:
1.2 | FF S-4 (4000 CFM) @ 1'' ESP | BVN TURKEY or UAE | Nos. | 1 | 850000 | 850000
2 | Duct Work & Accessories:
Supply, Installation, Testing & Commissioning of G.I. Sheet Metal Low Pressure ducting ( Machine Made ) as per SMACNA & ASHRAE Standards for air ducting, plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings with galvanized hanger supports as per specification and drawings.
2.1 | G.I Duct - 20 Gauge | ISL Pakistan | Sq. ft | 50 | 460 | 23000
2.2 | G.I Duct - 22 Gauge | ISL Pakistan | Sq. ft | 6454 | 495 | 3194730
3 | Duct Insulation:
3.1 | Supply and installation of 1 Inch thick Glass Wool Insulation of density 16 kg/m3 with Aluminum Foil for Internal G.I. sheet metal ducts of different sections for supply and return air duct with Alumninum tape and protected with 8 oz Canvas Cloth wrapping than painted anti fungus paint complete in all respect as per schedule, specifications and drawings. | Afico Saudia Arabia | Sq. ft | 6350 | 200 | 1270000
4 | Air Devices
4.1 | Supply, installation, testing & commissioning of Aluminum air devices Ionized with adjustable damper as specified, scheduled & specification and as shown in drawings should be included, complete in all respect, for installation refer to schedule & specification. (Color selection as per Architect).compliance to specification required. | EAP Pakistan
Exshaust Air Diffuser:
4.1 | Ground Floor:
a | GF E.A.D S-4 (15" x 15") | EAP Pakistan | Nos. | 14 | 6500 | 91000
4.2 | First Floor
a | GF E.A.D S-4 (15" x 15") | EAP Pakistan | Nos. | 12 | 6500 | 78000
5 | Exshaust Air Louver 60''X40'' |  | Nos. | 2 | 55000 | 110000
6 | Supply & Installation of MS C - Channal Bracket For Smoke Extract Fans Complete in all respect. |  | Nos. | 2 | 35000 | 70000
Miscellaneous Items:
7 | Cost testing, Starting up, Comissioning & Air Balancing, adjusting and handling over of the Complete System |  | Job | 1 | 50000 | 50000
8 | Equipment foundation and equipment shifting charges from Ground floor to foundation pads as per specification and drawings. |  | Job | 1 | 30000 | 30000
9 | Supply and Installation of Hangers and Supports System as per Drawings and Specification. |  | Job | 1 | 75000 | 75000
10 | Shop drawings (On minimum Scale 1/8"=1'-0") |  | Sets | 1 | 10000 | 10000
11 | As-installed drawings with Soft Copy as Auto Cad 2021 (03 Sets). (On minimum Scale 1/8"=1'-0") |  | Sets | 1 | 10000 | 10000
| Total Amount (Rs.) |  |  |  |  | 6711730
Validity:
i | Validity of our above offer is 20 days.
Payment Terms:
i | 50% advance with Purchase Order
ii | 30% on material delivery at site
iii | 20% on completion of the work.
Warranty:
i | 06 months from the date of commissioning of the System for all items
Special Note:
i | Prices are based on 1 USD = 280 Pkr as per current rate if exceed more then 2% then variation should be bear by client.
ii | Due to current forex rate fluctuations, deal will be lock in US dollars ($) and the time payment against order advance or running bill will be considered that day forex rate.
iii | If Payment not received till our delivery date than storage charges wil be on client @100 USD/day.
iv | Above mentioned prices are exclusive of all taxes.