## IPC-1
VISA FIT OUT PROJECT
10th FLOOR UNIT # 4, DOLMEN SKY TOWER - A, CLIFTON KARACHI.
ADDITIONAL WORKS FOR IDF ROOM - RUNNING BILL NO 1
Date: 06-11-2023
Rev-01
Sr. No. | Description | Unit | Billed Qty | Rate | Amount Rs. | Remarks
1 | AC UNITS:
1 | Supply, installation, testing and commissioning of of water cooled package unit complete in all respects, ready to operate including supply and installation of all accessories, lindaptor supports, hanger steel base, vibration isolators, including interconnecting power & control wiring (terminal connection) with inlet & outlet water pipe connections, drain connection, flexible rubber duct connection / connector etc. complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
1.1 | WCPU-01 | No. | 1 | 875000 | 875000
Total - 01
2 | VALVES & ACCESSORIES
2 | Supply & installation of valves & accessories for WCPU with supports, hangers, flanges, gas kits, nut & bolts where it required, etc. complete in all respects as per specifications, drawings and as per instructions of consultant.
2.1 | Ball Valve
a | 25mm dia | Nos. | 4 | 8000 | 32000
2.2 | Strainers
a | 25mm dia | No. | 1 | 7500 | 7500
2.3 | Balancing Valve (with self sealing measuring nipples)
a | 25mm dia | No. | 1 | 18000 | 18000
2.4 | Flexible Pipe Connector
a | 25mm dia | Nos. | 2 | 9000 | 18000
2.5 | Pressure Switch | No. | 1 | 35000 | 35000
2.6 | Digital Decorative Thermostat Controller (BMS Interfacable) with Duct Mounted Sensor | No. | 1 | 80000 | 80000
2.7 | Control wiring from controller to sensors, motorized valve and Power wiring up to 5 meter radius | Job. | 1 | 30000 | 30000
Total - 02
3 | M.S PIPE:
3 | Supply & installation of SCH-40 M.S.(As per ASME & API standard, Heavy Quality with standard SCH 40 wall thickness) pipes & fitting, complete with bends, tees, unions, sockets, specials, lindaptor support, hangers & anchors, M.S. angle, U channel, roller support, bolts, rods, clamps, concrete fasteners, with one coat of ICI make red lead oxide primer & two coats of ICI make enamel paint etc as required to complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
3.1 | 25mm dia | Rm | 10 | 3600 | 36000
Total - 03
4 | G.I DUCT:
4 | Supply, fabrication & installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector / connection, access door, transformation, plenums chambers, wooden frame, lindaptor type anchors supports & hangers etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 10 | 5600 | 56000
Total - 04
5 | DUCT INSULATION:
5 | Supply & installation of adhesive 20mm thick rubber foam (XLPE) insulation with aluminum foil over supply & return duct, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqm | 10 | 6500 | 65000
Total - 05
6 | S.S CLADDING:
6 | Supply, fabrication & installation of 24 SWG gauge SS-304 cladding (non false ceiling area only), complete in all respects ready to operate as per specification, drawings and as per instruction, approval of consultant. | Sqm | 0 | 14500 | 0
Total - 06
7 | SOUND LINER:
7 | Supply & installation of acoustical duct sound liner (adhesive 12mm thick) in supply air & return air duct etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant. | Sqm | 0 | 6500 | 0
Total - 07
8 | AIR DEVICES
8 | Supply & installation of aluminum fabricated, powder coated grills, diffusers and registers etc for supply, return, exhaust & fresh air of different sizes (Grade A) wooden frame, lindaptor supports and other accessories etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
8.1 | Supply & Return Air Registers
a | 650mm x 250mm | Nos. | 4 | 10000 | 40000
Total - 08
9 | MOTORIZED DAMPER:
9 | Supply, Installation of Motorized Damper with gas kits, nut bolts, including pressure transmeter, controller & control wiring, complete in all respects, ready to operate as per specification, drawings & as per instruction of Consultant.
9.1 | 650mm x 250mm | Nos. | 2 | 325000 | 650000
Total - 9
10 | VOLUME CONTROL DAMPER:
10 | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, etc, complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant.
10.1 | 650mm x 250mm | Nos. | 2 | 15000 | 30000
Total - 10
11 | DRAIN PIPE:
11 | Supply & installation of uPVC make class D SCH-40 pipe with 10mm thick expanded rubber foam insulation, PVC tape wrapping for condensate drain including lindaptor type support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
11.1 | 25mm dia | Rm | 8 | 1400 | 11200
Total - 11
12 | FSS PIPE & SPRINKLER:
12 | Dismantling & re-installation of fire suppression services M.S SCH-40 pipe with accessories, sprinklers etc., complete in all respects ready to operate as per site requirement, drawings and as per instruction of consultant. | Job. | 1 | 100000 | 100000
Total - 12
13 | AUTOMATIC CONTROLS SYSTEM
13.1 | Supply, installation, testing & commissioning of automatic control mechanism / system (logic based) of both WCPUs & DFCUs, including controls, BMS interfacable thermostat temperature sensors, timers, contactors, relays, communication protocols, input & output modules, interconnecting wiring, power wiring, panel box etc, complete in all respects ready to operate as per instruction of consultant, (refer to I/O summary for details). | Job. | 1 | 0
13.2 | Supply & installation of BMS interfacable digital display HMI, addressable, wirelessly connected with wifi, communicate through mobile app / software remotely, including fault alarm / notification etc, complete in all respects ready to operate as per instruction of consultant. | Job. | 1 | 0
Total - 13
14 | TESTING & BALANCING:
14 | Testing, balancing and commissioning of water & air side of the system complete in all respects including flow measurement & balancing, temp, pressure, electrical data of related equipment etc, complete in all respects as per instruction of consultant. | Job. | 0 | 50000 | 0
Total - 14
15 | SHOP & AS BUILT DRAWING:
15 | Making of Shop drawings on Auto CAD latest version with section details, equipment foundation details and Making of As Built drawings, Documentation Technical / Operational Manual & LOG Book for each equipment as per instruction of Consultant. | Job. | 0 | 20000 | 0
Total - 15
| Grand Total Amount Rs. |  |  |  | 2083700
NOTE: Above prices are related to PES, please add your Margin.