## Grand Summary
M/S Meezan Bank Ltd Head Office
Meezan House, C-25, Estate Avenue Site Khi
Plumbing & Fire fighting Works Meezan Bank Gujran wala MAKKAH TOWER, GUJRANWALA
Divisions | Description of Work | Supply Amount | Installation Amount | Total
1 | PLUMBING & FIREFIGHTING SYSTEMS | 22400000 | 9600000 | 32000000
| Grand Total (in PKR): | 22400000 | 9600000 | 32000000
| 15% SST on Installation (in PKR): | 0 | 1440000 | 1440000
| Grand Total Inclusive of Tax (in PKR): | 22400000 | 11040000 | 33440000
Mobilization advance 20% |  |  |  | 6688000

## Updated
MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA
BILL OF QUANTITIES
PLUMBING & FIREFIGHTING SYSTEMS
Sr. No. | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Labour Amount
Part-1: PLUMBING FIXTURES
INDIAN W.C
1.1 | Providing and fixing Indian W.C ceramics ware including muslim shower, tee stop cock, double bibcock with flushing cistern of best quality including hockey pipe. Fixing connection pipes and all joints to services and drains. Plugging and screwing the structure as necessary and make good the same, complete in all respect as per specifications and drawings as well as directed by the Engineer. MODEL # PORTA (HD70) | Nos. | 3 | 35399.7147 | 15171.3063 | 106199.1441 | 45513.9189 | -82599.3343 | 117999.049 |  | 24779.8003 | 10619.9144
[6 empty] | 0 | 0 | 0 | 0
| EUROPEAN W.C |  |  |  |  | 0 | 0 | 0 | 0
1.2 | Providing and fixing European W.C ceramics ware including muslim shower, tee stop cock with double bibcock, flushing cistern with hinged double seat and cover of best quality. Fixing connection pipes and all joints to services and drains. Plugging and screwing the structure as necessary and make good the same, complete in all respect as per specifications and drawings as well as directed by the Engineer. MODEL # PORTA (HD9N) |  |  |  |  | 0 | 0 | 0 | 0
| Items Included |  |  |  |  | 0 | 0 | 0 | 0
| European type W.C With Seat Cover. |  |  |  |  | 0 | 0 | 0 | 0
| W.C Thimble |  |  |  |  | 0 | 0 | 0 | 0
| Muslim Shower Porta Model # HD30 |  |  |  |  | 0 | 0 | 0 | 0
| Double Bibcock Porta Model HDA5270B |  |  |  |  | 0 | 0 | 0 | 0
| Tee Stop Cock Porta Model HDJ855 | Nos. | 27 | 60247.5913 | 25820.3963 | 1626684.9662 | 697150.6998 | -140577.7131 | 200825.3045 |  | 42173.3139 | 18074.2774
[6 empty] | 0 | 0 | 0 | 0
| CORE CUTTING |  |  |  |  | 0 | 0 | 0 | 0
1.3 | Cutting of R.C.C slab via core cutter of suitable diameter by using proper technique and equipment for the crossing of utility pipes and its water proof refilling with useful materials complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 42 | 1361.5275 | 583.5118 | 57184.1545 | 24507.4948 | -3176.8975 | 4538.425 |  | 953.0692 | 408.4582
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| WASH HAND BASIN VANITY |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1.4 | Providing and fixing wash hand basin vanity Under counter including basin mixer with waste coupling & bottle trap and fixing connection pipes, connections to water lines, nuts, washers, etc. complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Items Included |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Wash Hand Basin Vanity. Porta Model HD1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Basin Mixer Porta Model HDA781M |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Bottle Trap Porta Model GD1038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Waste Coupling Porta Model HDGD1023 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Tee Stop Cock Porta Model HDJ855 | Nos. | 36 | 46291.9346 | 19839.4005 | 1666509.6453 | 714218.4194 | -108014.514 | 154306.4486 |  | 32404.3542 | 13887.5804
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| KITCHEN SINK |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1.5 | Providing and fixing kitchen sink with mixer, waste coupling and tee stop cock including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Items Included |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Kitchen Sink Porta Model HDSC8728 |  |  |  |  | 0 | 0 | 0 | 0
| Kitchen Sink Mixer Porta Model HDA708XH |  |  |  |  | 0 | 0 | 0 | 0
| Waste Coupling Porta Model HDGD1023 |  |  |  |  | 0 | 0 | 0 | 0
| Tee Stop Cock Porta Model HDJ855 | Nos. | 5 | 75054.2028 | 32166.0869 | 375271.0139 | 160830.4345 | -175126.4731 | 250180.6759 |  | 52537.9419 | 22516.2608
[6 empty] | 0 | 0 | 0 | 0
| SOAP DISPENSER |  |  |  |  | 0 | 0 | 0 | 0
1.6 | Providing and fixing soap dispenser including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| Items Included |  |  |  |  | 0 | 0 | 0 | 0
| Soap Dispenser ZILVER 302C | Nos. | 16 | 6194.9501 | 2654.9786 | 99119.2011 | 42479.6576 | -14454.8835 | 20649.8336 |  | 4336.465 | 1858.485
[6 empty] | 0 | 0 | 0 | 0
| TOILET PAPER HOLDER |  |  |  |  | 0 | 0 | 0 | 0
1.7 | Providing and fixing chromium plated toilet paper holder including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| Items Included |  |  |  |  | 0 | 0 | 0 | 0
| Toilet Paper Holder PORTA JM70 | Nos. | 30 | 4254.7734 | 1823.4743 | 127643.202 | 54704.2294 | -9927.8046 | 14182.578 |  | 2978.3414 | 1276.432
[6 empty] | 0 | 0 | 0 | 0
| HAND DRYER |  |  |  |  | 0 | 0 | 0 | 0
1.8 | Providing and fixing electrical hand dryer with automatic sensor having fastest drying time of 12 seconds, temperature of 104 Fahrenheit. hand dryer must have noise Level of 81dB and automatic shut off including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| Items Included |  |  |  |  | 0 | 0 | 0 | 0
| Hand Dryer SIEMENS | Nos. | 9 | 16678.7117 | 7148.0193 | 150108.4055 | 64332.1738 | -38916.994 | 55595.7058 |  | 11675.0982 | 5003.6135
[6 empty] | 0 | 0 | 0 | 0
| LOOKING GLASS |  |  |  |  | 0 | 0 | 0 | 0
1.9 | Providing and fixing looking glass 5mm thick first quality complete with fixing clamps including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| Items Included |  |  |  |  | 0 | 0 | 0 | 0
| Looking Glass |  |  |  |  | 0 | 0 | 0 | 0
| Looking Glass Clamp | Sft. | 216 | 1838.0621 | 787.7409 | 397021.4155 | 170152.0352 | -4288.8116 | 6126.8737 |  | 1286.6435 | 551.4186
[6 empty] | 0 | 0 | 0 | 0
| TOWEL ROD |  |  |  |  | 0 | 0 | 0 | 0
2 | Providing and fixing towel rod including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| Items Included |  |  |  |  | 0 | 0 | 0 | 0
| Towel Rod PORTA JM11 | Nos. | 8 | 6467.2556 | 2771.681 | 51738.0445 | 22173.4477 | -15090.263 | 21557.5186 |  | 4527.0789 | 1940.1767
[6 empty] | 0 | 0 | 0 | 0
| TAP |  |  |  |  | 0 | 0 | 0 | 0
1.1 | Providing and fixing tap 3/4 inch dia including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| Items Included |  |  |  |  | 0 | 0 | 0 | 0
| Tap 3/4 inch dia | Nos. | 25 | 6739.5611 | 2888.3833 | 168489.0266 | 72209.5828 | -15725.6425 | 22465.2036 |  | 4717.6927 | 2021.8683
[6 empty] | 0 | 0 | 0 | 0
| Total Amount (Rs.) Part - 1 |  |  |  |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
| Part-2: INTERNAL WATER SUPPLY SYSTEM |  |  |  |  | 0 | 0 | 0 | 0
2.1 | Providing, fixing, jointing and testing Polypropylene Random (PPR) PN16 pressure pipe for cold, hot and hot water return water as per DIN 8077-8078 for pipes and DIN 16962,PN20 for fittings (polyfusion welded joints) inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting for pipelines, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| 25 mm dia | Rft. | 880 | 238.2673 | 102.1146 | 209675.2331 | 89860.8142 | -555.9571 | 794.2244 |  | 166.7871 | 71.4802
| 32 mm dia | Rft. | 374 | 357.401 | 153.1718 | 133667.9611 | 57286.2691 | -833.9356 | 1191.3366 |  | 250.1807 | 107.2203
| 40 mm dia | Rft. | 207 | 510.5728 | 218.8169 | 105688.5713 | 45295.102 | -1191.3366 | 1701.9094 |  | 357.401 | 153.1718
| 50 mm dia | Rft. | 55 | 748.8401 | 320.9315 | 41186.2065 | 17651.2314 | -1747.2936 | 2496.1337 |  | 524.1881 | 224.652
| 75 mm dia | Rft. | 208 | 1347.9122 | 577.6767 | 280365.7403 | 120156.7459 | -3145.1285 | 4493.0407 |  | 943.5385 | 404.3737
[6 empty] | 0 | 0 | 0 | 0
| GATE / BALL VALVE |  |  |  |  | 0 | 0 | 0 | 0
2.2 | Providing and installing gate/ball valves of following nominal dia, of approved equivalent make ,including jointing ,fitting, painting, testing, complete in all respects to match with following PPR pipe diameters. |  |  |  |  | 0 | 0 | 0 | 0
| 25 mm dia | Each | 8 | 7828.7831 | 3355.1927 | 62630.2644 | 26841.5419 | -18267.1605 | 26095.9435 |  | 5480.1481 | 2348.6349
| 32 mm dia | Each | 10 | 9939.1507 | 4259.636 | 99391.5066 | 42596.36 | -23191.3515 | 33130.5022 |  | 6957.4055 | 2981.7452
| 40 mm dia | Each | 11 | 11062.4108 | 4741.0332 | 121686.5192 | 52151.3654 | -25812.292 | 36874.7028 |  | 7743.6876 | 3318.7233
| 75 mm dia | Each | 4 | 44249.6434 | 18964.1329 | 176998.5734 | 75856.5315 | -103249.1678 | 147498.8112 |  | 30974.7504 | 13274.893
[6 empty] | 0 | 0 | 0 | 0
| Total Amount (Rs.) Part - 2 |  |  |  |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
| Part-3: INTERNAL SEWERAGE , VENTS & ROOF DRAINAGE |  |  |  |  | 0 | 0 | 0 | 0
3.1 | Providing, fixing, jointing and testing uPVC pipe including all fittings such as tees, bends and reducers. Also it includes the cost of joint solutions & clamping to walls, ceiling hangers, supports, cutting through walls for pipelines and pipe fittings of the following diameters, complete in all respect as per specifications and drawings as well as directed by the Engineer. |  |  |  |  | 0 | 0 | 0 | 0
| BSEN 1329 |  |  |  |  | 0 | 0 | 0 | 0
| 50 mm dia | Rft. | 308 | 374.4201 | 160.4657 | 115321.3782 | 49423.4478 | -873.6468 | 1248.0669 |  | 262.094 | 112.326
| 75 mm dia | Rft. | 48 | 612.6874 | 262.5803 | 29408.9937 | 12603.8545 | -1429.6039 | 2042.2912 |  | 428.8812 | 183.8062
| 100 mm dia | Rft. | 1256 | 987.1074 | 423.046 | 1239806.9305 | 531345.8274 | -2303.2507 | 3290.3581 |  | 690.9752 | 296.1322
| 200 mm dia | Rft. | 225 | 2144.4058 | 919.0311 | 482491.3035 | 206781.9872 | -5003.6135 | 7148.0193 |  | 1501.0841 | 643.3217
| CLASS :D: BS 3505/PS 3051 (For Pressure Pipe) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 2 inch dia pipe | Rft. | 130 | 476.5346 | 204.2291 | 61949.5007 | 26549.786 | -1111.9141 | 1588.4487 |  | 333.5742 | 142.9604
[6 empty] | 0 | 0 | 0 | 0
| FLOOR DRAIN |  |  |  |  | 0 | 0 | 0 | 0
3.2 | Providing and fixing 4" dia Floor Drain with P-trap including Stainless Steel grating and cover of approved make including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 22 | 5786.4918 | 2479.9251 | 127302.8201 | 54558.3515 | -13501.8143 | 19288.3061 |  | 4050.5443 | 1735.9475
[6 empty] | 0 | 0 | 0 | 0
| CLEAN-OUT |  |  |  |  | 0 | 0 | 0 | 0
3.3 | Providing and fixing 4" dia Clean-out for uPVC Pipes including Stainless Steel Cover Plate of approved make, core cutting of Slab concrete and its water proofed refilling as approved by Engineer In charge and complete in all respect. | Nos. | 8 | 5786.4918 | 2479.9251 | 46291.9346 | 19839.4005 | -13501.8143 | 19288.3061 |  | 4050.5443 | 1735.9475
[6 empty] | 0 | 0 | 0 | 0
| Total Amount (Rs.) Part - 3. |  |  |  |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
| Part-4: FIRE FIGHTING SYSTEM |  |  |  |  | 0 | 0 | 0 | 0
4.1 | Providing and fixing Mild Steel Schedule 40 Seamless Pipes including all fittings such as tees, bends and reducers with cost of clamping to walls and ceiling hangers, supports, cutting through walls and concrete in slabs with core cutter for pipelines and pipe fittings of the following diameters complete in all respect. |  |  |  |  | 0 | 0 | 0 | 0
| 2-1/2" dia (63mm) | Rft. | 576 | 1463.642 | 627.2752 | 843057.8205 | 361310.4945 | -3415.1648 | 4878.8068 |  | 1024.5494 | 439.0926
| 4" dia (100mm) | Rft. | 612 | 2689.0168 | 1152.4358 | 1645678.2747 | 705290.6892 | -6274.3725 | 8963.3893 |  | 1882.3118 | 806.705
[6 empty] | 0 | 0 | 0 | 0
| GATE / BALL VALVE |  |  |  |  | 0 | 0 | 0 | 0
4.2 | Providing and installing gate/ball valves of following nominal dia, of approved make, including jointing, fitting, painting, testing, complete in all respects to match with following pipe dia meters. |  |  |  |  | 0 | 0 | 0 | 0
| 2-1/2" dia (63mm) | Nos. | 12 | 62834.4936 | 26929.0687 | 754013.9228 | 323148.8241 | -146613.8183 | 209448.3119 |  | 43984.1455 | 18850.3481
[6 empty] | 0 | 0 | 0 | 0
| LANDING VALVE |  |  |  |  | 0 | 0 | 0 | 0
4.3 | Providing, Installing, testing and commissioning Landing valves in Stair hall on intermediate landings with reducing tee of size 4"x2-1/2" as required by NFPA codes for including jointing, fitting, testing, including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 7 | 45611.1708 | 19547.6446 | 319278.1959 | 136833.5125 | -106426.0653 | 152037.2362 |  | 31927.8196 | 13683.3513
[6 empty] | 0 | 0 | 0 | 0
| HOSE REEL CABINET |  |  |  |  | 0 | 0 | 0 | 0
4.4 | Providing, Installing, testing and commission fire hose reel cabinets, swing type hose reel in cabinet, Dia 1" x 100' long, swing type with imported high pressure PE pipe house, and imported jet/spray/shut nozzle, in steel cabinet (34" x 32" x 10.5") where indicated on drawings including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 12 | 119133.6552 | 51057.2808 | 1429603.8624 | 612687.3696 | -277978.5288 | 397112.184 |  | 83393.5586 | 35740.0966
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
| ALARM CHECK ASSEMBLY |  |  |  |  | 0 | 0 | 0 | 0
4.5 | Installing and fixing Alarm Check Valve Wt type 4" Flanged End Complete set with Basic trim, Pressure switch, Retard chamber and water motor alarm Gong, UL Listed and FM Approved | Nos. | 1 | 328468.5065 | 140772.2171 | 328468.5065 | 140772.2171 | -766426.5151 | 1094895.0216 |  | 229927.9545 | 98540.5519
[6 empty] | 0 | 0 | 0 | 0
| PILLAR TYPE FIRE HYDRANT |  |  |  |  | 0 | 0 | 0 | 0
4.6 | Providing, Installing, testing and commissiong Pillar type fire hydrants with inlet flanged 4" size with double deliveries 2 1/2" female instantaneous coupling with blank cap and chain, including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 2 | 143130.5772 | 61341.6759 | 286261.1543 | 122683.3519 | -333971.3467 | 477101.9239 |  | 100191.404 | 42939.1732
[6 empty] | 0 | 0 | 0 | 0
| BREACHING INLET |  |  |  |  | 0 | 0 | 0 | 0
4.7 | Providing, Installation, testing and commissioning of Interconnection with Municipal Fire Brigade (Siamese connection), consisting of breach inlet valve and casing, flang 4" dia, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 1 | 67395.6107 | 28883.8331 | 67395.6107 | 28883.8331 | -157256.4249 | 224652.0355 |  | 47176.9275 | 20218.6832
[6 empty] | 0 | 0 | 0 | 0
| Total Amount (Rs.) Part - 4. |  |  |  |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
| Part-5: MISCELLANEOUS |  |  |  |  | 0 | 0 | 0 | 0
| UNDERGROUND WATER TANK |  |  |  |  | 0 | 0 | 0 | 0
5.1 | Providing, placing sleeves and puddle flange in R.C.C. under ground water tank walls, pipe connection (G.I) with inlet / outlet pipe work, manhole covers, floating ball valve etc, including all necessary accessories required for sleeces placing, complete in all respects. | Job | 1 | 57864.9182 | 24799.2507 | 57864.9182 | 24799.2507 | -135018.1426 | 192883.0608 |  | 40505.4428 | 17359.4755
[6 empty] | 0 | 0 | 0 | 0
| OVERHEAD WATER TANK |  |  |  |  | 0 | 0 | 0 | 0
5.2 | Providing, placing sleeves and puddle flange in R.C.C. over head water tank walls, pipe connection (G.I) with inlet / outlet pipe work, manhole covers, floating ball valve etc, including all necessary accessories required for sleeves placing, complete in all respects. | Job | 1 | 30634.3685 | 13129.0151 | 30634.3685 | 13129.0151 | -71480.1931 | 102114.5616 |  | 21444.0579 | 9190.3105
[6 empty] | 0 | 0 | 0 | 0
| SEPTIC TANK |  |  |  |  | 0 | 0 | 0 | 0
5.3 | Providing, placing sleeves and puddle flange in R.C.C. over head water tank walls, pipe connection (G.I) with inlet / outlet pipe work, manhole covers, floating ball valve etc, including all necessary accessories required for sleeves placing, complete in all respects. | Job | 1 | 30634.3685 | 13129.0151 | 30634.3685 | 13129.0151 | -71480.1931 | 102114.5616 |  | 21444.0579 | 9190.3105
[6 empty] | 0 | 0 | 0 | 0
| STORAGE GEYSER |  |  |  |  | 0 | 0 | 0 | 0
5.4 | Providing, installing, testing and commission of storage type electric geyser of approved make 25 Liters capacity complete with inlet, outlet, safety valves complete in all respects. | Nos. | 14 | 64672.5557 | 27716.8096 | 905415.7795 | 388035.3341 | -150902.6299 | 215575.1856 |  | 45270.789 | 19401.7667
[6 empty] | 0 | 0 | 0 | 0
| Total Amount (Rs.) Part - 5. |  |  |  |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
| Part-6: GI PIPES |  |  |  |  | 0 | 0 | 0 | 0
6.1 | Providing, fixing, jointing and testing G.I pipes and fittings inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting and core cutter for cutting of concrete slab with sealing and water proofing with epoxy grouting for pipelines complete in all respects. |  |  |  |  | 0 | 0 | 0 | 0
| 1-1/2 inch dia | Rft | 165 | 987.1074 | 423.046 | 162872.7257 | 69802.5967 | -2303.2507 | 3290.3581 |  | 690.9752 | 296.1322
| 2 inch dia | Rft | 12 | 1157.2984 | 495.985 | 13887.5804 | 5951.8202 | -2700.3629 | 3857.6612 |  | 810.1089 | 347.1895
| 2-1/2 inch dia | Rft | 126 | 1347.9122 | 577.6767 | 169836.9388 | 72787.2595 | -3145.1285 | 4493.0407 |  | 943.5385 | 404.3737
| 3 inch dia | Rft | 290 | 1667.8712 | 714.8019 | 483682.6401 | 207292.56 | -3891.6994 | 5559.5706 |  | 1167.5098 | 500.3614
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| GATE / BALL VALVE |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
6.2 | Providing and installing gate/ball valves of following nominal dia, of approved make ,including jointing ,fitting, painting, testing, complete in all respects to match with following G.I pipe diameters. |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 1-1/2 inch dia | Nos. | 4 | 12594.1293 | 5397.484 | 50376.5171 | 21589.9359 | -29386.3016 | 41980.4309 |  | 8815.8905 | 3778.2388
| 2 inch dia | Nos. | 1 | 19674.0722 | 8431.7452 | 19674.0722 | 8431.7452 | -45906.1685 | 65580.2407 |  | 13771.8505 | 5902.2217
| 2-1/2 inch dia | Nos. | 7 | 28932.4591 | 12399.6253 | 202527.2138 | 86797.3774 | -67509.0713 | 96441.5304 |  | 20252.7214 | 8679.7377
| 3 inch dia | Nos. | 1 | 46291.9346 | 19839.4005 | 46291.9346 | 19839.4005 | -108014.514 | 154306.4486 |  | 32404.3542 | 13887.5804
[6 empty] | 0 | 0 | 0 | 0
| Total Amount (Rs.) Part - 6. |  |  |  |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
| Part-07:- PLUMBING EQUIPMENT |  |  |  |  | 0 | 0 | 0 | 0
| FIRE FIGHTING PUMP SET |  |  |  |  | 0 | 0 | 0 | 0
7.1 | Providing, Fixing ,testing & installing pump set for fire fighting of following capacities. Pump set shall be Standard Firefighting Pump: |  |  |  |  | 0 | 0 | 0 | 0
| a) Horizontal centrifugal pump set (50Hz x 380V, 3 phase Motor) 350 GPM @ 5 bar complete with automatic control panel , Pressure switch & Pressure gauge. It should be capable of operating 1 remotest 21/2" hydrants 200 GPM each @ min. 4.5 bar pressure |  |  |  |  | 0 | 0 | 0 | 0
| b) Horizontal centrifugal engine driven pump set 350 GPM @ 5 bar complete with automatic control panel , Pressure switch, Pressure gauge & diesel tank. It should be capable of operating 1 remotest 21/2" hydrants 200 GPM each @ min. 4.5 bar pressure |  |  |  |  | 0 | 0 | 0 | 0
| c) Jockey electric motor driven pump set (50Hz x 380 V ,3Ph Motor) 25 GPM @ 5.5 bar complete with automatic control panel, pressure switch and pressure gauge. |  |  |  |  | 0 | 0 | 0 | 0
| d) Pump control cabinet for above mentioned pump. |  |  |  |  | 0 | 0 | 0 | 0
| e) Pump room's fitting and controls i.e. gate valves, NRV, expansion joints, headers, pressure reducing/ relief valve, test return line to reservoir, supports and painting. | Set | 1 | 4459342.905 | 1911146.9593 | 4459342.905 | 1911146.9593 | -10405133.4449 | 14864476.3498 |  | 3121540.0335 | 1337802.8715
[6 empty] | 0 | 0 | 0 | 0
| WATER TRANSFER PUMP |  |  |  |  | 0 | 0 | 0 | 0
7.2 | Providing, Installing, fixing, testing and commission, centrifugal pumps of make KSB, Grundfos or approved equivalent (2 Nos. - 1 running + 1 standby) of capacity 75 gpm each with stainless steel impeller capable of pumping against a total pumping head of 110 ft. coupled with water cooled electric motor of , 440 volts, 3 - phase, 50 Hz. The pump shall be provided with control panel having auto / manual switches, dry running protection, low / high level water controls with alternative standby duty operation system, complete in all respects. | Set. | 1 | 980299.7913 | 420128.482 | 980299.7913 | 420128.482 | -2287366.1798 | 3267665.9711 |  | 686209.8539 | 294089.9374
[6 empty] | 0 | 0 | 0 | 0
| SUMP PUMP |  |  |  |  | 0 | 0 | 0 | 0
7.3 | Providing, Installing, testing and commissioning non-clogging, centrifugal submersible Drainage pumps 30 gpm against a total pumping head of 35 ft (one running one standby). coupled with water cooled IP Class 68 electric motor of 2 HP, 400 volts, 3 - phase, 50 Hz. of approved make with auto / manual switches, dry running protection, low / high level water controls, gate valves, NRV, flexible Joints, Strainer, with alternative standby duty operation system),All accesorries/consumables to be provided by contractor. | Set. | 1 | 510572.808 | 218816.9177 | 510572.808 | 218816.9177 | -1191336.552 | 1701909.36 |  | 357400.9656 | 153171.8424
[6 empty] | 0 | 0 | 0 | 0
| WATER SUPPLY BOOSTER (MINI) |  |  |  |  | 0 | 0 | 0 | 0
7.4 | Supply, Installing, fixing, testing and commissioning of Water Pressure Booster Pump (1 working + 1 standby) with a capacity of 25 USGPM against a total head of 40 feet. The pump shall be provided with control panel having auto / manual switches, dry running protection, low / high level water controls with alternative standby duty operation system, complete in all respects. | Set | 1 | 442496.4336 | 189641.3287 | 442496.4336 | 189641.3287 | -1032491.6784 | 1474988.112 |  | 309747.5035 | 132748.9301
Total Amount (Rs.) Part - 7.
SUMMARY
Sub-Total (Plumbing Fixtures)
Sub-Total (Internal Water Supply)
Sub-Total (Internal Sewerage, Vents & Roof Drainage)
Sub-Total (Fire Fighting System)
Sub-Total (Miscellaneous)
Sub-Total (GI Pipes)
Sub-Total (Plumbing Equipment)
Sub-Total ( 0.25 Cusec Tube Well)
Total Amount | [5 empty] | 22400000 | 9600000 |  |  |  | 32000000 |  | -22400000 | -233.3%
SST 15% | [6 empty] | 1440000 |  |  |  | 22400000 |  |  | -22400000
Grand Total Amount | [6 empty] | 33440000 |  |  |  | 9600000 |  |  | 32000000
1248000
33248000
Note:
It should be clearly understood by the contractor / bidder that the above mentioned items shall be complete in all respects, including cost of all necessary materials / accessories whether mentioned or not but are required for proper functioning of the system shall be deemed to be included in the cost of each above mentioned items, no extra charge shall be paid or claimed by the contractor / bidder.
[9 empty] | Amount Without Taxes | 22400000 | 9600000 | 32000000
[9 empty] | SST 13% on Labor | 0 | 1248000 | 1248000
[9 empty] | Grand total inclusive of all taxes | 22400000 | 10848000 | 33248000

## Tube well
MEEZAN BANK LIMITED MAKKAH TOWER, GUJRANWALA
BILL OF QUANTITIES
DRILLING AND INSTALLATION OF 0.25 CUSEC TUBE WELL
Sr. No. | Description | Unit. | Qty | Rate(Rs) | Amount (Rs.)
1 | Mobilization Demobilization of drilling equipment, materials and crew. | Job | 1 | 50000 | 50000
2 | SITE PREPARATION
| Excavation of drilling Pit and Supply well. | Job | 1 | 400000 | 400000
3 | TUBEWELL BORING
Drilling of bore dia 16" (408 mm) i/d for tubewell in all type of soils except shingle and rock.
| From ground level to 100 ft depth. | Rft | 100 | 650 | 65000
| From 100 ft to 200 ft depth | Rft | 100 | 700 | 70000
| From 200 ft to 300 ft depth | Rft | 100 | 750 | 75000
| From 300 ft to 400 ft depth | Rft | 100 | 800 | 80000
| From 400 ft to 500 ft depth | Rft | 100 | 850 | 85000
| From 500 ft to 600 ft depth | Rft | 100 | 900 | 90000
| From 600 ft to 700 ft depth | Rft | 100 | 950 | 95000
4 | TUBEWELL MATERIALS
4.1 | Housing
| Supply and installation of Fiberglass, Dia: 8", wall thickness: 6mm, including welding etc. | Rft | 220 | 3010.5 | 662310
4.2 | Strainer
Providing and installing Fiberglass Reinforced Polypropelene (FRP) strainer of specifid wall thickness having slot size of 0.9 mm to 1.10 mm in Tubewell borehole i/c the cost of male/female coupling with Nylone Strip,studs complete in all respect as approved and directed by the Engineer Incharge.
| 6" inch dia (5 mm thickness) | Rft | 90 | 2524.5 | 227205
4.3 | Blind Pipe
| Supply & installing fiberglass pipes, Dia:6", wall thickness: 5mm, including nylon sticks etc. | Rft | 380 | 2430 | 923400
4.4 | Bail Plug
| Supply and installing of fiberglass bail plug, Dia:6", wall thickness: 5mm, Slot Size: 1mm, including nylon sticks etc. | Rft | 10 | 2430 | 24300
4.5 | Reducer
| Supply and installation of MS Reducer Dia: 8"/6", Wall thickness: 6mm, including welding etc | Each | 1 | 22950 | 22950
4.6 | Pea Gravels (Shrouding)
| Supply of Pea Gravels of gradation appropriate to 1 mm slot size from Attock quarry, including sieving, washing and lowering in the annular space of the borehole | Cft | 865 | 310.5 | 268582.5
4.7 | GI Pipe
| Providing, fixing, cutting, jointing and testing 2 inch dia GI medium gauge piping for pea gravels (Shrouding) including GI fittings with welding, complete in all respects. | Rft | 100 | 742.5 | 74250
5 | M.S PLATE
| Providing and fixing, M.S bore cover plate 2'-6'' x 2'-6'' including paint complete in all respect | Kgs | 120 |  | 56700
6 | AIR VALVE
Providing and fixing, air valve 2½ (65mm) dia of B.S.S.quality and weight (complete with jointing material).
| 2 1/2 inch dia | No. | 1 | 33750 | 33750
7 | GATE VALVE
Providing and fixing, Cast Iron flanged Gate Valve (B.S. 5163) quality and weight with jointing material complete in all respect and directed by the Engineer-in-charge:-
| 4 inch dia | No. | 1 | 81000 | 81000
8 | NON-RETURN VALVE/ CHECK VALVE
Providing and fixing, Cast Iron flanged Non Return Valve (B.S. 5153) quality and weight with jointing material complete in all respect and directed by the Engineer-in-charge:-
| 4 inch dia | No. | 1 | 87750 | 87750
9 | FLOW METER
| Providing and fixing, analog and recordable flow meter / water meter complete in all respect and directed by the Engineer-in-charge. | No. | 1 | 60750 | 60750
10 | PRESSURE GUAGE
| Providing and installing Pressure guages made up of stainless steel body having pressure of 0-16 bars. | No. | 1 | 16200 | 16200
11 | SOIL SAMPLING
| Taking soil samples at every 5 ft interval or at change of strata, which ever is less, Sieve analyses. | Job | 140 | 0 | 25650
12 | ELECTRICAL LOGGING
| Electrical Logging for analysing water quality and tubewell designing | Job | 1 | 65475 | 65475
13 | DEVELOPMENT
| Development of tubewell for 24 - 48 hrs till pumped water is sand free and the formation around well has stabilized to the satisfaction of Engineer | Job | 1 | 81000 | 81000
14 | CONCRETE BLOCK
| Construction of cement concrete block RCC ratio 1:2:4 around house pipe, complete in all respect . | Job | 1 | 74250 | 74250
15 | PUMPING MACHINERY
Submersible Pump with Submersible Motor)
PUMP PARAMETERS AND SCOPE OF SUPPLY
| Discharge: 0.25 Cusec | Set | 1 | 2632500 | 2632500
Head: 330ft
Pump Setting: 230ft
Pump Type: Deep Well Submersible Pump KSB or Grundfoss OR Approved Equivalent Submersible Pumps.
Motor Submersible Motor,
Colum Pipe: ERW,
Bowl Assembly: Impellors: SS , Bowls: SS, Shaft SS
MCU with all protection devices, such as over/under current relay, starting method Y/D of metallic box magnetic contactor, circuit breakers on/off switch controle wire under and over voltage protection relay and indication lamps. Ampere and volt meters for each phase, emergency stop button, Suitable size submerssible cable from MCU to motor, complete in all respect as per satisfaction of the engineer in charge.
Accessories: Gate Valve, Non Return Valve, Set of Lowering Clamp, Top Plate, Discharge Bend etc
|  |  | Total Amount Rs. : |  | 6428022.5
NOTE:
After the selection of contractor and before the start of drilling process the contractor must provide shop drawings to the consultant for approval.

## Ex Water Supply (hidden)
#REF!
EXTERNAL WATER SUPPLY
ENGINEER'S COST ESTIMATE
PLUMBING WORK
Sr. No. | Description | Unit | Quantity | Unit Rate (Rs.) | Amount (Rs.)
EXTERNAL WATER SUPPLY SYSTEM
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 8137.5 | #REF! | #REF!
2 | Providing, transportation, laying, cutting, butt fusion jointing, testing, commissioning & disinfecting the Polyethylene Pipe (PE-100), PN 10, of SDR 17 of any of the manufacturer DADEX and BETA or approved equivalent including fixing all type of fittings and special such as tee, bend,cross collar, reducer, tail piece, flanged spigot,end cap, flanged socket, taper, angle branch, plug etc complete in all respects (Including Injection moulded fittings) as recommended by the manufacturer.
| 4" dia 100 mm | Rft. | 1175 | #REF! | #REF!
G.I Pipe
3 | Providing, fixing, jointing and testing G.I pipes and fittings inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting and core cutter for cutting of concrete slab with sealing and water proofing with epoxy grouting for pipelines complete in all respects.
| 4 inch dia | Rft | 1150 | #REF! | #REF!
GATE / BALL VALVE
4 | Providing and installing gate/ball valves of following nominal dia, of approved equivalent make ,including jointing ,fitting, painting, testing, complete in all respects to match with following PE pipe diameters.
| 4 inch dia | Each | 4 | #REF! | #REF!
Sand Filling
5 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft | 2325 | 20 | 46500
Under Ground Water Tank
6 | Providing, placing sleeves and puddle flange in R.C.C. under ground water tank walls, pipe connection (G.I) with inlet / outlet pipe work, manhole covers, floating ball valve etc, including all necessary accessories required for sleeces placing, complete in all respects. | Job | 2 | 25000 | 50000
| Grand Total |  |  |  | #REF!

## Ex Water Supply (COQ) (hidden)
#REF!
EXTERNAL WATER SUPPLY
PLUMBING WORK
Calculation of Quantities
Sr. No. | Description | Unit | No | L | W | H | Qty
EXTERNAL WATER SUPPLY
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 1 | 2325 | 1 | 3.5 | 8137.5
2 | Providing, transportation, laying, cutting, butt fusion jointing, testing, commissioning & disinfecting the Polyethylene Pipe (PE-100), PN 10, of SDR 17 of any of the manufacturer DADEX and BETA or approved equivalent including fixing all type of fittings and special such as tee, bend,cross collar, reducer, tail piece, flanged spigot,end cap, flanged socket, taper, angle branch, plug etc complete in all respects (Including Injection moulded fittings) as recommended by the manufacturer.
| 4" dia 100 mm | Rft |  | 1175 |  |  | 1175
G.I Pipe
3 | Providing, fixing, jointing and testing G.I pipes and fittings inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting and core cutter for cutting of concrete slab with sealing and water proofing with epoxy grouting for pipelines complete in all respects.
| 4 inch dia | Rft. |  | 1150 |  |  | 1150
4 | Providing and installing gate/ball valves of following nominal dia, of approved equivalent make ,including jointing ,fitting, painting, testing, complete in all respects to match with following PE pipe diameters.
| 4 inch dia | Nos. |  | 4 |  |  | 4
Sand Filling
5 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft |  | 2325 | 1 | 1 | 2325
Under Ground Water Tank
6 | Providing, placing sleeves and puddle flange in R.C.C. under ground water tank walls, pipe connection (G.I) with inlet / outlet pipe work, manhole covers, floating ball valve etc, including all necessary accessories required for sleeces placing, complete in all respects. | Job | 2 |  |  |  | 2

## Ex Sewerage (hidden)
CLUB HOUSE BAHAWALPUR
EXTERNAL SEWERAGE
ENGINEER'S COST ESTIMATE
PLUMBING WORK
Sr. No. | Description | Unit | Quantity | Unit Rate (Rs.) | Amount (Rs.)
EXTERNAL SEWERAGE
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 15198.75 | #REF! | #REF!
uPVC Pipe
2 | Providing and fixing uPVC pipe including all fittings such as tees, bends and reducers. Also it includes the cost of joint solutions for pipelines and pipe fittings of the following diameters, complete in all respect as per specifications and drawings as well as directed by the Engineer.
BSEN 1329
| 200 mm dia | Rft. | 2325 | #REF! | #REF!
| 250 mm dia | Rft. | 570 | #REF! | #REF!
Sand Filling
3 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft | 6513.75 | 20 | 130275
Brick Work Manhole
4 | Construction of square manhole of 2'x2' for sewer complete with 9" thick brick work ratio 1:3, plastering from internal and external side Ratio 1:3, PCC 1:4:8 base, RCC slab, benching with 1:2:4 cement concrete, including 18" dia manhole cover and frame, including all necessary accessories required for installation, complete in all respect as per specifications and drawings and as directed by the Engineer. | Each | 45 | #REF! | #REF!
Septic Tank
5 | Providing, placing sleeves and puddle flange in brick work walls, pipe connection (G.I) with inlet / outlet pipe work, manhole covers etc, including all necessary accessories required for sleeces placing, complete in all respects. | Nos | 1 | 20000 | 20000
| Grand Total |  |  |  | #REF!

## Ex Sewerage (COQ) (hidden)
CLUB HOUSE BAHAWALPUR
EXTERNAL SEWERAGE
PLUMBING WORK
Calculation of Quantities
Sr. No. | Description | Unit | No | L | W | H | Qty
EXTERNAL SEWERAGE
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 1 | 2895 | 1.5 | 3.5 | 15198.75
2 | Providing and fixing uPVC pipe including all fittings such as tees, bends and reducers. Also it includes the cost of joint solutions for pipelines and pipe fittings of the following diameters, complete in all respect as per specifications and drawings as well as directed by the Engineer.
BSEN 1329
| 200mm dia | Rft. |  | 2325 |  |  | 2325
| 250 mm dia | Rft. |  | 570 |  |  | 570
Sand Filling
3 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft | 1 | 2895 | 1.5 | 1.5 | 6513.75
4 | Construction of square manhole of 2'x2' for sewer complete with 9" thick brick work ratio 1:3, plastering from internal and external side Ratio 1:3, PCC 1:4:8 base, RCC slab, benching with 1:2:4 cement concrete, including 18" dia manhole cover and frame, including all necessary accessories required for installation, complete in all respect as per specifications and drawings and as directed by the Engineer. | Nos. | 45 |  |  |  | 45
Septic Tank
5 | Providing, placing sleeves and puddle flange in brick work walls, pipe connection (G.I) with inlet / outlet pipe work, manhole covers etc, including all necessary accessories required for sleeces placing, complete in all respects. | Job | 1 |  |  |  | 1

## Ex Fire Fighting (hidden)
#REF!
EXTERNAL FIRE FIGHTING
ENGINEER'S COST ESTIMATE
PLUMBING WORK
Sr. No. | Description | Unit | Quantity | Unit Rate (Rs.) | Amount (Rs.)
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 18768.75 | #REF! | #REF!
P.E Pipe
2 | Providing, transportation, laying, cutting, butt fusion jointing, testing, commissioning & disinfecting the Polyethylene Pipe (PE-100), PN 10, of SDR 17 of any of the manufacturer DADEX and BETA or approved equivalent including fixing all type of fittings and special such as tee, bend,cross collar, reducer, tail piece, flanged spigot,end cap, flanged socket, taper, angle branch, plug etc complete in all respects (Including Injection moulded fittings) as recommended by the manufacturer.
| 4 inch dia | Rft. | 3575 | #REF! | #REF!
Gate Valve
3 | Providing and installing gate/ball valves of following nominal dia, of approved make, including jointing, fitting, painting, testing, complete in all respects to match with following pipe dia meters.
| 4 inch dia | Nos. | 5 | #REF! | #REF!
Sand Filling
4 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft | 8043.75 | 20 | 160875
Pillar Type Fire Hydrant
5 | Providing, Installing, testing and commissiong Pillar type fire hydrants with inlet flanged 4" size with double deliveries 2 1/2" female instantaneous coupling with blank cap and chain, including all necessary accessories required for installation, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 15 | #REF! | #REF!
Interconnection with Municipal Fire Brigade
6 | Providing, Installation, testing and commissioning of Interconnection with Municipal Fire Brigade (Siamese connection), consisting of breach inlet valve and casing, flang 4" dia, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Nos. | 1 | #REF! | #REF!
| Grand Total |  |  |  | #REF!

## Ex Fire Fighting (COQ) (hidden)
#REF!
EXTERNAL FIRE FIGHTING
PLUMBING WORK
Calculation of Quantities
Sr. No. | Description | Unit | No | L | W | H | Qty.
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 1 | 3575 | 1.5 | 3.5 | 18768.75
P.E Pipe
2 | Providing, transportation, laying, cutting, butt fusion jointing, testing, commissioning & disinfecting the Polyethylene Pipe (PE-100), PN 10, of SDR 17 of any of the manufacturer DADEX and BETA or approved equivalent including fixing all type of fittings and special such as tee, bend,cross collar, reducer, tail piece, flanged spigot,end cap, flanged socket, taper, angle branch, plug etc complete in all respects (Including Injection moulded fittings) as recommended by the manufacturer.
| 4" dia 100 mm | Rft | 1 | 3575 |  |  | 3575
3 | Providing and installing gate/ball valves of following nominal dia, of approved equivalent make ,including jointing ,fitting, painting, testing, complete in all respects to match with following PE pipe diameters.
| 4 inch dia | Nos. | 5 |  |  |  | 5
Sand Filling
4 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft | 1 | 3575 | 1.5 | 1.5 | 8043.75
Pillar Type Fire Hydrant
5 | Providing, Installing, testing and commissiong Pillar type fire hydrants with inlet flanged 4" size with double deliveries 2 1/2" female instantaneous coupling with blank cap and chain, including all necessary accessories required for installation, complete in all respects. | Nos. | 15 |  |  |  | 15
Interconnection with Municipal Fire Brigade
6 | Providing, Installation, testing and commissioning of Interconnection with Municipal Fire Brigade (Siamese connection), consisting of breach inlet valve and casing, flang 4" complete in all respects. | Nos. | 1 |  |  |  | 1

## Irrigation (hidden)
#REF!
IRRIGATION
ENGINEER'S COST ESTIMATE
PLUMBING WORK
Sr. No. | Description | Unit | Quantity | Unit Rate (Rs.) | Amount (Rs.)
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 26775 | #REF! | #REF!
P.E Pipe
2 | Providing, transportation, laying, cutting, butt fusion jointing, testing, commissioning & disinfecting the Polyethylene Pipe (PE-100), PN 10, of SDR 17 of any of the manufacturer DADEX and BETA or approved equivalent including fixing all type of fittings and special such as tee, bend,cross collar, reducer, tail piece, flanged spigot,end cap, flanged socket, taper, angle branch, plug etc complete in all respects (Including Injection moulded fittings) as recommended by the manufacturer.
| 4 inch dia | Rft. | 5100 | #REF! | #REF!
Gate Valve
3 | Providing and installing gate/ball valves of following nominal dia, of approved make, including jointing, fitting, painting, testing, complete in all respects to match with following pipe dia meters.
| 1-1/2 inch dia | Nos. | 10 | #REF! | #REF!
| 4 inch dia | Nos. | 5 | #REF! | #REF!
Sand Filling
4 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft | 11475 | 20 | 229500
| Grand Total |  |  |  | #REF!

## Irrigation (COQ) (hidden)
#REF!
IRRIGATION
PLUMBING WORK
Calculation of Quantities
Sr. No. | Description | Unit | No | L | W | H | Qty.
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 1 | 5100 | 1.5 | 3.5 | 26775
P.E Pipe
2 | Providing, transportation, laying, cutting, butt fusion jointing, testing, commissioning & disinfecting the Polyethylene Pipe (PE-100), PN 10, of SDR 17 of any of the manufacturer DADEX and BETA or approved equivalent including fixing all type of fittings and special such as tee, bend,cross collar, reducer, tail piece, flanged spigot,end cap, flanged socket, taper, angle branch, plug etc complete in all respects (Including Injection moulded fittings) as recommended by the manufacturer.
| 4" dia 100 mm | Rft | 1 | 5100 |  |  | 5100
3 | Providing and installing gate/ball valves of following nominal dia, of approved equivalent make ,including jointing ,fitting, painting, testing, complete in all respects to match with following PE pipe diameters.
| 1-1/2 inch dia | Nos. | 10 |  |  |  | 10
| 4 inch dia | Nos. | 5 |  |  |  | 5
Sand Filling
4 | Supplying and filling sand under floor; or plugging in wells, complete in all respect and as directed by the engineer incharge. | Cft | 1 | 5100 | 1.5 | 1.5 | 11475

## Ex Gas Supply (hidden)
CLUB HOUSE BAHAWALPUR
EXTERNAL GAS SUPPLY
ENGINEER'S COST ESTIMATE
PLUMBING WORK
Sr. No. | Description | Unit | Quantity | Unit Rate (Rs.) | Amount (Rs.)
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 4862.5 | #REF! | #REF!
G.I Pipe
2 | Providing, fixing, jointing and testing G.I pipes and fittings inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting and core cutter for cutting of concrete slab with sealing and water proofing with epoxy grouting for pipelines complete in all respects.
| 1 inch dia | Rft | 795 | #REF! | #REF!
| 1-1/2 inch dia | Rft | 50 | #REF! | #REF!
| 2 inch dia | Rft | 1100 | #REF! | #REF!
Gate Valve
3 | Providing and installing gate/ball valves of following nominal dia, of approved make ,including jointing ,fitting, painting, testing, complete in all respects to match with following G.I pipe diameters.
| 1 inch dia | No | 2 | #REF! | #REF!
| 1-1/2 inch dia | No | 1 | #REF! | #REF!
| 2 inch dia | No | 4 | #REF!
| Grand Total |  |  |  | #REF!

## Ex Gas Supply (COQ) (hidden)
CLUB HOUSE BAHAWALPUR
EXTERNAL GAS SUPPLY
PLUMBING WORK
Calculation of Quantities
Sr. No. | Description | Unit | No | L | W | H | Qty
Excavation / Backfilling
1 | Excavation and backfilling (0' to 5' depth) in open cutting for sewers and manholes as shown in drawings including dressing to correct section and dimensions according to templates and levels in all types of soil except shingle, gravel and rock, complete in all respect as per specifications and drawings as well as directed by the Engineer. | Cft | 1 | 1945 | 1 | 2.5 | 4862.5
G.I Pipe
2 | Providing, fixing, jointing and testing G.I pipes and fittings inside building including fittings and specials (sockets, tees, elbows, bends, crosses, reducers, adaptor, plugs and union etc.) supported on walls or suspended from roof slab or run in chases including pipe hangers, supports, walls cutting and core cutter for cutting of concrete slab with sealing and water proofing with epoxy grouting for pipelines complete in all respects.
| 1 inch dia | Rft | 1 | 795 |  |  | 795
| 1-1/2 inch dia | Rft | 1 | 50 |  |  | 50
| 2 inch dia | Rft | 1 | 1100 |  |  | 1100
Gate Valve
3 | Providing and installing gate/ball valves of following nominal dia, of approved make ,including jointing ,fitting, painting, testing, complete in all respects to match with following G.I pipe diameters.
| 1 inch dia | No | 2 |  |  |  | 2
| 1-1/2 inch dia | No | 1 |  |  |  | 1
| 2 inch dia | No | 4 |  |  |  | 4