## HVAC
[6 empty] | Date | 10 Jan 2025
[6 empty] | Quote # | 002
Attn: Mr. Taha Ghaznavi
Variation for Extra work carried out for VRF Outdoor units - Gul Ahmed 7th Floor Tijarah Center Karachi
S. # | Description | Unit | Qty | Material Rate | Labour Rate | Material Amount | Labour Amount
1 | Making existing as built drawings of VRF system. | Job | 1 | 0 | 15000 | 0 | 15000
2 | Removal of installed indoor units wall mounted / cassette type | Nos | 20 | 0 | 7000 | 0 | 140000
a) Dismantle of evaporator coil from indoor unit.
b) Wash with Karchar pump
c) Pressurized with nitrogen and test leak.
d) Satisfaction of leak test reassembled evaporator coil.
e) Clean all body and related parts.
f) Reassemble with evaporator coil and assembled whole unit.
g) Reassemble with evaporator coil and assembled whole unit.
3 | Reinstallation of wall mounted / cassette units at their new desired location. | Nos | 32 | 0 | 5000 | 0 | 160000
4 | Supply and installation of isolation valve for indoor units (Gas + Liquid) (Make Danfoss) |  |  |  |  | 0 | 0
| a) 1/4" Dia | Nos | 5 | 10000 | 2000 | 50000 | 10000
| b) 3/8" Dia | Nos | 25 | 11280 | 2000 | 282000 | 50000
| c) 1/2" Dia | Nos | 5 | 11875 | 2000 | 59375 | 10000
| d) 5/8" Dia | Nos | 22 | 13125 | 2000 | 288750 | 44000
| e) 3/4" Dia | No | 3 | 25625 | 2000 | 76875 | 6000
5 | Supply and installation of Fresh air tube axial fan wall mounted (7500 CFM) (Make BVN) | Nos | 2 | 601800 | 30000 | 1203600 | 60000
6 | Supply and installation of exhaust air wall mounted fan (10000 CFM) (Make BVN) | Nos | 1 | 395300 | 35000 | 395300 | 35000
7 | Providing and installation of electric cables and conduit for the fans. | Job | 1 | 50000 | 30000 | 50000 | 30000
8 | Supply and installation of exhaust air ducting. (20 SWG) | Sft | 250 | 500 | 100 | 125000 | 25000
9 | Removal of existing fan motor, serviced, replaced with new motor (Siemens) and re installation complete in all respect. | Job | 1 | 108011 | 10000 | 108011 | 10000
10 | After installation of copper piping, flushing with nitrogen and freon. (Honeywell) | Jar | 2 | 57230 | 20000 | 114460 | 40000
11 | Dismantle of copper pipes, power / controls cable from VRF condensing units. | Unit | 5 |  | 8000 | 0 | 40000
12 | Regging, liftings and shifting of VRF condensing unit at new location. | Nos | 4 | 0 | 5000 | 0 | 20000
13 | Providing and installation of motorized damper for fresh air units. 24 x 10 (Make Hoenywell) | No | 1 | 82195 | 5000 | 82195 | 5000 | 8640 | 10195.2
Sub Total Amount Rs | [5 empty] | 2835566 | 700000
Total Amount Rs | [6 empty] | 3535566
Note: (for item # 4) Please note that in the BOQ the new copper pipe rates were submitted with the old Y-joints and valves. However, during several meetings, it was decided to replace the old leaking valves with new ones. Accordingly, we installed the new valves as per the decision.
For PIONEER ENGINEERING SERVICES

## eee
|  |  |  | Date | 29 June 2024
|  |  |  | Quotation # | 001
Attn: Mr. Taha Ghaznavi
Quotation
Extra work to be carried out for VRF Outdoor units - Gul Ahmed 7th Floor Tijarah Center Karachi
S. # | Description | Unit | Qty | Rate | Amount
1 | Removal of installaed indoor units service/ pressure tesr of evaporator coil re assebled and reintall adter wood work | Nos | 32 | 10000 | 320000
| Supply and installation of isolation valve for indoor units (Gas + Liquid) |  |  |  | 0
| Making existing as built drawings of VRF system. | Job | 1 | 25000 | 25000
| Makind new piping layout tree for Gree (copper sizing) of system | Job | 1 | 25000 | 25000
5 | Removal Reinstallation of GI sheet metal ducts with new fittings hanger & supports. |  |  |  | 0
6 | Providing and fixing of flexible duct connector for condenser discharge. | Rft | 800 | 6000 | 4800000
1 | Dismantle of copper refrigerent pipes electric power cable control wiring from condensing units. | Job | 1 | 1001 | 1001
2 | Remove all of existing exhaust air ducts |  |  | 1002 | 0
3 | Regging lifting and shifitng of VRF condensing units at new location. |  |  | 1003 | 0
4 | Providing and installation of Newpron pads for condensing units. |  |  | 1004 | 0
9 | Providing an installation of fresh air fans 8000 CFM for condensing units. |  |  | 1009 | 0
9 | Removal of refixing of cable tray. |  |  | 1010 | 0
Total Amount Rs |  |  |  |  | 1001
Note: Copper pipe and new GI Ducts rates already in BOQ, charged accordingly.
Terms & Conditions: 1) Above prices are exclusive of SST 2) Scaffolding included for installation of Platform.
For PIONEER ENGINEERING SERVICES