## SUMMARY
NATIONAL ENGINEERS CO.
ENGRO OFFICE, THF, KHI
SUMMARY OF AMOUNT
S.NO | DESCRIPTION | AMOUNT
PLUMBING
3 | 19THA FLOOR
4 | 19THB FLOOR
| SUB-TOTAL | 0
HVAC
3 | 19THA FLOOR | 12005480.8494
4 | 19THB FLOOR | 9199688.253
| SUB-TOTAL | 21205169.1024
FIRE
3 | 19THA FLOOR | 4836112.956
4 | 19THB FLOOR | 4686724.44
| SUB-TOTAL | 9522837.396
| GRAND TOTAL AMOUNT | 30728006.4984

## 19A-HVAC
SECTION III/A/III: BILL OF QUANTITIES FOR HVAC WORKS (LEVEL-19A)
|  |  | BOQ | [6 empty] | FIRST RUNNING BILL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost | Qty | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7 | 11 | 12 | 12 x 11 | 14 | 14 x 11 | 13 + 15
AIR CONDITIONING AND VENTILATION SYSTEM 19A
| 23 31 00 | Supply, Installation and Commissioning of G.I Sheet metal air ducts as per ASHRAE Standards plenums and other sheet fabrications including splitter dampers, take off, vanes elbows and other necessary fittings as per drawings and specification.
Ducting
A |  | 18 Gauge | 1520 | Sq.ft | 351.88 | 534857.6 | 76 | 115520 | 650377.6 |  | 351.88 | 0 | 76 | 0 | 0
B |  | 22 Gauge | 1560 | Sq.ft | 436.24 | 680534.4 | 76 | 118560 | 799094.4 | 3228.31 | 436.24 | 1408317.9544 | 76 | 245351.56 | 1653669.5144
C |  | 24 Gauge | 4840 | Sq.ft | 478.8 | 2317392 | 76 | 367840 | 2685232 | 4916.66 | 478.8 | 2354096.808 | 76 | 373666.16 | 2727762.968
D |  | 26 Gauge | 110 | Sq.ft | 648.28 | 71310.8 | 76 | 8360 | 79670.8 |  | 648.28 | 0 | 76 | 0 | 0
E | 23 07 00 | Supply, Installation & Commissioning of Closed cell elastromeric Insulation of thickness for G.I Ducts required as per drawings and specifications. | 8180 | Sq.ft | 500 | 4090000 | 60.8 | 497344 | 4587344 | 9665.08 | 500 | 4832540 | 60.8 | 587636.864 | 5420176.864
F |  | Supply, Installation & Commissioning of Coloured wrapping for G.I Ducts required as per drawings and specifications. | 0 | Sq.ft | 76 | 0 | 19 | 0 | 0 |  | 76 | 0 | 19 | 0 | 0
| 23 33 46 | Supply, installation and Commissioning of flexible ducts complete in all respects as per schedule, drawings and specifications.
F |  | 8" Diameter | 154 | Rft. | 677.92 | 104399.68 | 83.6 | 12874.4 | 117274.08 | 515 | 677.92 | 349128.8 | 83.6 | 43054 | 392182.8
G |  | 6" Diameter | 19 | Rft. | 593.56 | 11277.64 | 83.6 | 1588.4 | 12866.04 |  | 593.56 | 0 | 83.6 | 0 | 0
H |  | 4" Diameter | 2 | Rft. | 551.057 | 1102.114 | 83.6 | 167.2 | 1269.314 |  | 551.057 | 0 | 83.6 | 0 | 0
|  | Sub Total (Page 1) |  |  |  | 7810874.234 |  | 1122254 | 8933128.234 |  |  | 8944083.5624 |  | 1249708.584 | 10193792.1464
Supply, installation and Commissioning of butterfly damper complete in all respects as per schedule, drawings and specifications.
A |  | 8" | 118 | Nos. | 3391.12 | 400152.16 | 836 | 98648 | 498800.16 | 131 | 3391.12 | 444236.72 | 836 | 109516 | 553752.72
B |  | 6" | 15 | Nos. | 2967.23 | 44508.45 | 836 | 12540 | 57048.45 |  | 2967.23 | 0 | 836 | 0 | 0
C |  | 4" | 1 | No. | 2712.896 | 2712.896 | 836 | 836 | 3548.896 |  | 2712.896 | 0 | 836 | 0 | 0
| 23 37 13 | Supply, Installation and Commissioning of Air Devices as per drawings, schedules and specifications.
Supply Air Liner Slot Diffuser
D |  | 3/1"/78" | 3 | Nos. | 9749.47 | 29248.41 | 1672 | 5016 | 34264.41 |  | 9749.47 | 0 | 1672 | 0 | 0
E |  | 3/1"/102" | 1 | No. | 14412.26 | 14412.26 | 1672 | 1672 | 16084.26 |  | 14412.26 | 0 | 1672 | 0 | 0
F |  | 3/1"/114" | 2 | Nos. | 11784.142 | 23568.284 | 1672 | 3344 | 26912.284 |  | 11784.142 | 0 | 1672 | 0 | 0
G |  | 3/1"/192" | 2 | Nos. | 23313.95 | 46627.9 | 1672 | 3344 | 49971.9 |  | 23313.95 | 0 | 1672 | 0 | 0
H |  | 3/1"/186" | 2 | Nos. | 21024.944 | 42049.888 | 1672 | 3344 | 45393.888 |  | 21024.944 | 0 | 1672 | 0 | 0
I |  | 3/1"/72" | 1 | No. | 8901.69 | 8901.69 | 1672 | 1672 | 10573.69 |  | 8901.69 | 0 | 1672 | 0 | 0
J |  | 3/1"/180" | 7 | Nos. | 19922.83 | 139459.81 | 1672 | 11704 | 151163.81 |  | 19922.83 | 0 | 1672 | 0 | 0
K |  | 3/1"/132" | 5 | Nos. | 14836.15 | 74180.75 | 1672 | 8360 | 82540.75 |  | 14836.15 | 0 | 1672 | 0 | 0
L |  | 2/1"/30" | 1 | No. | 4069.344 | 4069.344 | 1672 | 1672 | 5741.344 |  | 4069.344 | 0 | 1672 | 0 | 0
|  | Sub Total (Page 2) |  |  |  | 829891.842 |  | 152152 | 982043.842 |  |  | 444236.72 |  | 109516 | 553752.72
Supply Air Liner Slot Diffuser (Contd.)
A |  | 3/1"/96" | 2 | Nos. | 11445.03 | 22890.06 | 1672 | 3344 | 26234.06 |  | 11445.03 | 0 | 1672 | 0 | 0
B |  | 3/1"/78" | 1 | No. | 9749.47 | 9749.47 | 1672 | 1672 | 11421.47 |  | 9749.47 | 0 | 1672 | 0 | 0
C |  | 3/1"/156" | 1 | No. | 17379.49 | 17379.49 | 1672 | 1672 | 19051.49 |  | 17379.49 | 0 | 1672 | 0 | 0
D |  | 3/1"/120" | 1 | No. | 13564.48 | 13564.48 | 1672 | 1672 | 15236.48 |  | 13564.48 | 0 | 1672 | 0 | 0
E |  | 3/1"/108" | 1 | No. | 11868.92 | 11868.92 | 1672 | 1672 | 13540.92 |  | 11868.92 | 0 | 1672 | 0 | 0
|  | Return Air Liner Slot Diffuser |  |  | 0 | 0 | 0 | 0 | 0
F |  | 1/1"/84" | 2 | Nos. | 4238.9 | 8477.8 | 1672 | 3344 | 11821.8 |  | 4238.9 | 0 | 1672 | 0 | 0
G |  | 3/1"/174" | 1 | No. | 19922.83 | 19922.83 | 1672 | 1672 | 21594.83 |  | 19922.83 | 0 | 1672 | 0 | 0
H |  | 2/1"/30" | 1 | No. | 3815.01 | 3815.01 | 1672 | 1672 | 5487.01 |  | 3815.01 | 0 | 1672 | 0 | 0
I |  | 1/1"/84" | 2 | Nos. | 4238.9 | 8477.8 | 1672 | 3344 | 11821.8 |  | 4238.9 | 0 | 1672 | 0 | 0
J |  | 2/1"/96" | 4 | Nos. | 7630.02 | 30520.08 | 1672 | 6688 | 37208.08 |  | 7630.02 | 0 | 1672 | 0 | 0
K |  | 3/1"/132" | 2 | Nos. | 13564.48 | 27128.96 | 1672 | 3344 | 30472.96 |  | 13564.48 | 0 | 1672 | 0 | 0
L |  | 3/1"/132" | 3 | Nos. | 13564.48 | 40693.44 | 1672 | 5016 | 45709.44 |  | 13564.48 | 0 | 1672 | 0 | 0
M |  | 3/1"/132" | 2 | Nos. | 13564.48 | 27128.96 | 1672 | 3344 | 30472.96 |  | 13564.48 | 0 | 1672 | 0 | 0
N |  | 3/1"/108" | 2 | Nos. | 11868.92 | 23737.84 | 1672 | 3344 | 27081.84 |  | 11868.92 | 0 | 1672 | 0 | 0
O |  | 2/1"/168" | 4 | Nos. | 12547.144 | 50188.576 | 1672 | 6688 | 56876.576 |  | 12547.144 | 0 | 1672 | 0 | 0
P |  | 3/1"/192" | 1 | No. | 21109.722 | 21109.722 | 1672 | 1672 | 22781.722 |  | 21109.722 | 0 | 1672 | 0 | 0
|  | Sub Total (Page 3) |  |  |  | 336653.438 |  | 50160 | 386813.438 |  |  | 0 |  | 0 | 0
Return Air Liner Slot Diffuser
A |  | 3/1"/108" | 1 | No. | 11868.92 | 11868.92 | 1672 | 1672 | 13540.92 |  | 11868.92 | 0 | 1672 | 0 | 0
B |  | 3/1"/228" | 1 | No. | 24585.62 | 24585.62 | 1672 | 1672 | 26257.62 |  | 24585.62 | 0 | 1672 | 0 | 0
C |  | 3/1"/180" | 3 | Nos. | 11868.92 | 35606.76 | 1672 | 5016 | 40622.76 |  | 11868.92 | 0 | 1672 | 0 | 0
D |  | 3/1"/114" | 1 | No. | 13564.48 | 13564.48 | 1672 | 1672 | 15236.48 |  | 13564.48 | 0 | 1672 | 0 | 0
E |  | 3/1"/258" | 1 | No. | 27044.182 | 27044.182 | 1672 | 1672 | 28716.182 |  | 27044.182 | 0 | 1672 | 0 | 0
F |  | 3/1"/60" | 1 | No. | 7630.02 | 7630.02 | 1672 | 1672 | 9302.02 |  | 7630.02 | 0 | 1672 | 0 | 0
G |  | 3/1"/102" | 1 | No. | 13564.48 | 13564.48 | 1672 | 1672 | 15236.48 |  | 13564.48 | 0 | 1672 | 0 | 0
H |  | 3/1"/228" | 1 | No. | 24585.62 | 24585.62 | 1672 | 1672 | 26257.62 |  | 24585.62 | 0 | 1672 | 0 | 0
I |  | 3/1"/66" | 2 | Nos. | 8393.022 | 16786.044 | 1672 | 3344 | 20130.044 |  | 8393.022 | 0 | 1672 | 0 | 0
J |  | 3/1"/78" | 4 | Nos. | 9749.47 | 38997.88 | 1672 | 6688 | 45685.88 |  | 9749.47 | 0 | 1672 | 0 | 0
K |  | 2/1"/84" | 1 | No. | 6697.462 | 6697.462 | 1672 | 1672 | 8369.462 |  | 6697.462 | 0 | 1672 | 0 | 0
L |  | 3/1"/78" | 4 | Nos. | 9749.47 | 38997.88 | 1672 | 6688 | 45685.88 |  | 9749.47 | 0 | 1672 | 0 | 0
M |  | 3/1"/90" | 5 | Nos. | 11445.03 | 57225.15 | 1672 | 8360 | 65585.15 |  | 11445.03 | 0 | 1672 | 0 | 0
|  | Exhaust Air Diffuser |  |  | 0 | 0 | 0 | 0 | 0
A |  | 6"x6" | 9 | Nos. | 2119.45 | 19075.05 | 678.224 | 6104.016 | 25179.066 |  | 2119.45 | 0 | 678.224 | 0 | 0
|  | Sub Total (Page 4) |  |  |  | 336229.548 |  | 49576.016 | 385805.564 |  |  | 0 |  | 0 | 0
| 23 33 05 | Installation, Testing & Commissioning of VAVs complete in all respect as per drawing and specification and schedule.
VAVs
A |  | VAV-19F-A-01 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
B |  | VAV-19F-A-02 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
C |  | VAV-19F-A-03 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
D |  | VAV-19F-A-04 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
E |  | VAV-19F-A-05 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
F |  | VAV-19F-A-06 | 2 | Nos. | 0 | 0 | 7980 | 15960 | 15960 | 2 | 0 | 0 | 7980 | 15960 | 15960
G |  | VAV-19F-A-07 | 4 | Nos. | 0 | 0 | 7980 | 31920 | 31920 | 4 | 0 | 0 | 7980 | 31920 | 31920
H |  | VAV-19F-A-08 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
I |  | VAV-19F-A-09 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
J |  | VAV-19F-A-10 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
K |  | VAV-19F-A-11 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
L |  | VAV-19F-A-12 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
M |  | VAV-19F-A-13 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
N |  | VAV-19F-A-14 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
O |  | VAV-19F-A-15 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
P |  | VAV-19F-A-16 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
|  | Sub Total (Page 5) |  |  |  | 0 |  | 159600 | 159600 |  |  | 0 |  | 159600 | 159600
VAVs (Contd.)
A |  | VAV-19F-A-17 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
B |  | VAV-19F-A-18 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
C |  | VAV-19F-A-19 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
D |  | VAV-19F-A-20 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
E |  | VAV-19F-A-21 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
F |  | VAV-19F-A-22 | 1 | No. | 0 | 0 | 7980 | 7980 | 7980 | 1 | 0 | 0 | 7980 | 7980 | 7980
| 23 33 05 | Supply, Installation and Commissioning of Volume Control Damper for ducts as per SMACNA standards as mentioned in the specifications and drawings.
G |  | 16"x12" | 1 | Nos. | 56801.26 | 56801.26 | 836 | 836 | 57637.26 |  | 56801.26 | 0 | 836 | 0 | 0
Supply, Installation and Commissioning of MS Schedule 40 piping with insulation for supply and return condensor Water piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications.
H |  | 3/4" Diameter | 140 | Rft. | 508.668 | 71213.52 | 101.7336 | 14242.704 | 85456.224 |  | 508.668 | 0 | 101.7336 | 0 | 0
Supply, Installation and Commissioning of U-PVC piping with insulation for condensate drain piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications.
I |  | 1" Diameter | 240 | Rft. | 678.224 | 162773.76 | 127.167 | 30520.08 | 193293.84 | 213 | 678.224 | 144461.712 | 127.167 | 27086.571 | 171548.283
J |  | Sound Trap with duct Z-piece and sound lining for return lot air intake | 1 | Lot | 254334 | 254334 | 60800 | 60800 | 315134 | 1 | 254334 | 254334 | 60800 | 60800 | 315134
|  | Engineering & Programming commissioning testing all above VAVs including Controller and thermostat. | 1 | Lot | 0 | 0 | 140600 | 140600 | 140600 |  | 0 | 0 | 140600 | 0 | 0
|  | Sub Total (Page 6) |  |  |  | 545122.54 |  | 294878.784 | 840001.324 |  |  | 398795.712 |  | 135766.571 | 534562.283
MISCELLANEOUS
A | 01 46 00 | Supply, Installation & Commissioning of brass tags for Equipment and system including all accessories complete in all respect. | 1 | Job | 21194.5 | 21194.5 | 4238.9 | 4238.9 | 25433.4 |  | 21194.5 | 0 | 4238.9 | 0 | 0
B | 23 05 48 | Supply, Installation & Commissioning of hangers and supports for pipes and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 296723 | 296723 | 63583.5 | 63583.5 | 360306.5 | 1 | 296723 | 296723 | 63583.5 | 63583.5 | 360306.5
C | 09 90 00 | Painting on equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 29672.3 | 29672.3 | 12716.7 | 12716.7 | 42389 | 1 | 29672.3 | 29672.3 | 12716.7 | 12716.7 | 42389
D | 23 05 93 23 08 00 | Testing, adjusting, Balancing & Commissioning of HVAC system omplete in all respect. | 1 | Job | 0 | 0 | 144122.6 | 144122.6 | 144122.6 | 0.5 | 0 | 0 | 144122.6 | 72061.3 | 72061.3
E | 07 84 00 | Supply, Installation and commision of fire stopping materials as per specifications and drawings complete in all respect. | 1 | Job | 63583.5 | 63583.5 | 12716.7 | 12716.7 | 76300.2 | 1 | 63583.5 | 63583.5 | 12716.7 | 12716.7 | 76300.2
Drawings
F | 01 00 00 23 05 01 | Shop Drawings and As Built Drawings as per specifications. | 1 | Job | 8477.8 | 8477.8 | 8477.8 | 8477.8 | 16955.6 | 0.75 | 8477.8 | 6358.35 | 8477.8 | 6358.35 | 12716.7
Sundries
G | 01 00 00 23 05 01 | Supply, installing and Commissioning of items not listed in BOQ but required. | 1 | Job | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sub Total (Page 7) |  |  |  | 419651.1 |  | 245856.2 | 665507.3 |  |  | 396337.15 |  | 167436.55 | 563773.7
|  | GRAND TOTAL FOR HVAC WORKS (LEVEL-19A) |  |  |  | 10278422.702 |  | 2074477 | 12352899.702 |  |  | 10183453.1444 |  | 1822027.705 | 12005480.8494

## 19B-HVAC
SECTION III/A/IV: BILL OF QUANTITIES FOR HVAC WORKS (LEVEL-19B)
|  |  | BOQ | [6 empty] | FIRST RUNNING BILL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost | Qty | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7 | 11 | 12 | 12 x 11 | 14 | 14 x 11 | 13 + 15
AIR CONDITIONING AND VENTILATION SYSTEM
| 23 82 19 | Installation, Testing & Commissioning of Ceiling Suspended WCP Units complete with hanger Supports, Vibration Isolator as per drawing and specification.
A |  | WCP-19B-01 | 1 | No. | OFM | OFM | 21194.5 | 21194.5 | 21194.5 | 1 | OFM |  | 21194.5 | 21194.5 | 21194.5
B |  | Automatic Air Vent | 1 | No. | 4238.9 | 4238.9 | 1672 | 1672 | 5910.9 | 1 | 4238.9 | 4238.9 | 1672 | 1672 | 5910.9
C |  | Temperature Sensor | 2 | Nos. | 16531.71 | 33063.42 | 1672 | 3344 | 36407.42 | 2 | 16531.71 | 33063.42 | 1672 | 3344 | 36407.42
Flexible Connectors
D |  | 3/4 inch | 2 | Nos. | 12716.7 | 25433.4 | 1672 | 3344 | 28777.4 | 2 | 12716.7 | 25433.4 | 1672 | 3344 | 28777.4
E |  | Pressure guages | 2 | Nos. | 10597.25 | 21194.5 | 1672 | 3344 | 24538.5 | 2 | 10597.25 | 21194.5 | 1672 | 3344 | 24538.5
Strainer
F |  | 3/4 inch | 2 | Nos. | 13140.59 | 26281.18 | 1672 | 3344 | 29625.18 | 2 | 13140.59 | 26281.18 | 1672 | 3344 | 29625.18
Double Regulating Valve
G |  | 3/4 inch | 1 | No. | 16531.71 | 16531.71 | 1672 | 1672 | 18203.71 | 1 | 16531.71 | 16531.71 | 1672 | 1672 | 18203.71
Gate Valve
H |  | 3/4 inch | 2 | Nos. | 12292.81 | 24585.62 | 1672 | 3344 | 27929.62 | 2 | 12292.81 | 24585.62 | 1672 | 3344 | 27929.62
I |  | 3/4 inch | 1 | No. | 10173.36 | 10173.36 | 1672 | 1672 | 11845.36 | 1 | 10173.36 | 10173.36 | 1672 | 1672 | 11845.36
|  | Sub Total (Page 1) |  |  |  | 161502.09 |  | 42930.5 | 204432.59 |  |  | 161502.09 |  | 42930.5 | 204432.59
| 23 82 19 | Installation and Comissioning of Fan Coil Units, complete in all respects with necessary fittings and as per schedule, drawings and specifications.
A |  | FCU-19B-01 | 1 | No. | OFM | OFM | 5086.68 | 5086.68 | 5086.68 | 1 | OFM |  | 5086.68 | 5086.68 | 5086.68
B |  | FCU-19B-02 | 2 | Nos. | OFM | OFM | 5086.68 | 10173.36 | 10173.36 | 2 | OFM |  | 5086.68 | 10173.36 | 10173.36
C |  | FCU-19B-03 | 2 | Nos. | OFM | OFM | 5086.68 | 10173.36 | 10173.36 | 2 | OFM |  | 5086.68 | 10173.36 | 10173.36
D |  | FCU-19B-04 | 2 | Nos. | OFM | OFM | 5086.68 | 10173.36 | 10173.36 | 2 | OFM |  | 5086.68 | 10173.36 | 10173.36
E |  | FCU-19B-05 | 1 | No. | OFM | OFM | 5086.68 | 5086.68 | 5086.68 | 1 | OFM |  | 5086.68 | 5086.68 | 5086.68
F |  | FCU-19B-06 | 1 | No. | OFM | OFM | 5086.68 | 5086.68 | 5086.68 | 1 | OFM |  | 5086.68 | 5086.68 | 5086.68
Supply, Installation & Commissioning of Valve Assembly for Fan Coil Units, complete in all respects with necessary fittings and as per schedule, drawings, schedule & specifications.
G |  | Automatic Air Vent | 9 | Nos. | 4239.28 | 38153.52 | 1672 | 15048 | 53201.52 | 9 | 4239.28 | 38153.52 | 1672 | 15048 | 53201.52
Gate Valve
H |  | 1" Ø | 27 | Nos. | 13680 | 369360 | 1672 | 45144 | 414504 | 27 | 13680 | 369360 | 1672 | 45144 | 414504
Flexible Connectors
I |  | 1" Ø | 18 | Nos. | 13680 | 246240 | 1672 | 30096 | 276336 | 18 | 13680 | 246240 | 1672 | 30096 | 276336
Strainer
J |  | 1" Ø | 9 | Nos. | 14440 | 129960 | 1672 | 15048 | 145008 | 9 | 14440 | 129960 | 1672 | 15048 | 145008
Double Regulating Valve
K |  | 1" Ø | 9 | Nos. | 21280 | 191520 | 1672 | 15048 | 206568 | 9 | 21280 | 191520 | 1672 | 15048 | 206568
|  | 2-Way Motorized Valve |  |  | 0 | 0 | 0 | 0 | 0
L |  | 1" Ø | 9 | Nos. | 45000 | 405000 | 2280 | 20520 | 425520 | 9 | 45000 | 405000 | 2280 | 20520 | 425520
| 23 34 00 | Supply, Installation & Commissioning of Exhaust Fans with wire mesh as per drawings, schedule & specifications.
M |  | EF-01 | 1 | No. | 105972.5 | 105972.5 | 21194.5 | 21194.5 | 127167 | 0 | 105972.5 | 0 | 21194.5 | 0 | 0
|  | Sub Total (Page 2) |  |  |  | 1486206.02 |  | 207878.62 | 1694084.64 |  |  | 1380233.52 |  | 186684.12 | 1566917.64
23 31 00
Ducting
A |  | 18 Gauge | 95 | Sq.ft | 351.88 | 33428.6 | 80.5391 | 7651.2145 | 41079.8145 | 48 | 351.88 | 16890.24 | 80.5391 | 3865.8768 | 20756.1168
B |  | 22 Gauge | 315 | Sq.ft | 436.24 | 137415.6 | 80.5391 | 25369.8165 | 162785.4165 | 714.56 | 436.24 | 311719.6544 | 80.5391 | 57550.0193 | 369269.6737
C |  | 24 Gauge | 3230 | Sq.ft | 478.8 | 1546524 | 80.5391 | 260141.293 | 1806665.293 | 2757.9 | 478.8 | 1320482.52 | 80.5391 | 222118.7839 | 1542601.3039
D | 23 07 00 | Supply, Installation & Commissioning of Closed cell elastromeric Insulation of thickness for G.I Ducts required as per drawings and specifications. | 3720 | Sq.ft | 500 | 1860000 | 60.8 | 226176 | 2086176 | 4539.91 | 500 | 2269955 | 60.8 | 276026.528 | 2545981.528
E |  | Supply, Installation & Commissioning of Coloured wrapping for G.I Ducts required as per drawings and specifications. | 1590 | Sq.ft | 76 | 120840 | 19 | 30210 | 151050 |  | 76 | 0 | 19 | 0 | 0
| 23 33 46 | Supply, installation and Commissioning of flexible ducts complete in all respects as per schedule, drawings and specifications.
A |  | 8" Diameter | 40 | Rft. | 678.224 | 27128.96 | 84.778 | 3391.12 | 30520.08 | 148 | 678.224 | 100377.152 | 84.778 | 12547.144 | 112924.296
Supply, installation and Commissioning of butterfly damper complete in all respects as per schedule, drawings and specifications.
B |  | 8" Diameter | 27 | Nos. | 3391.12 | 91560.24 | 836 | 22572 | 114132.24 | 43 | 3391.12 | 145818.16 | 836 | 35948 | 181766.16
|  | Sub Total (Page 3) |  |  |  | 3816897.4 |  | 575511.444 | 4392408.844 |  |  | 4165242.7264 |  | 608056.352 | 4773299.0784
| 23 21 13 | Supply, Installation & Commissioning of ASTM Schedule 40 chilled water seamless piping(Supply/Return) complete with fittings, flanges unions, gaskets, specialties, flexible connections, etc, including all cutting, fixing fitting, laying, cleaning and making good complete in all respects as per drawings and specifications.
A |  | Ø 1" | 100 | Rft. | 682.4629 | 68246.29 | 186.5116 | 18651.16 | 86897.45 | 407 | 682.4629 | 277762.4003 | 186.5116 | 75910.2212 | 353672.6215
B |  | Ø 1-1/4" | 110 | Rft. | 763.002 | 83930.22 | 254.334 | 27976.74 | 111906.96 | 24.5 | 763.002 | 18693.549 | 254.334 | 6231.183 | 24924.732
C |  | Ø 1-1/2" | 110 | Rft. | 890.169 | 97918.59 | 339.112 | 37302.32 | 135220.91 | 32 | 890.169 | 28485.408 | 339.112 | 10851.584 | 39336.992
D |  | Ø 2" | 330 | Rft. | 1186.892 | 391674.36 | 356.0676 | 117502.308 | 509176.668 | 444.1 | 1186.892 | 527098.7372 | 356.0676 | 158129.6212 | 685228.3584
Supply, Installation & Commissioning of Closed Cell NBR Insulation for chilled water piping with complete in all respect as mentioned in the drawings & specifications. 1" Thick insulation as mentioned in the specs
E |  | Ø 1" | 100 | Rft. | 254.334 | 25433.4 | 76.3002 | 7630.02 | 33063.42 | 407 | 254.334 | 103513.938 | 76.3002 | 31054.1814 | 134568.1194
F |  | Ø 1-1/4" | 110 | Rft. | 339.112 | 37302.32 | 76.3002 | 8393.022 | 45695.342 | 24.5 | 339.112 | 8308.244 | 76.3002 | 1869.3549 | 10177.5989
G |  | Ø 1-1/2" | 110 | Rft. | 415.4122 | 45695.342 | 76.3002 | 8393.022 | 54088.364 | 32 | 415.4122 | 13293.1904 | 76.3002 | 2441.6064 | 15734.7968
H |  | Ø 2" | 330 | Rft. | 508.668 | 167860.44 | 76.3002 | 25179.066 | 193039.506 | 444.1 | 508.668 | 225899.4588 | 76.3002 | 33884.9188 | 259784.3776
|  | Sub Total (Page 4) |  |  |  | 918060.962 |  | 251027.658 | 1169088.62 |  |  | 1203054.9257 |  | 320372.6709 | 1523427.5966
| 23 37 13 | Supply, Installation and Commissioning of Air Devices as per drawings, schedules and specifications.
Supply Air Liner Slot Diffuser
A |  | 3/1"/174" | 2 | Nos. | 19922.83 | 39845.66 | 1672 | 3344 | 43189.66 |  | 19922.83 | 0 | 1672 | 0 | 0
B |  | 3/1"/162" | 1 | No. | 18227.27 | 18227.27 | 1672 | 1672 | 19899.27 |  | 18227.27 | 0 | 1672 | 0 | 0
C |  | 3/1"/114" | 2 | Nos. | 13564.48 | 27128.96 | 1672 | 3344 | 30472.96 |  | 13564.48 | 0 | 1672 | 0 | 0
Return Air Liner Slot Diffuser
D |  | 3/1"/114" | 2 | Nos. | 13564.48 | 27128.96 | 1672 | 3344 | 30472.96 |  | 13564.48 | 0 | 1672 | 0 | 0
E |  | 3/1"/264" | 1 | No. | 26705.07 | 26705.07 | 1672 | 1672 | 28377.07 |  | 26705.07 | 0 | 1672 | 0 | 0
F |  | 3/1"/264" | 1 | No. | 26705.07 | 26705.07 | 1672 | 1672 | 28377.07 |  | 26705.07 | 0 | 1672 | 0 | 0
G |  | 3/1"/174" | 2 | Nos. | 19922.83 | 39845.66 | 1672 | 3344 | 43189.66 |  | 19922.83 | 0 | 1672 | 0 | 0
H |  | 3/1"/162" | 1 | No. | 18227.27 | 18227.27 | 1672 | 1672 | 19899.27 |  | 18227.27 | 0 | 1672 | 0 | 0
I |  | 3/1"/186" | 1 | No. | 20770.61 | 20770.61 | 1672 | 1672 | 22442.61 |  | 20770.61 | 0 | 1672 | 0 | 0
Supply Air Diffuser
J |  | 21x21 | 2 | Nos. | 8477.8 | 16955.6 | 836 | 1672 | 18627.6 |  | 8477.8 | 0 | 836 | 0 | 0
K |  | 12x12 | 2 | Nos. | 4238.9 | 8477.8 | 836 | 1672 | 10149.8 |  | 4238.9 | 0 | 836 | 0 | 0
L |  | 21x21 | 2 | Nos. | 8477.8 | 16955.6 | 836 | 1672 | 18627.6 |  | 8477.8 | 0 | 836 | 0 | 0
M |  | 18x18 | 2 | Nos. | 7206.13 | 14412.26 | 836 | 1672 | 16084.26 |  | 7206.13 | 0 | 836 | 0 | 0
N |  | 12x12 | 2 | Nos. | 4238.9 | 8477.8 | 836 | 1672 | 10149.8 |  | 4238.9 | 0 | 836 | 0 | 0
O |  | 12x12 | 1 | No. | 4238.9 | 4238.9 | 836 | 836 | 5074.9 |  | 4238.9 | 0 | 836 | 0 | 0
|  | Sub Total (Page 5) |  |  |  | 314102.49 |  | 30932 | 345034.49 |  |  | 0 |  | 0 | 0
Return Air Diffuser
A |  | 12x12 | 2 | Nos. | 3815.01 | 7630.02 | 836 | 1672 | 9302.02 |  | 3815.01 | 0 | 836 | 0 | 0
Return Air Register
B |  | 28x6 | 2 | Nos. | 4238.9 | 8477.8 | 836 | 1672 | 10149.8 |  | 4238.9 | 0 | 836 | 0 | 0
C |  | 28x8 | 1 | No. | 5086.68 | 5086.68 | 836 | 836 | 5922.68 |  | 5086.68 | 0 | 836 | 0 | 0
D |  | 12x12 | 5 | Nos. | 3391.12 | 16955.6 | 836 | 4180 | 21135.6 |  | 3391.12 | 0 | 836 | 0 | 0
E |  | 16x12 | 6 | Nos. | 4238.9 | 25433.4 | 836 | 5016 | 30449.4 |  | 4238.9 | 0 | 836 | 0 | 0
F |  | 12x10 | 1 | No. | 3391.12 | 3391.12 | 836 | 836 | 4227.12 |  | 3391.12 | 0 | 836 | 0 | 0
Supply Air Register
G |  | 16x12 | 6 | Nos. | 4238.9 | 25433.4 | 836 | 5016 | 30449.4 |  | 4238.9 | 0 | 836 | 0 | 0
H |  | 12x12 | 5 | Nos. | 4238.9 | 21194.5 | 836 | 4180 | 25374.5 |  | 4238.9 | 0 | 836 | 0 | 0
I |  | 28x6 | 2 | Nos. | 5086.68 | 10173.36 | 836 | 1672 | 11845.36 |  | 5086.68 | 0 | 836 | 0 | 0
J |  | 12x12 | 5 | Nos. | 4238.9 | 21194.5 | 836 | 4180 | 25374.5 |  | 4238.9 | 0 | 836 | 0 | 0
Volume Control Damper (VCD)
K |  | 14" x 6" | 2 | Nos. | 3391.12 | 6782.24 | 836 | 1672 | 8454.24 |  | 3391.12 | 0 | 836 | 0 | 0
L |  | 18" x 6" | 2 | Nos. | 4662.79 | 9325.58 | 836 | 1672 | 10997.58 |  | 4662.79 | 0 | 836 | 0 | 0
M |  | 14" x 8" | 2 | Nos. | 3815.01 | 7630.02 | 836 | 1672 | 9302.02 |  | 3815.01 | 0 | 836 | 0 | 0
|  | Sub Total (Page 6) |  |  |  | 168708.22 |  | 34276 | 202984.22 |  |  | 0 |  | 0 | 0
| 23 33 05 | Supply, Installation and Commissioning of Motorised Fire and Smoke Damper for ducts as per SMACNA standards as mentioned in the specifications and drawings.
A |  | 14"x10" | 2 | Nos. | 93255.8 | 186511.6 | 5934.46 | 11868.92 | 198380.52 |  | 93255.8 | 0 | 5934.46 | 0 | 0
B |  | 28"x6" | 2 | Nos. | 114450.3 | 228900.6 | 5934.46 | 11868.92 | 240769.52 |  | 114450.3 | 0 | 5934.46 | 0 | 0
| 23 33 05 | Installation, Testing & Commissioning of VAVs complete in all respect as per drawing and specification and schedule.
VAVs
C |  | VAV-19BF-01 | 1 | Nos. | OFM | OFM | 7980 | 7980 | 7980 | 1 | OFM |  | 7980 | 7980 | 7980
D |  | VAV-19BF-02 | 1 | Nos. | OFM | OFM | 7980 | 7980 | 7980 | 1 | OFM |  | 7980 | 7980 | 7980
E |  | VAV-19BF-03 | 1 | Nos. | OFM | OFM | 7980 | 7980 | 7980 | 1 | OFM |  | 7980 | 7980 | 7980
F |  | VAV-19BF-04 | 1 | Nos. | OFM | OFM | 7980 | 7980 | 7980 | 1 | OFM |  | 7980 | 7980 | 7980
G |  | VAV-19BF-05 | 1 | Nos. | OFM | OFM | 7980 | 7980 | 7980 | 1 | OFM |  | 7980 | 7980 | 7980
H |  | VAV-19BF-06 | 1 | Nos. | OFM | OFM | 7980 | 7980 | 7980 | 1 | OFM |  | 7980 | 7980 | 7980
Supply, Installation and Commissioning of U-PVC piping with insulation for condensate drain piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications.
I |  | 3/4" Diameter | 100 | Rft. | 508.668 | 50866.8 | 59.3446 | 5934.46 | 56801.26 |  | 508.668 | 0 | 59.3446 | 0 | 0
J |  | 1" Diameter | 125 | Rft. | 678.224 | 84778 | 101.7336 | 12716.7 | 97494.7 | 200 | 678.224 | 135644.8 | 101.7336 | 20346.72 | 155991.52
Supply, Installation and Commissioning of MS Schedule 40 piping with insulation for supply and return condensor Water piping including all cutting fixing, layout, cleaning and making good complete in all respect as per drawings and specifications.
K |  | 3/4" Diameter | 150 | Rft. | 508.668 | 76300.2 | 101.7336 | 15260.04 | 91560.24 | 80 | 508.668 | 40693.44 | 101.7336 | 8138.688 | 48832.128
|  | Sub Total (Page 7) |  |  |  | 627357.2 |  | 105529.04 | 732886.24 |  | 0 | 176338.24 |  | 76365.408 | 252703.648
A |  | Sound Trap with duct Z-piece and sound lining for return lot air intake | 1 | Lot | 254334 | 254334 | 60800 | 60800 | 315134 | 1 | 254334 | 254334 | 60800 | 60800 | 315134
B |  | Engineering & Programming commissioning testing all above VAVs including Controller and thermostat. | 1 | Lot | 0 | 0 | 140600 | 140600 | 140600 |  | 0 | 0 | 140600 | 0 | 0
MISCELLANEOUS
C | 01 46 00 | Supply, Installation & Commissioning of brass tags for Equipment and system including all accessories complete in all respect. | 1 | Job | 21194.5 | 21194.5 | 4238.9 | 4238.9 | 25433.4 |  | 21194.5 | 0 | 4238.9 | 0 | 0
D | 23 05 48 | Supply, Installation & Commissioning of hangers and supports for pipes and equipment including all noise and Vibration controller roller type and others as per drawings and specifications. | 1 | Job | 296723 | 296723 | 63583.5 | 63583.5 | 360306.5 | 1 | 296723 | 296723 | 63583.5 | 63583.5 | 360306.5
E | 09 90 00 | Painting on equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 29672.3 | 29672.3 | 12716.7 | 12716.7 | 42389 | 1 | 29672.3 | 29672.3 | 12716.7 | 12716.7 | 42389
F | 23 05 93 23 08 00 | Testing, adjusting, Balancing & Commissioning of HVAC system omplete in all respect. | 1 | Job | 0 | 0 | 144122.6 | 144122.6 | 144122.6 | 0.5 | 0 | 0 | 144122.6 | 72061.3 | 72061.3
G | 07 84 00 | Supply, Installation and commision of fire stopping materials as per specifications and drawings complete in all respect. | 1 | Job | 63583.5 | 63583.5 | 12716.7 | 12716.7 | 76300.2 | 1 | 63583.5 | 63583.5 | 12716.7 | 12716.7 | 76300.2
|  | Drawings |  |  | 0 | 0 | 0 | 0 | 0
H | 01 00 00 23 05 01 | Shop Drawings and As Built Drawings as per specifications. | 1 | Job | 8477.8 | 8477.8 | 8477.8 | 8477.8 | 16955.6 | 0.75 | 8477.8 | 6358.35 | 8477.8 | 6358.35 | 12716.7
Sundries
I | 01 00 00 23 05 01 | Supply, installing and Commissioning of items not listed in BOQ but required. | 1 | Job | 0 | 0 | 0 | 0 | 0
|  | Sub Total (Page 7) |  |  |  | 673985.1 |  | 447256.2 | 1121241.3 |  |  | 650671.15 |  | 228236.55 | 878907.7
|  | GRAND TOTAL FOR HVAC WORKS (LEVEL-19B) |  |  |  | 8166819.482 |  | 1695341.462 | 9862160.944 |  |  | 7737042.6521 |  | 1462645.6009 | 9199688.253

## 19A-FIRE
SECTION III/C/III: BILL OF QUANTITIES FOR FIRE FIGHTING WORKS (LEVEL-19A)
|  |  | BOQ | [6 empty] | FIRST RUNNING BILL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost | Qty | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7 | 11 | 12 | 12 x 11 | 14 | 14 x 11 | 13 + 15
Fire Fighting 19th A
| 21 11 00 | Supply, install and commission of Mild Steel Schedule 40 pipe including all special fittings and Hangers including the cost of breaking through wall and roof complete in all respects shown on drawings & specifications.
|  | 4" Diameter | 100 | Rft. | 3793.16 | 379316 | 518.32 | 51832 | 431148 | 4.5 | 3793.16 | 17069.22 | 518.32 | 2332.44 | 19401.66
A |  | 3" Diameter | 147.2 | Rft. | 3015.68 | 443908.096 | 471.2 | 69360.64 | 513268.736 | 187.5 | 3015.68 | 565440 | 471.2 | 88350 | 653790
B |  | 2.5" Diameter | 64.4 | Rft. | 2073.28 | 133519.232 | 433.2 | 27898.08 | 161417.312 | 73.1 | 2073.28 | 151556.768 | 433.2 | 31666.92 | 183223.688
C |  | 2" Diameter | 80.5 | Rft. | 1319.36 | 106208.48 | 395.96 | 31874.78 | 138083.26 | 127.5 | 1319.36 | 168218.4 | 395.96 | 50484.9 | 218703.3
D |  | 1.5" Diameter | 151.8 | Rft. | 989.52 | 150209.136 | 376.96 | 57222.528 | 207431.664 | 179.3 | 989.52 | 177420.936 | 376.96 | 67588.928 | 245009.864
E |  | 1.25" Diameter | 172.5 | Rft. | 848.16 | 146307.6 | 282.72 | 48769.2 | 195076.8 | 166.8 | 848.16 | 141473.088 | 282.72 | 47157.696 | 188630.784
F |  | 1" Diameter | 520 | Rft. | 758.48 | 394409.6 | 207.48 | 107889.6 | 502299.2 | 611.5 | 758.48 | 463810.52 | 207.48 | 126874.02 | 590684.54
| 21 11 00 | Supply, install and commissioning of Sprinklers including all accessories complete in all respects as per drawings & specifications.
G |  | Concealed Pendent Sprinkler with Paint Finish (Quick Response) | 94 | Nos. | 9000 | 846000 | 659.68 | 62009.92 | 908009.92 | 99 | 9000 | 891000 | 659.68 | 65308.32 | 956308.32
|  | Corrugated Stainless Steel Flexible Connector 1inch x 3ft (ULFM) | 94 | Nos. | 12160 | 1143040 | 1140 | 107160 | 1250200 | 99 | 12160 | 1203840 | 1140 | 112860 | 1316700
| 21 20 00 | Supply, install and commission Fire Extinguisher as per drawing & specification.
H |  | Fire Blanket | 1 | No. | 30156.8 | 30156.8 | 942.4 | 942.4 | 31099.2 |  | 30156.8 | 0 | 942.4 | 0 | 0
I |  | CO2 Extinguisher Capacity | 0 | No. | 30156.8 | 0 | 942.4 | 0 | 0 |  | 30156.8 | 0 | 942.4 | 0 | 0
J |  | Dry Powder Extinguisher Capacity | 0 | No. | 25444.8 | 0 | 942.4 | 0 | 0 |  | 25444.8 | 0 | 942.4 | 0 | 0
| 21 20 00 | Supply, installation, testing & commissioning of FM200 fire supression system with all valves and accessories,control panels,control switches etc:- complete as per drawings & specifications.
K |  | I.T Rooms ( Volume=720 ft3) | 0 | No. | 1649200 | 0 | 155496 | 0 | 0 |  | 1649200 | 0 | 155496 | 0 | 0
|  | Sub Total (Page 1) |  |  |  | 3773074.944 |  | 564959.148 | 4338034.092 |  |  | 3779828.932 |  | 592623.224 | 4372452.156
Miscellaneous
A | 01 46 00 | Supply, Installation & Commissioning of brass tags of 2" dia tags for valves and fixed with chains complete as per drawings & specifications. | 1 | Job | 23560 | 23560 | 1884.8 | 1884.8 | 25444.8 |  | 23560 | 0 | 1884.8 | 0 | 0
B | 21 11 00 | Supply, Installation & Commissioning of hangers and supports for pipes and Equipments including roller type (if required) as per drawings & specifications. | 1 | Job | 282720 | 282720 | 32984 | 32984 | 315704 | 1 | 282720 | 282720 | 32984 | 32984 | 315704
C | 07 84 00 | Supply, installation and commision fire stopping aid as per specifications and drawings complete in all respect. | 1 | Job | 47120 | 47120 | 6596.8 | 6596.8 | 53716.8 | 1 | 47120 | 47120 | 6596.8 | 6596.8 | 53716.8
D | 22 11 00 | Painting of equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 65968 | 65968 | 14136 | 14136 | 80104 | 1 | 65968 | 65968 | 14136 | 14136 | 80104
E | 21 05 05 | Testing, adjusting, Balancing & commissioning of Fire Fighting System. | 1 | Job | 32984 | 32984 | 6596.8 | 6596.8 | 39580.8 |  | 32984 | 0 | 6596.8 | 0 | 0
Drawings
F | 21 05 01 | Shop drawings and As Built Drawings as per specifications. | 1 | Job | 9424 | 9424 | 9424 | 9424 | 18848 | 0.75 | 9424 | 7068 | 9424 | 7068 | 14136
Sundries
G |  | Supply, installing and commissioning of items not listed in BOQ but required.(Contractors to provide list) | 1 | Job | 0 | 0 | 0 | 0 | 0
|  | Sub Total (Page 2) |  |  |  | 461776 |  | 71622.4 | 533398.4 |  |  | 402876 |  | 60784.8 | 463660.8
|  | GRAND TOTAL FOR FIRE FIGHTING WORKS (LEVEL-19A) |  |  |  | 4234850.944 |  | 636581.548 | 4871432.492 |  |  | 4182704.932 |  | 653408.024 | 4836112.956

## 19B-FIRE
SECTION III/C/IV: BILL OF QUANTITIES FOR FIRE FIGHTING WORKS (LEVEL-19B)
[5 empty] | BOQ |  |  |  |  | FIRST RUNNING BILL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
BOQ No. | Specification Reference | Description | Qty | Unit | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost | Qty | Material Unit Rate | Material Cost | Installation Unit Rate | Installation Cost | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 6 x 4 | 8 | 8 x 4 | 9 + 7 | 11 | 12 | 12 x 11 | 14 | 14 x 11 | 13 + 15
Fire Fighting 19B
| 21 11 00 | Supply, install and commission of Mild Steel Schedule 40 pipe including all special fittings and Hangers including the cost of breaking through wall and roof complete in all respects shown on drawings & specifications.
A |  | 4" Diameter | 86.25 | Rft. | 3793.16 | 327160.05 | 518.32 | 44705.1 | 371865.15 | 148 | 3793.16 | 561387.68 | 518.32 | 76711.36 | 638099.04
B |  | 3" Diameter | 196.65 | Rft. | 3015.68 | 593033.472 | 471.2 | 92661.48 | 685694.952 | 108 | 3015.68 | 325693.44 | 471.2 | 50889.6 | 376583.04
C |  | 2.5" Diameter | 55.2 | Rft. | 2073.28 | 114445.056 | 433.2 | 23912.64 | 138357.696 | 67 | 2073.28 | 138909.76 | 433.2 | 29024.4 | 167934.16
D |  | 2" Diameter | 23 | Rft. | 1319.36 | 30345.28 | 395.96 | 9107.08 | 39452.36 | 40 | 1319.36 | 52774.4 | 395.96 | 15838.4 | 68612.8
E |  | 1.5" Diameter | 74.75 | Rft. | 989.52 | 73966.62 | 376.96 | 28177.76 | 102144.38 | 59 | 989.52 | 58381.68 | 376.96 | 22240.64 | 80622.32
F |  | 1.25" Diameter | 52.9 | Rft. | 848.16 | 44867.664 | 282.72 | 14955.888 | 59823.552 | 79 | 848.16 | 67004.64 | 282.72 | 22334.88 | 89339.52
G |  | 1" Diameter | 449 | Rft. | 758.48 | 340557.52 | 207.48 | 93158.52 | 433716.04 | 743 | 758.48 | 563550.64 | 207.48 | 154157.64 | 717708.28
| 21 11 00 | Supply, install and commissioning of Sprinklers including all accessories complete in all respects as per drawings & specifications.
H |  | Concealed Pendent Sprinkler with Paint Finish (Quick Response) | 73 | Nos. | 9000 | 657000 | 659.68 | 48156.64 | 705156.64 | 92 | 9000 | 828000 | 659.68 | 60690.56 | 888690.56
I |  | Extended Coverage Horizontal Side- wall Chrome Sprinklers | 34 | Nos. | 8010.4 | 272353.6 | 659.68 | 22429.12 | 294782.72 | 29 | 8010.4 | 232301.6 | 659.68 | 19130.72 | 251432.32
J |  | Upright Sprinkler Head Quick Response | 5 | Nos. | 4240.8 | 21204 | 659.68 | 3298.4 | 24502.4
|  | Corrugated Stainless Steel Flexible Connector 1inch x 3ft (ULFM) | 73 | Nos. | 12160 | 887680 | 1140 | 83220 | 970900 | 73 | 12160 | 887680 | 1140 | 83220 | 970900
| 21 20 00 | Supply, install and commission Fire Extinguisher as per drawing & specification.
K |  | CO2 Extinguisher Capacity | 2 | Nos. | 30156.8 | 60313.6 | 942.4 | 1884.8 | 62198.4 |  | 30156.8 | 0 | 942.4 | 0 | 0
L |  | Dry Powder Extinguisher Capacity | 2 | Nos. | 25444.8 | 50889.6 | 942.4 | 1884.8 | 52774.4 |  | 25444.8 | 0 | 942.4 | 0 | 0
| 21 20 00 | Supply, installation, testing & commissioning of FM200 fire supression system with all valves and accessories,control panels,control switches etc:- complete as per drawings & specifications.
M |  | I.T Rooms ( Volume=720 ft3) | 1 | No. | 1649200 | 1649200 | 155496 | 155496 | 1804696 |  | 1649200 | 0 | 155496 | 0 | 0
|  | Sub Total (Page 1) |  |  |  | 5123016.462 |  | 623048.228 | 5746064.69 |  |  | 3715683.84 |  | 534238.2 | 4249922.04
Miscellaneous
A | 01 46 00 | Supply, Installation & Commissioning of brass tags of 2" dia tags for valves and fixed with chains complete as per drawings & specifications. | 1 | Job | 23560 | 23560 | 1884.8 | 1884.8 | 25444.8
B | 21 11 00 | Supply, Installation & Commissioning of hangers and supports for pipes and Equipments including roller type (if required) as per drawings & specifications. | 1 | Job | 282720 | 282720 | 32984 | 32984 | 315704 | 1 | 282720 | 282720 | 32984 | 32984 | 315704
C | 07 84 00 | Supply, installation and commision fire stopping aid as per specifications and drawings complete in all respect. | 1 | Job | 47120 | 47120 | 6596.8 | 6596.8 | 53716.8 | 0.5 | 47120 | 23560 | 6596.8 | 3298.4 | 26858.4
D | 22 11 00 | Painting of equipment / Hangers, Supports, Pipe etc as per specifications. | 1 | Job | 65968 | 65968 | 14136 | 14136 | 80104 | 1 | 65968 | 65968 | 14136 | 14136 | 80104
E | 21 05 05 | Testing, adjusting, Balancing & commissioning of Fire Fighting System. | 1 | Job | 32984 | 32984 | 6596.8 | 6596.8 | 39580.8
Drawings
F | 21 05 01 | Shop drawings and As Built Drawings as per specifications. | 1 | Job | 9424 | 9424 | 9424 | 9424 | 18848 | 0.75 | 9424 | 7068 | 9424 | 7068 | 14136
Sundries
G |  | Supply, installing and commissioning of items not listed in BOQ but required.(Contractors to provide list) | 1 | Job | 0 | 0 | 0 | 0 | 0
|  | Sub Total (Page 2) |  |  |  | 461776 |  | 71622.4 | 533398.4 |  |  | 379316 |  | 57486.4 | 436802.4
|  | GRAND TOTAL FOR FIRE FIGHTING WORKS (LEVEL-19B) |  |  |  | 5584792.462 |  | 694670.628 | 6279463.09 |  |  | 4094999.84 |  | 591724.6 | 4686724.44