## SUMM
DOLMEN CITY FAMILY AREA, SECOND FLOOR
RUNNING BILL NO 1
S.NO | SUMMARY OF COST | Material | Labour | AMOUNT
1 | HVAC |  |  | 3084597
2 | Fire Fighting |  |  | 844505
3 | Plumbing |  |  | 649226
4 | Variations (07 Nos) |  |  | 1365810.935
| Total Amount |  |  | 4578328

## HVAC
DOLMEN CITY FAMILY AREA, SECOND FLOOR | [9 empty] | BILL OF QUANTITIES
HVAC WORKS | [9 empty] | DATED: APRIL 12, 2023
ITEM NO. | DESCRIPTION | BILL OF QUANTITIES |  |  |  | RUNNING BILL NO 1
|  | Qty | UNIT | MATERIAL RATE | LABOUR RATE | Material |  | Labour |  | Total Amount
[6 empty] | Billed Qty | Amount | Billed Qty | Amount
1 | HYDRONIC PIPING & SPECIALITIES (SECTION 23 21 13 & DS/1637-23 21 13)
1.1 | Drain Piping uPVC Pressure Pipe (IP/1) (Section 23 21 13 & DS/1637-23 21 13)
1.1.1 | Ø 1" (Ø 25mm) | 12 | Rm | 765 | 150 | 15 | 11475 | 15 | 2250 | 13725
1.1.2 | Pipe Sleeves | 1 | Lot | 4000 | 1000 | 1 | 4000 | 1 | 1000 | 5000
1.1.3 | Pipe Supports (Section 23 05 29) | 1 | Lot | 18000 | 2000 | 1 | 18000 | 1 | 2000 | 20000
Sub-total Carried to Summary | [9 empty] | 38725
2 | DUCT WORK (MACHINE MADE) (SECTION 23 31 13)
2.1 | Sheet Metal Duct Work (Air Conditioning) (Supply Air), Machine made Ducts (Section 23 31 13) | 74 | m2 | 4900 | 900 | 121 | 592900 | 121 | 108900 | 701800
2.2 | Sheet Metal Duct Work (Air Conditioning) (Return Air), Machine made Ducts (Section 23 31 13) | 5.6 | m2 | 4900 | 900 | 16 | 78400 | 16 | 14400 | 92800
2.3 | Sheet Metal Duct Work (Exhaust Air) Machine made Ducts (Section 23 31 13) | 12.1 | m2 | 4900 | 900 | 24 | 117600 | 24 | 21600 | 139200
2.4 | Inspection and Insulation Replacement of Existing AHU C2-12 Supply Duct | 1 | Lot | 72000 | 12000 | 1 | 72000 | 1 | 12000 | 84000
2.5 | Volume Control Damper | 1 | Lot | 48500 | 7000 | 1 | 48500 | 1 | 7000 | 55500
2.6 | Duct Test Holes | 1 | Lot
2.7 | Duct Supports (Hot Dipped Galvanized up to 50 to 70 Micron) System | 1 | Lot | 45000 | 15000 | 1 | 45000 | 1 | 15000 | 60000
2.8 | G.I Frame as Duct Sleeves | 1 | Lot | 11000 | 2000 | 1 | 11000 | 1 | 2000 | 13000
Sub-total Carried to Summary | [9 empty] | 1146300
3 | SOUND LINERS ON SUPPLY AND RETURN AIR DUCTS (SECTION 23 33 19)
3.1 | Supply Air Duct (32"x18") | 2.5 | Rm | 7500 | 1000 | 7.14 | 53550 | 7.14 | 7140 | 60690
3.2 | Return Air Duct (14"x12") | 2.05 | Rm | 5190 | 1000 | 12.8 | 66432 | 12.8 | 12800 | 79232
Sub-total Carried to Summary | [9 empty] | 139922
4 | THERMAL INSULATION (SECTION 23 07 13 & 23 07 19)
4.1 | Sheet Metal Duct Work (Air-Conditioning) (Supply Air, Return Air & Fresh Air) | 79.6 | m2 | 6750 | 700 | 137 | 924750 | 137 | 95900 | 1020650
4.2 | Sheet Metal Duct Work (Exhaust Air) | 12.1 | m2 | 5900 | 600 | 24 | 141600 | 24 | 14400 | 156000
Sub-total Carried to Summary | [9 empty] | 1176650
5 | AIR DEVICES (SECTION 23 37 13)
5.1 | Supply & Installation of Tuttle & Bailey Supply Air Linear Slot Diffuser (Series 6000)
5.1.1 | Air Terminal Number (ST-01) | 1 | No. | 3200 | 1000 | 1 | 3200 | 1 | 1000 | 4200
5.1.2 | Air Terminal Number (ST-02) | 1 | No. | 3200 | 1000 | 1 | 3200 | 1 | 1000 | 4200
5.1.3 | Air Terminal Number (ST-03) | 1 | No. | 4700 | 1000 | 1 | 4700 | 1 | 1000 | 5700
5.1.4 | Air Terminal Number (ST-04) | 1 | No. | 5880 | 1000 | 1 | 5880 | 1 | 1000 | 6880
5.1.5 | Air Terminal Number (ST-05) | 1 | No. | 3300 | 1000 | 1 | 3300 | 1 | 1000 | 4300
5.1.6 | Air Terminal Number (ST-06) | 3 | Nos. | 5880 | 1000 | 3 | 17640 | 3 | 3000 | 20640
5.1.7 | Air Terminal Number (ST-07) | 1 | No. | 7050 | 1000 | 2 | 14100 | 2 | 2000 | 16100
5.2 | Supply & Installation of Round Diffuser (Tuttle & Bailey)
5.2.1 | Air Terminal Number (ST-08) | 1 | No. | 4560 | 1000 | 1 | 4560 | 1 | 1000 | 5560
5.2.2 | Air Terminal Number (ST-09) | 4 | Nos. | 4560 | 1000 | 4 | 18240 | 4 | 4000 | 22240
5.2.3 | Air Terminal Number (RT-10) | 3 | Nos. | 4560 | 1000 | 3 | 13680 | 3 | 3000 | 16680
5.3 | Supply & Installation of Tuttle & Bailey Return Air Linear Slot Diffuser (Series 6000)
5.3.1 | Air Terminal Number (RT-01) | 1 | No. | 14900 | 1000 |  | 0 | 0 | 0 | 0
5.3.2 | Air Terminal Number (RT-02) | 1 | No. | 8700 | 1000 |  | 0 | 0 | 0 | 0
5.3.3 | Air Terminal Number (RT-03) | 3 | Nos. | 5320 | 1000 |  | 0 | 0 | 0 | 0
5.3.4 | Air Terminal Number (RT-04) | 1 | No. | 3200 | 1000 |  | 0 | 0 | 0 | 0
5.3.5 | Air Terminal Number (RT-05) | 1 | No. | 3200 | 1000 |  | 0 | 0 | 0 | 0
5.3.6 | Air Terminal Number (RT-06) | 1 | No. | 4700 | 1000 |  | 0 | 0 | 0 | 0
5.3.7 | Air Terminal Number (RT-07) | 1 | No. | 5850 | 1000 |  | 0 | 0 | 0 | 0
5.3.8 | Air Terminal Number (RT-08) | 1 | No. | 3200 | 1000 |  | 0 | 0 | 0 | 0
5.4 | Supply & Installation of R.A.G A70
5.4.1 | Air Terminal Number (ET-01) | 7 | Nos. | 1200 | 500 | 5 | 6000 | 5 | 2500 | 8500
Sub-total Carried to Summary | [9 empty] | 115000
6 | FANS (SECTION 23 34 13 & DS/1283E-23 34 13)
6.1 | Supply & Installation of Tube Axial Exhaust Fan (FN/01) | 1 | No. | 215000 | 8000 | 1 | 215000 | 1 | 8000 | 223000
6.2 | Commissioning & Testing | 1 | Lot | 0 | 90000 | 1 | 0 | 1 | 90000 | 90000
Sub-total Carried to Summary | [9 empty] | 313000
7 | AIR HANDLING UNITS (REFER SECTION 23 73 10 & DS/1283E-23 73 10) (OWNER FURNISHED)
7.1 | Installation of Owner Furnished Air Handling Unit (AHU-00248) | 1 | No. | 0 | 35000 | 1 | 0 | 1 | 35000 | 35000
7.2 | Spare parts for AHU-00248 (Refer Data Sheet) | 1 | Lot | 0 | 0 |  | 0 | 0 | 0 | 0
7.3 | Foundation/Supports (By Civil Contractor) | 1 | Lot | 0 | 0 |  | 0 | 0 | 0 | 0
7.4 | Commissioning & Testing | 1 | Lot | 0 | 15000 | 1 | 0 | 1 | 15000 | 15000
Sub-total Carried to Summary | [9 empty] | 50000
8 | TEST RUN (SECTION 23 05 94)
8.1 | One Month Test Run of the System | 1 | Lot | 0 | 60000 |  | 0 | 0 | 0 | 0
Sub-total Carried to Summary | [9 empty] | 0
9 | CLEANING, BALANCING & TESTING (SECTION 23 05 93)
9.1 | Cleaning & Adjusting | 1 | Lot | 0 | 15000 | 1 | 0 | 1 | 15000 | 15000
9.2 | Balancing | 1 | Lot | 0 | 60000 |  | 0 | 0 | 0 | 0
9.3 | Testing & Commissioning | 1 | Lot | 0 | 15000 | 1 | 0 | 1 | 15000 | 15000
Sub-total Carried to Summary | [9 empty] | 30000
10 | PAINTING & FINISHING AND MECHANICAL IDENTIFICATION (SECTION 23 05 50 & 23 05 53)
10.1 | Painting & Finishing (Section 23 05 50) | 1 | Lot | 0 | 30000 | 1 | 0 | 1 | 30000 | 30000
10.2 | Equipment Data Plates (Section 23 05 53) | 1 | Lot | 0 | 15000 |  | 0 | 0 | 0 | 0
Sub-total Carried to Summary | [9 empty] | 30000
11 | MISCELLANEOUS
11.1 | Shop Drawings | 1 | Lot | 0 | 15000 | 1 | 0 | 1 | 15000 | 15000
11.2 | As Built Drawings | 1 | Lot | 0 | 10000 |  | 0 | 0 | 0 | 0
11.3 | Structural Opening & Core Cuts | 1 | Lot | 0 | 30000 | 1 | 0 | 1 | 30000 | 30000
11.4 | Wall Openings | 1 | Lot | 0 | 20000 |  | 0 | 0 | 0 | 0
Sub-total Carried to Summary | [9 empty] | 45000
Grand Total Amount Rs | [9 empty] | 3084597

## Fire
DOLMEN CITY FAMILY AREA, SECOND FLOOR | [9 empty] | BILL OF QUANTITIES
FIRE SUPPRESSION SYSTEM WORKS | [9 empty] | DATED: APRIL 12, 2023
BILL OF QUANTITIES
ITEM NO. | DESCRIPTION | BILL OF QUANTITIES |  |  |  | RUNNING BILL NO 1
|  | Qty | UNIT | MATERIAL RATE | LABOUR RATE | Material |  | Labour |  | Total Amount
[6 empty] | Billed Qty | Amount | Billed Qty | Amount
1 | FIRE SPRINKLERS (SECTION 21 13 10 & DS/1283E-21 13 10)
1.1 | Fire Sprinkler-Concealed Pendent, Standard Response (SP-01)- NEW | 5 | Nos. | 9000 | 1000 | 9 | 81000 | 9 | 9000 | 90000
1.2 | Dismantling and relocation of Existing Fire Sprinkler-Concealed Pendent, Standard Response (SP-01)- Complete in all Respect | 1 | Lot | 0 | 35000 | 1 | 0 | 1 | 35000 | 35000
1.3 | Cabinet complete with 06 Spare Sprinklers (Pendent ESFR Sprinkler) (SP-01) | - | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-total Carried to Summary | [9 empty] | 125000
2 | CORRUGATED STAINLESS STEEL FLEXIBLE CONNECTOR
2.1 | Corrugated Stainless Steel Flexible Connector Ø 1" X 3 ft (UL/FM) - NEW | 5 | Nos. | 11000 | 1000 | 9 | 99000 | 9 | 9000 | 108000
Sub-total Carried to Summary | [9 empty] | 108000
3 | PORTABLE FIRE EXTINGUISHER FOR FIRE TYPES A, B, C & AFFF (SECTION 21 21 10 & DS/1283E-21 21 10)
3.1 | Supply & Installation of 6kg Dry Powder Extinguisher (ABC) | 1 | No. | 17000 | 500 | 0 | 0 | 0 | 0 | 0
Sub-total Carried to Summary | [9 empty] | 0
4 | BLACK STEEL SCHEDULE-40 PIPING (SECTION 21 10 10)
4.1 | Welded Piping System
4.1.1 | Ø 250 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
4.1.2 | Ø 200 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
4.1.3 | Ø 150 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
4.1.4 | Ø 100 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
4.1.5 | Ø 75 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
4.1.6 | Ø 65 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
4.2 | Threaded Piping System
4.2.1 | Ø 50 mm | - | Rm | 6800 | 1200 |  | 0 | 0 | 0 | 0
4.2.2 | Ø 40 mm | 4 | Rm | 5750 | 1000 | 7.1 | 40825 | 7.1 | 7100 | 47925
4.2.3 | Ø 32 mm | 7 | Rm | 4800 | 900 | 7.2 | 34560 | 7.2 | 6480 | 41040
4.2.4 | Ø 25 mm | 44 | Rm | 3250 | 800 | 61 | 198250 | 61 | 48800 | 247050
Sub-total Carried to Summary | [9 empty] | 336015
5 | SIESMIC BRACING
5.1 | Transverse Seismic Bracing (As per FND Detail No. FND/SS/10)
5.1.1 | Ø 200 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.1.2 | Ø 150 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.1.3 | Ø 100 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.1.4 | Ø 75 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.1.5 | Ø 65 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.2 | Longitudinal Seismic Bracing (As per FND Detail No. FND/SS/11)
5.2.1 | Ø 200 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.2.2 | Ø 150 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.2.3 | Ø 100 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.2.4 | Ø 75 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.2.5 | Ø 65 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.3 | Four Way Seismic Bracing (As per FND Detail No. FND/ADD/10)
5.3.1 | Ø 200 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.3.2 | Ø 150 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.3.3 | Ø 100 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.3.4 | Ø 75 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.3.5 | Ø 65 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.4 | Seismic Restraint (As per FND Detail No. FND/ADD/08)
5.4.1 | Ø 50 mm | - | No. | 0 | 0 |  | 0 | 0 | 0 | 0
5.4.2 | Ø 40 mm | 1 | No. | 6500 | 1000 | 1 | 6500 | 1 | 1000 | 7500
5.4.3 | Ø 32 mm | 1 | No. | 6000 | 1000 | 1 | 6000 | 1 | 1000 | 7000
5.4.4 | Ø 25 mm | 12 | Nos. | 5500 | 1000 | 12 | 66000 | 12 | 12000 | 78000
Sub-total Carried to Summary | [9 empty] | 92500
6 | FIRE SPRINKLER SYSTEM ACCEPTANCE TEST (SECTION 21 13 17)
6.1 | Fire Sprinkler System Acceptance Test | 1 | Lot | 0 | 15000 | 1 | 0 | 1 | 15000 | 15000
Sub-total Carried to Summary | [9 empty] | 15000
7 | PAINTING COATING & STENCILING (SECTION 21 05 50)
7.1 | Painting, Coating
7.1.1 | Ø 250 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
7.1.2 | Ø 200 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
7.1.3 | Ø 150 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
7.1.4 | Ø 100 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
7.1.5 | Ø 75 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
7.1.6 | Ø 65 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
7.1.7 | Ø 50 mm | - | Rm | 0 | 0 |  | 0 | 0 | 0 | 0
7.1.8 | Ø 40 mm | 4 | Rm | 600 | 500 | 7.1 | 4260 | 7.1 | 3550 | 7810
7.1.9 | Ø 32 mm | 7 | Rm | 500 | 400 | 7.2 | 3600 | 7.2 | 2880 | 6480
7.1.10 | Ø 25 mm | 44 | Rm | 400 | 300 | 61 | 24400 | 61 | 18300 | 42700
7.2 | Stenciling & Identification | 1 | Lot | 15000 | 5000 | 1 | 15000 | 1 | 5000 | 20000
7.3 | Signage as per NFPA (For Example: Signage of Fire Hose Reel, Landing Valve etc.) | - | Lot | 40000 | 5000 |  | 0 | 0 | 0 | 0
Sub-total Carried to Summary | [9 empty] | 76990
8 | PIPE SUPPORT SYSTEM (SECTION 21 05 29)
8.1 | Engineered Pipe Support System | 1 | Lot | 45000 | 8000 | 1 | 45000 | 1 | 8000 | 53000
Sub-total Carried to Summary | [9 empty] | 53000
9 | MISCELLANEOUS
9.1 | Hydrostatic Testing | 1 | Lot | 0 | 15000 | 1 | 0 | 1 | 15000 | 15000
9.2 | Shop Drawings | 1 | Lot | 0 | 8000 | 1 | 0 | 1 | 8000 | 8000
9.3 | As Built Drawings | 1 | Lot | 0 | 5000 |  | 0 | 0 | 0 | 0
9.4 | Fire Stoping of Walls & Structure Openings (For Small Openings - Hilti FS - ONE or Approved Equivalent) - UL based Solution | 1 | Lot | 15000 | 2000 |  | 0 | 0 | 0 | 0
9.5 | Pipe Sleeves | 1 | Lot | 7000 | 2000 |  | 0 | 0 | 0 | 0
9.6 | Cutting, tapping and Connecting Fire Pipe to Existing Fire Piping as Shown in the drawing 03-FND-1283E-FA-F-14-02-200-00 | 1 | Lot | 0 | 15000 | 1 | 0 | 1 | 15000 | 15000
Sub-total Carried to Summary | [9 empty] | 38000
Grand Total Amount | [9 empty] | 844505

## Plumbing
DOLMEN CITY FAMILY AREA, SECOND FLOOR | [8 empty] | BILL OF QUANTITES
PLUMBING WORKS | [8 empty] | DATED: APRIL 12, 2023
BILL OF QUANTITES
ITEM NO. | DESCRIPTION | BILL OF QUANTITIES |  |  |  | RUNNING BILL NO 1
|  | Qty | UNIT | MATERIAL RATE | LABOUR RATE | Material |  | Labour |  | Total Amount
[6 empty] | Billed Qty | Amount | Billed Qty | Amount
1 | COLD WATER SUPPLY SYSTEM (DOMESTIC WATER)
1.1 | Poly Propylene Random Pipes - PPR Pipe PN-20 Including all Fittings and Accessories Required for Piping Installation, Testing & Commissioning (Section 22 11 16 & DS/1283E-22 11 16)
1.1.1 | Ø 65mm | - | Rm | 0 | Rate Only |  | 0 | 0 |  | 0
1.1.2 | Ø 50mm | 7.5 | Rm | 5371 | 413 |  | 0 | 0 | 0 | 0
1.1.3 | Ø 40mm | 4 | Rm | 3718 | 372 |  | 0 | 0 | 0 | 0
1.1.4 | Ø 32mm | 13 | Rm | 2024 | 331 |  | 0 | 0 | 0 | 0
1.1.5 | Ø 25mm | 25 | Rm | 1570 | 289 |  | 0 | 0 | 0 | 0
1.1.6 | Ø 20mm | 3 | Rm | 992 | 248 |  | 0 | 0 | 0 | 0
1.2 | Valve & Specialities
1.2.1 | Gate Valves - Brass (Including all Fittings and Accessories Required for Valve Installation) (Section 22 05 23)
1.2.1.1 | Ø 50mm | - | Nos. | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
1.2.1.2 | Ø 40mm | - | Nos. | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
1.2.1.3 | Ø 32mm | 3 | Nos. | 9295 | 826 | 3 | 27885 | 3 | 2478 | 30363
1.2.1.4 | Ø 25mm | 6 | Nos. | 7023 | 826 | 6 | 42138 | 6 | 4956 | 47094
1.2.2 | Air Vents (Including all Fittings and Accessories Required for Air Vent Installation. Refer Detail # FND/PH/07) (Section 22 68 35)
1.2.2.1 | Ø 25mm | 1 | Nos. | 7436 | 826 | 1 | 7436 | 1 | 826 | 8262
1.2.3 | Pressure Reducing Valves (PRV Assembly with Complete Accessories e.g Valves, Strainers, Pressure Gauges etc.) Refer Tender Drawings (Section 22 05 23)
1.2.3.1 | Ø 50mm | 1 | No. | 122286 | 2479 | 1 | 122286 | 1 | 2479 | 124765
1.3 | Engineered Pipe Support System as per make indicated in Approved list of Manufacturers in Tender document. | 1 | Lot | 37182 | 6610 | 1 | 37182 | 1 | 6610 | 43792
1.4 | Pressure Testing of Water Supply Piping (Minimum 150 psi) including all equipment, accessories and arrangements required for Pressure Testing | 1 | Lot | 0 | 20656 | 1 | 0 | 1 | 20656 | 20656
1.5 | Supply & Installation of Access Panel 300mm x 300mm in False Ceiling as shown in Tender Drawings | 5 | Nos. | 7436 | 826 |  | 0 | 0 | 0 | 0
1.6 | Supply & Installation of Access Panel 600mm x 600mm in False Ceiling as shown in Tender Drawings | 1 | No. | 14873 | 826 |  | 0 | 0 | 0 | 0
1.7 | Pressure Gauge With Siphon and Gauge Cock (Section 22 05 23) | 1 | No. | 8263 | 826 | 1 | 8263 | 1 | 826 | 9089
Sub-total Carried to Summary |  |  |  |  | 36354 |  | 245190 |  | 38831 | 284021
2 | HOT & TEMPERED WATER SUPPLY SYSTEM (DOMESTIC WATER)
2.1 | Poly Propylene Random Pipes - PPR Pipe PN-20 Including all Fittings and Accessories Required for Piping Installation, Testing & Commissioning (Section 22 11 16 & DS/1283E-22 11 16)
2.1.1 | Ø 32mm | - | Rm | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
2.1.2 | Ø 25mm | 32 | Rm | 1363 | 331 |  | 0 | 0 | 0 | 0
2.1.3 | Ø 20mm | - | Rm | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
2.2 | Valve & Specialities
2.2.1 | 3 Way Thermostatic Mixing Valve (Including all Fittings and Accessories Required for Valve Installation)
2.2.1.1 | Ø 25mm | 2 | Nos. | 71058 | 1653 |  | 0 | 0 | 0 | 0
2.2.2 | Gate Valves - Brass (Including all Fittings and Accessories Required for Valve Installation) (Section 22 05 23)
2.2.2.1 | Ø 32mm | - | No. | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
2.2.2.2 | Ø 25mm | 6 | Nos. | 8263 | 826 | 6 | 49578 | 6 | 4956 | 54534
2.2.2.3 | Ø 20mm | - | Nos. | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
2.2.3 | Air Vents (Including all Fittings and Accessories Required for Air Vent Installation. Refer Detail # FND/PH/07) (Section 22 68 35)
2.2.3.1 | Ø 25mm | 3 | Nos. | 7436 | 826 | 3 | 22308 | 3 | 2478 | 24786
2.3 | Hot & Tempered Water Pipe Insulation With Cladding Where Applicable as per (DS/1283E-22 07 19 & Section 22 07 19)
2.3.1 | Ø 32mm | - | Rm | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
2.3.2 | Ø 25mm | 32 | Rm | 3512 | 496 |  | 0 | 0 | 0 | 0
2.3.3 | Ø 20mm | - | Rm | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
2.4 | Pipe Support System as per make indicated in Approved list of Manufacturers in Tender document. | 1 | Lot | 39660 | 9915 | 1 | 39660 | 1 | 9915 | 49575
2.5 | Pressure Testing of Hot Water Supply Piping (Including all equipment, accessories and arrangements required for Pressure Testing) | 1 | Lot | 0 | 12394 | 1 | 0 | 1 | 12394 | 12394
2.6 | Supply & Installation of Electric Operated Hot Water Heaters (Section 22 33 00 & DS/1283E-22 33 00)
2.6.1 | Supply, Installation and Commissioning of Electric Operated Hot Water Heater EHWH/01 & 02, 30L heating capacity. Including all fittings and accessories required from installation till commissioning of Hot Water Heater. | 2 | Nos. | 65274 | 2479 | 2 | 130548 | 2 | 4958 | 135506
Sub-total Carried to Summary |  |  |  |  | 28920 |  | 242094 |  | 34701 | 276795
3 | SOIL, WASTE & VENT DRAIN SYSTEM
3.1 | Building Toilet & Kitchen Drainage Pipe Conformance to BS-EN1329 (uPVC-NON-PRESSURE CLASS FOR ø ≥ 50mm & uPVC-PRESSURE CLASS-E for ø < 50mm) Including all Fittings and Accessories Required for Piping Installation, Testing and Commissioning e.g Elbows, Y, Double Y, Reducers, Sockets etc. (Section 22 13 20 & DS/1283E-22 13 20)
3.1.1 | Ø 100mm | 18 | Rm | 4049 | 826 |  | 0 | 0 | 0 | 0
3.1.2 | Ø 75mm | 5 | Rm | 3123 | 826 |  | 0 | 0 | 0 | 0
3.1.3 | Ø 50mm | - | Rm | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
3.1.4 | Ø 40mm | 29 | Rm | 1405 | 496 |  | 0 | 0 | 0 | 0
3.1.5 | Ø 32mm | - | Rm | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
3.2 | Building Vent Pipe Conformance to BS-EN1329 (uPVC-NON-PRESSURE CLASS FOR ø ≥ 50mm & uPVC-PRESSURE CLASS-E for ø < 50mm) Including all Fittings and Accessories Required for Piping Installation, Testing and Commissioning e.g Elbows, Y, Double Y, Reducers, Sockets etc. (Section 22 13 20 & DS/1283E-22 13 20)
3.2.1 | Ø 75mm | - | Rm | 0 | Rate Only | 0 | Rate Only | 0 | Rate Only
3.2.2 | Ø 50mm | 10 | Rm | 1900 | 413 |  | 0 | 0 | 0 | 0
3.2.3 | Ø 40mm | 15 | Rm | 1405 | 413 |  | 0 | 0 | 0 | 0
3.3 | Drain Accessories (Section 22 11 19)
3.3.1 | SS Floor Drain with Multifloor Trap - Refer Detail # FND/SDS/20 (Section 22 11 19) | [7 empty] | .
3.3.1.1 | Ø 75mm | 5 | Nos. | 7436 | 826 |  | 0 | 0 | 0 | 0
3.3.2 | Floor Clean Out (Sewerage) Refer Detail # FND/SDS/18 (Section 22 11 19)
3.3.2.1 | Ø 100mm | 2 | Nos. | 5784 | 826 |  | 0 | 0 | 0 | 0
3.3.3 | Multifloor Trap (Section 22 11 19)
3.3.3.1 | Ø 100mm | 1 | No. | 6197 | 826 |  | 0 | 0 | 0 | 0
3.4 | Pipe Support System for Drain Pipe as per make indicated in Approved list of Manufacturers in Tender document. | 1 | Lot | 26440 | 6610 |  | 0 | 0 | 0 | 0
3.5 | Head Testing of Soil, waste and vent piping (Including all equipment, accessories and arrangements required for Head Testing) | 1 | Lot | 0 | 12394 |  | 0 | 0 | 0 | 0
Sub-total Carried to Summary |  |  |  |  | 24456 |  | 0 |  | 0 | 0
4 | PLUMBING FIXTURES & FITTINGS
4.1 | Supply & Installation of Wall Mounted Western WC With Concealed Flush Tank and Angle valves and associated accessories (Including test run) (Section 22 41 10 & DS-1283E-22 41 10) | 3 | Nos. | 133854 | 8263 |  | 0 | 0 | 0 | 0
4.2 | Supply & Installation of Counter Sunk Wash Basin with Waste, Bottle Trap & Tee Stop-Cock (Including test run) (Section 22 41 10 & DS-1283E-22 41 10) | 3 | Nos. | 82626 | 6610 |  | 0 | 0 | 0 | 0
4.3 | Supply & Installation of Wash Basin Single Lever Mixer With Flexible Hoses (Including test run) (Section 22 41 10 & DS-1283E-22 41 10) | 3 | Nos. | 45444 | 6610 |  | 0 | 0 | 0 | 0
4.4 | Supply & Installation of Single Bowl Kitchen Sink With Sink Mixer, Waste, Tee Stop-Cock (Including test run) (Section 22 41 10 & DS-1283E-22 41 10) | 1 | No. | 59491 | 4958 |  | 0 | 0 | 0 | 0
4.5 | Supply & Installation of Hand Operated Shower Spray With Angle Valve (Including test run) (Section 22 41 10 & DS-1283E-22 41 10) | 3 | Nos. | 11981 | 826 |  | 0 | 0 | 0 | 0
4.6 | Supply & Installation of Toilet Roll Holder (Section 22 41 10 & DS-1283E-22 41 10) (Including test run) | 3 | Nos. | 6610 | 413 |  | 0 | 0 | 0 | 0
4.7 | Supply & Installation of Soap Dispenser (Section 22 41 10 & DS-1283E-22 41 10) (Including test run) | 5 | Nos. | 9089 | 826 |  | 0 | 0 | 0 | 0
4.8 | Supply & Installation of bibcock for janitor room (Including test run) (Section 22 41 10 & DS-1283E-22 41 10) | 1 | No. | 8474 | 826 |  | 0 | 0 | 0 | 0
4.9 | Supply & Installation of Single Lever Mixer with Pullout Spout & Flexible Hoses (Including test run) for Diaper Changing Station (Section 22 41 10 & DS-1283E-22 41 10) | 3 | Nos. | 65274 | 2479 |  | 0 | 0 | 0 | 0
Sub-total Carried to Summary |  |  |  |  | 31811 |  | 0 |  | 0 | 0
5 | MISCELLANEOUS
5.1 | Adaptors/flanges/unions required to join any two dis-similar material pipes (PPR/UPVC) | 1 | Lot | 24788 | 41313 | 1 | 24788 | 1 | 41313 | 66101
5.2 | Shop Drawings | 1 | Lot | 0 | 12394 | 1 | 0 | 1 | 12394 | 12394
5.3 | As Built Drawings | 1 | Lot | 0 | 8263 |  | 0 | 0 | 0 | 0
5.4 | Pipe Sleeves/Core Cutting where required on RCC Walls & Slabs including core sealing by using material specific for core sealing application - Refer Tender Drawings and relevant Standard Details | 1 | Lot | 16525 | 2479 |  | 0 | 0 | 0 | 0
5.5 | Connection of New Water Supply, Drainage & Vent piping with Existing risers by taking tap-offs, complete in all respect - Refer Tender Drawings | 1 | Lot | 0 | 9915 | 1 | 0 | 1 | 9915 | 9915
Sub-total Carried to Summary | [6 empty] | 24788 |  | 63622 | 88410
Grand Total Amount Rs | [6 empty] | 512072 |  | 137154 | 649226