## Summary
M/S AAA Partnership Pvt Ltd |  |  |  | 2025-03-07
RUNNING BILL NO 1 FOR HVAC WORK - NICVD JPMC
| Description of Work | Supply Amount | Installation Amount | Total
A | HVAC Works | 20733554.05 | 2495776.75 | 23229330.8
B | Grand Total | 20733554.05 | 2495776.75 | 23229330.8
C | Less Discount 13% | 2695362.0265 | 324450.9775 | 3019813.004
D | After Discount | 18038192.0235 | 2171325.7725 | 20209517.796
E | Less Special Discount 07% | 1262673.4416 | 151992.8041 | 1414666.2457
F | After Discount | 16775518.5819 | 2019332.9684 | 18794851.5503
G | SST 15% | 0 | 302899.9453 | 302899.9453
H | Grand Total Amount Rs | 16775518.5819 | 2322232.9137 | 19097751.4955

## Table 1
S. No. |  | DESCRIPTION | UNIT | BILL OF QUANTITIES | [5 empty] | RUNNING BILL NO 1 | [5 empty] | Reason for variation
|  |  |  | QTY | MATERIAL |  | LABOUR |  | TOTAL | QTY | MATERIAL |  | LABOUR |  | TOTAL
[5 empty] | RATE | AMOUNT | RATE | AMOUNT | AMOUNT |  | RATE | AMOUNT | RATE | AMOUNT | AMOUNT
All works shall be completed, tested and commissioned as per drawings, specifications and as per instruction of Consultant
1 |  | Unloading, rigging, lifting, placement, installation, testing and commissioning of (OWNER SUPPLIED) VRF / VRV air conditioning units with multiple indoor evaporative units of different capacities with central controller complete in all respects, ready to operate including supply & installation of supports, brackets, flexible duct connector / connection, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 1.1 | BF-CU-01 (11 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 40000 | 40000 | 85000 | 85000 | 125000 | 0 | 40000 | 0 | 85000 | 0 | 0
| 1.2 | BF-CU-02 (11 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 40000 | 40000 | 85000 | 85000 | 125000 | 0 | 40000 | 0 | 85000 | 0 | 0
| 1.3 | RF-CU-01 (14 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 50000 | 50000 | 95000 | 95000 | 145000 | 0 | 50000 | 0 | 95000 | 0 | 0
| 1.4 | GF-CU-01 (09 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 45000 | 45000 | 80000 | 80000 | 125000 | 0 | 45000 | 0 | 80000 | 0 | 0
| 1.5 | GF-CU-02 (09 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 40000 | 40000 | 80000 | 80000 | 120000 | 0 | 40000 | 0 | 80000 | 0 | 0
| 1.6 | GF-CU-03 (09 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 40000 | 40000 | 80000 | 80000 | 120000 | 0 | 40000 | 0 | 80000 | 0 | 0
| 1.7 | FF-CU-01 (06 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 35000 | 35000 | 60000 | 60000 | 95000 | 0 | 35000 | 0 | 60000 | 0 | 0
| 1.8 | FF-CU-02 (10 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 45000 | 45000 | 80000 | 80000 | 125000 | 0 | 45000 | 0 | 80000 | 0 | 0
| 1.9 | FF-CU-03 (09 Indoors + 1 Outdoor Condensing Unit Consisted of Different Modules) | Set | 1 | 40000 | 40000 | 75000 | 75000 | 115000 | 0 | 40000 | 0 | 75000 | 0 | 0
2 |  | Unloading, installation, testing and commissioning of (OWNER SUPPLIED) single split units of different capacities including supply & installation of supports, brackets, rubber isolators, flashing, power wiring from isolation box to unit (10' to 15' radius), control wiring termination etc, complete in all respects ready to operate as per schedule, specification, drawings and as per instruction of consultant.
| 2.1 | BF-WM-01 | No. | 1 | 5000 | 5000 | 5000 | 5000 | 10000 | 0 | 5000 | 0 | 5000 | 0 | 0
| 2.2 | GF-WM-01 | No. | 1 | 5000 | 5000 | 5000 | 5000 | 10000 | 0 | 5000 | 0 | 5000 | 0 | 0
| 2.3 | GF-WM-01 | Nos. | 2 | 5000 | 10000 | 5000 | 10000 | 20000 | 0 | 5000 | 0 | 5000 | 0 | 0
| 2.4 | FF-WM-01 | No. | 1 | 5000 | 5000 | 5000 | 5000 | 10000 | 0 | 5000 | 0 | 5000 | 0 | 0
| 2.5 | RF-AC-01 | Nos. | 3 | 5000 | 15000 | 5000 | 15000 | 30000 | 0 | 5000 | 0 | 5000 | 0 | 0
3 |  | Supply & installation of refrigerant pipes for all units (liquid + gas) with 1/2" thick expended close cell rubber foam insulation, PVC tape wrapping including additional gas charging if required and installation of branch distributor (supplied with VRF / VRV units) complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. (VRF / VRV Units copper pipes sizes & quantities shall be vary according to the equipment brand / selection) For VRF units all hard pipes except 1/4"
| 3.1 | 1/4" dia | Rft | 950 | 522 | 495900 | 150 | 142500 | 638400 | 0 | 522 | 0 | 150 | 0 | 0
| 3.2 | 3/8" dia | Rft | 1405 | 897 | 1260285 | 150 | 210750 | 1471035 | 2443.67 | 897 | 2191971.99 | 150 | 366550.5 | 2558522.49 | Qty exceed due to NIL Qty of 1/4"
| 3.3 | 1/2" dia | Rft | 1425 | 1340 | 1909500 | 175 | 249375 | 2158875 | 1593.15 | 1340 | 2134821 | 175 | 278801.25 | 2413622.25 | Drawing Ref AC-01, AC-02, AC-03
| 3.4 | 5/8" dia | Rft | 1395 | 1715 | 2392425 | 200 | 279000 | 2671425 | 1161.15 | 1715 | 1991372.25 | 200 | 232230 | 2223602.25
| 3.5 | 3/4" dia | Rft | 430 | 2115 | 909450 | 200 | 86000 | 995450 | 400.41 | 2115 | 846867.15 | 200 | 80082 | 926949.15
| 3.6 | 7/8" dia | Rft | 75 | 2525 | 189375 | 225 | 16875 | 206250 | 163.96 | 2525 | 413999 | 225 | 36891 | 450890 | Drawing Ref AC-01, AC-02, AC-03
| 3.7 | 1 1/8" dia (also for 1") | Rft | 970 | 3508 | 3402760 | 250 | 242500 | 3645260 | 437.52 | 3508 | 1534820.16 | 250 | 109380 | 1644200.16
| 3.8 | 1 3/8" dia (also for 1-1/4") | Rft | 5 | 4900 | 24500 | 275 | 1375 | 25875 | 33.5 | 4900 | 164150 | 275 | 9212.5 | 173362.5 | Drawing Ref AC-03
| 3.9 | 1 5/8" dia (also for 1-1/2") | Rft | 5 | 6400 | 32000 | 300 | 1500 | 33500 | 0 | 6400 | 0 | 300 | 0 | 0
| 3.1 | For single split units all soft pipes 1/4" dia | Rft | 550 | 540 | 297000 | 150 | 82500 | 379500 | 276 | 540 | 149040 | 150 | 41400 | 190440
| 3.11 | 1/2" dia | Rft | 550 | 878 | 482900 | 200 | 110000 | 592900 | 276 | 878 | 242328 | 200 | 55200 | 297528
| 3.12 | 3/8" dia | Rft | 10 | 700 | 7000 | 200 | 2000 | 9000 | 0 | 700 | 0 | 200 | 0 | 0
| 3.13 | 5/8" dia | Rft | 10 | 1125 | 11250 | 200 | 2000 | 13250 | 0 | 1125 | 0 | 200 | 0 | 0
4 |  | Supply & installation of control wiring in G.I. conduit for external / PVC conduit for internal area from outdoor unit to indoor unit including microprocessor & central controller wiring & fixing / installation of central controller supplied with units complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Lot | 1 | 1150000 | 1150000 | 200000 | 200000 | 1350000 | 1 | 1150000 | 1150000 | 200000 | 200000 | 1350000
5 |  | Supply & installation of 18 SWG powder quoted G.I. sheet metal tray with cover for refrigerant pipes and control wiring exposed to weather area and for main hall internal area complete in all respects including hangers, supports brackets complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 600 | 650 | 390000 | 100 | 60000 | 450000 | 0 | 650 | 0 | 100 | 0 | 0
6 |  | Supply & installation of uPVC make class D SCH-40 pipe for internal area with 3/8" thick expanded closed cell rubber foam insulation, PVC tape wrapping for condensate drain including support hangers, excavation, cutting, chiseling and making good complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 6.1 | 1" dia | Rft | 1600 | 445 | 712000 | 80 | 128000 | 840000 | 1768 | 445 | 786760 | 80 | 141440 | 928200 | Drawing Ref AC-01, AC-02, AC-03
| 6.2 | 1.25" dia | Rft | 150 | 540 | 81000 | 100 | 15000 | 96000 | 65 | 540 | 35100 | 100 | 6500 | 41600
| 6.3 | 1.5" dia | Rft | 10 | 640 | 6400 | 125 | 1250 | 7650 | 0 | 640 | 0 | 125 | 0 | 0
| 6.4 | 2" dia | Rft | 10 | 950 | 9500 | 150 | 1500 | 11000 | 0 | 950 | 0 | 150 | 0 | 0
7 |  | Supply & installation of copper isolation valves, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant.
| 7.1 | 1/4" dia | Nos. | 67 | 9600 | 643200 | 400 | 26800 | 670000 | 66 | 9600 | 633600 | 400 | 26400 | 660000
| 7.2 | 3/8" dia | Nos. | 21 | 10120 | 212520 | 450 | 9450 | 221970 | 21 | 10120 | 212520 | 450 | 9450 | 221970
| 7.3 | 1/2" dia | Nos. | 70 | 10925 | 764750 | 500 | 35000 | 799750 | 70 | 10925 | 764750 | 500 | 35000 | 799750
| 7.4 | 5/8" dia | Nos. | 26 | 11270 | 293020 | 500 | 13000 | 306020 | 26 | 11270 | 293020 | 500 | 13000 | 306020
| 7.5 | 3/4" dia | Nos. | 1 | 27600 | 27600 | 600 | 600 | 28200 |  | 27600 |  | 600
| 7.6 | 7/8" dia | Nos. | Rate only | 28750 | 0 | 600 | 0 | 0 | 0 | 28750 | 0 | 600 | 0 | 0
| 7.7 | 1 1/8" dia (also for 1") | Nos. | Rate only | 31875 | 0 | 700 | 0 | 0 | 0 | 31875 | 0 | 700 | 0 | 0
| 7.8 | 1 3/8" dia (also for 1-1/4") | Nos. | Rate only | 42000 | 0 | 800 | 0 | 0 | 0 | 42000 | 0 | 800 | 0 | 0
| 7.9 | 1 5/8" dia (also for 1-1/2") | Nos. | Rate only | 45000 | 0 | 1000 | 0 | 0 | 0 | 45000 | 0 | 1000 | 0 | 0
8 |  | Supply, installation, testing and commissioning of ventilation fans as per mentioned in schedule, including supply & installation of vibration isolator, flexible duct connection / connector, support & hangers, power wiring from isolation box to unit (10' to 15' radius) etc, complete in all respects ready to operate as per drawings, specification and as per instruction of consultant.
| 8.1 | BF-EAF-01 | No. | 1 | 44250 | 44250 | 2000 | 2000 | 46250 | 1 | 44250 | 44250 | 2000 | 2000 | 46250
| 8.2 | BF-EAF-02 | No. | 1 | 78175 | 78175 | 3000 | 3000 | 81175 | 1 | 78175 | 78175 | 3000 | 3000 | 81175
| 8.3 | BF-EAF-03 | No. | 1 | 218300 | 218300 | 5000 | 5000 | 223300 | 1 | 218300 | 218300 | 5000 | 5000 | 223300
| 8.4 | GF-EAF-01 | No. | 1 | 44250 | 44250 | 2000 | 2000 | 46250 | 1 | 44250 | 44250 | 2000 | 2000 | 46250
| 8.5 | GF-EAF-02 | No. | 1 | 44250 | 44250 | 2500 | 2500 | 46750 | 1 | 44250 | 44250 | 2500 | 2500 | 46750
| 8.6 | GF-EAF-03 | No. | 1 | 72250 | 72250 | 5000 | 5000 | 77250 | 1 | 72250 | 72250 | 5000 | 5000 | 77250
| 8.7 | FF-EAF-01 | No. | 1 | 44250 | 44250 | 2000 | 2000 | 46250 | 1 | 44250 | 44250 | 2000 | 2000 | 46250
| 8.8 | FF-EAF-02 | No. | 1 | 44250 | 44250 | 2000 | 2000 | 46250 | 1 | 44250 | 44250 | 2000 | 2000 | 46250
| 8.9 | FF-EAF-03 | No. | 1 | 72250 | 72250 | 3000 | 3000 | 75250 | 1 | 72250 | 72250 | 3000 | 3000 | 75250
| 9 | FF-EAF-04 | No. | 1 | 21387 | 21387 | 2000 | 2000 | 23387 | 1 | 21387 | 21387 | 2000 | 2000 | 23387
| 9.1 | RF-EAF-01 | Nos. | 2 | 460000 | 920000 | 10000 | 20000 | 940000 | 2 | 460000 | 920000 | 10000 | 20000 | 940000
| 9.2 | RF-EAF-02 | Nos. | 2 | 488000 | 976000 | 10000 | 20000 | 996000 | 2 | 488000 | 976000 | 10000 | 20000 | 996000
9 |  | Supply, fabrication and installation of machine made G.I sheet metal duct different sections supply, return, fresh & exhaust air including plenums, splitter dampers, guide vanes, flexible duct connector/connection, access door, transformation, plenums chambers, wooden frame, anchors supports & hangers complete in all respects ready to operate as per drawings, specification, instruction of consultant. | Sqft | 7050 | 425 | 2996250 | 75 | 528750 | 3525000 | 6316.3 | 425 | 2684427.5 | 75 | 473722.5 | 3158150
10 |  | Supply & installation of 3/4" thick 25kg/m3 density rubber foam (XLPE) adhesive insulation with aluminum foil over internal area ducts (except toilet exhaust duct), complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqft | 4900 | 450 | 2205000 | 70 | 343000 | 2548000 | 4243.1 | 450 | 1909395 | 70 | 297017 | 2206412
11 |  | Supply & installation of aluminum fabricated powder coated exhaust & fresh Air louvers including wooden frame, rain protection sheet bird mesh etc complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Sqin | 3000 | 28 | 84000 | 5 | 15000 | 99000 | 0 | 28 | 0 | 5 | 0 | 0
12 | 12.1 | Supply, installation of Aluminum fabricated, powder coated Grills, Diffusers and Registers for supply air, return air, exhaust air & fresh air of different sizes (Grade A ), wooden frame, supports and other accessories etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. Registers / Diffuser with Damper | Sqin | 9850 | 28 | 275800 | 5 | 49250 | 325050 | 0 | 28 | 0 | 5 | 0 | 0
| 12.2 | Grills | Sqin | 1000 | 25 | 25000 | 5 | 5000 | 30000 | 0 | 25 |  | 5
| 12.3 | Linear Slot 6,000 Series 2 Slots of 3/4" | Rft | 95 | 1450 | 137750 | 300 | 28500 | 166250 | 0 | 1450 | 0 | 300 | 0 | 0
| 12.4 | Exhaust Air Disc Valves 6" dia | Nos. | 68 | 2500 | 170000 | 500 | 34000 | 204000 | 0 | 2500 | 0 | 500 | 0 | 0
13 |  | Supply & installation of flexible duct including hangers, jubilee clamp complete in all respects as per specification, drawings & as per instruction of consultant. 6" dia | Rft | 5 | 450 | 2250 | 100 | 500 | 2750 | 0 | 450 | 0 | 100 | 0 | 0
14 |  | Supply & installation of butterfly damper for above flexible duct with gas kits, nut bolts, complete in all respects, ready to operate as per specification, drawings & as per instruction of consultant. 6" dia | Nos. | 1 | 3000 | 3000 | 1000 | 1000 | 4000 | 0 | 3000 | 0 | 1000 | 0 | 0
15 |  | Supply & installation of Volume Control Damper in 16 SWG G.I sheet metal with gas kits, nut bolts, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Sqin | 3000 | 27 | 81000 | 5 | 15000 | 96000 | 0 | 27 | 0 | 5 | 0 | 0
16 |  | Supply and installation of Fire Damper with linkage & fuse complete in all respects ready to operate as per specification, drawings & as per instruction of Consultant. | Sqin | 2000 | 32 | 64000 | 5 | 10000 | 74000 | 0 | 32 | 0 | 5 | 0 | 0
17 |  | Supply & installation of Motorized Damper with gas kits, nut bolts, including pressure transmeter, controller & control wiring, complete in all respects, ready to operate as per specification, drawings & as per instruction of Consultant. 22" x 14" | Nos. | 2 | 275000 | 550000 | 10000 | 20000 | 570000 | 0 | 275000 | 0 | 10000 | 0 | 0
18 |  | Integration of smoke control system using I/O modules with the fire alarm control panel of building with fire resistant wiring & fixing accessories, complete in all respects, ready to operate as per drawings, specification and instruction of consultant. | Job. | 1 | 485000 | 485000 | 95000 | 95000 | 580000 | 0 | 485000 | 0 | 95000 | 0 | 0
19 |  | Painting & Identification work on supports, hangers, platform of condensing units etc complete in all respects with one coat of ICI make Red lead oxide primer & two coats of ICI make enamel paint complete in all respects ready to operate as per drawings, specification, instruction and approval of Consultant. | Lot | 1 | 30000 | 30000 | 30000 | 30000 | 60000 | 0 | 30000 | 0 | 30000 | 0 | 0
20 |  | Testing, balancing and commissioning of air side of the system (from independent agency) complete in all respects including air measurement & balancing, temp, pressure & electrical data of related equipment etc. complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 0 | 0 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 100000 | 0 | 0
21 |  | Making of Shop drawings on Auto CAD (latest version) with section details, equipment foundation details etc, complete in all respects ready to operate as per specification, drawings and as per instruction of consultant. | Job. | 1 | 15000 | 15000 | 15000 | 15000 | 30000 | 1 | 15000 | 15000 | 15000 | 15000 | 30000
22 |  | Making of As Built drawings Auto CAD (latest version), Documentation Technical / Operational Manual & LOG Book for each equipment etc, complete in all respects ready to operate as per specification, drawings and as per instruction of Consultant. | Job. | 1 | 10000 | 10000 | 10000 | 10000 | 20000 | 0 | 10000 | 0 | 10000 | 0 | 0
|  | Total Cost of Works with I.Tax Rs. |  |  |  | 25832997 |  | 4045475 | 29878472 |  |  | 20733554.05 |  | 2495776.75 | 23229330.8